## Slide 1: Solid Works - SketchUp Project Procurement Strategy MGMT-6063-(01)-24W
Group 10 | 
Divya Mathew S M Rakibul Basher Gihan Shamike Liyanage | 1192361 1168369 1142109
Submitted for: Prof. Mona Brennan-Coles Submitted Date: 08/02/2024 | 
Notes: Good morning/afternoon, everyone. Today, I'll be presenting our project procurement plan for the Solid Works - SketchUp project to the IT Support & Services Department (ISSD). Let's dive into it.

## Slide 2: Project Procurement Strategy
Our comprehensive approach to ensure effective software selection, negotiation, installation, and use is part of our procurement strategy for new software for the IT Support & Services Department (ISSD) of the Office Furniture Manufacturing organization. Using innovation and logical reasoning, this method adapts basic procurement concepts to the specific needs of the company.
Notes: Our project procurement strategy aims to ensure the seamless acquisition and implementation of new software solutions for the ISSD. It encompasses various aspects, including delivery methods, contract payment types, procurement phases, resource management, risk management, user role identification, benefits evaluation, vendor selection, license and support contracts, configuration and implementation, training, and benefits measurement.

## Slide 3: Procurement Overview
SketchUp project, responding to ISSD relocation, aims to procure software for 1,000+ employees, prioritizing operational efficiency and alignment with organizational goals for transition..
Key Components of the SketchUp project:
Purchase | Meticulous selection and acquisition of tailored software through market research, vendor evaluations, and contract negotiations.
Back-up & Data Migration | Ensuring smooth transition by minimizing data loss or corruption through secure data backup and migration.
Installation | Setting up new equipment at user desks, including unpacking, configuration, and network connectivity.
Training | Extensive staff training on new hardware and software features to enhance daily work efficiency.
Notes: The procurement overview outlines the strategic approach we'll take to identify, procure, and implement software solutions tailored to the ISSD's needs. This includes market research, vendor evaluations, negotiation of contracts, and risk assessment to ensure smooth transitions and operational efficiency.
The impending relocation of our IT Support & Services Department to a new location within the next eight months has sparked the launch of the SketchUp project. This initiative is strategically crafted to identify, procure, and implement new software solutions tailored to our industry's unique needs. With a workforce exceeding 1,000 employees, the project emphasizes the critical importance of software that not only boosts operational efficiency but also seamlessly aligns with our organizational goals, ensuring a smooth transition and uninterrupted service delivery.
Let's delve into the key components of the SketchUp project:
Firstly, we're diving into the procurement process. This involves meticulously selecting and acquiring software solutions that resonate with our department's specific needs and challenges. It encompasses extensive market research, vendor evaluations, and contract negotiations to secure the most suitable software solutions for our requirements.
Next up, we have the crucial task of backing up and migrating data. A comprehensive plan is imperative to ensure a seamless transition to the new laptops, minimizing the risk of data loss or corruption. Our top priority is guaranteeing the security and integrity of sensitive data throughout the migration process.
Then comes the installation phase. We'll be setting up the new laptops and peripherals at user desks in our new location. This involves unpacking the equipment, configuring hardware components, and ensuring proper connectivity to the network and other essential systems.
As last point, we're prioritizing staff training. Extensive training sessions will be provided to familiarize our team with the new laptops and accessories. The aim is to equip our staff with the necessary skills to effectively utilize the technology in their daily work.

## Slide 4: Procurement (Detailed) Description
The SketchUp project's procurement process ensures minimal disruption for the ISSD relocation by meticulously acquiring resources covering services, software, hardware, and training to maintain operational effectiveness and continuity.
Objective: Procure 1000 sets of laptops and peripherals tailored to specific roles for efficient task performance during relocation.
Specifications: For graphic designers, support staff managers, software developers, front desk workers, and security staff.
Considerations: Preferred colors, sizes, and accessories to enhance user productivity and comfort.
Licensing: Importance of compliance with licensing agreements to avoid interruptions in operational continuity.
Implementation Deadline: Successful installation and configuration of software by February 12th, 2024, to match department workflows and procedures.
Long-term Stability: Prices of goods and services will remain unchanged for five years to ensure stability.
Overall Impact: Strategic initiative leveraging technology to enhance organizational growth and operational efficiency during relocation.
Notes: The detailed procurement description covers specific requirements, including computer specifications, accessories, licenses, implementation, and configuration of software. It also addresses the backup and migration of data, installation of hardware, and facilitation of training sessions for staff.
The SketchUp project's procurement process is meticulously designed to minimize disruption for the impending ISSD relocation by acquiring resources covering services, software, hardware, and training, thereby ensuring operational effectiveness and continuity.
Objective: Our primary objective is to procure 1000 sets of laptops and peripherals tailored to specific roles, facilitating efficient task performance during the relocation process.
Specifications: We'll cater to the diverse needs of our workforce, including graphic designers, support staff managers, software developers, front desk workers, and security staff. Each role will have customized sets of laptops and peripherals tailored to enhance productivity and comfort, taking into account preferred colors, sizes, and accessories.
Considerations: User productivity and comfort are paramount considerations in selecting laptops and peripherals. We'll ensure that the chosen equipment not only meets our technical requirements but also enhances the user experience.
Licensing: Compliance with licensing agreements is essential to avoid interruptions in operational continuity. We'll prioritize vendors who offer clear and comprehensive licensing agreements to ensure legal compliance and seamless operation of software solutions.
Implementation Deadline: To align with department workflows and procedures, successful installation and configuration of software must be completed by February 12th, 2024. This deadline is crucial to maintaining operational efficiency during the relocation process.
Long-term Stability: To provide stability and predictability, prices of goods and services will remain unchanged for five years. This commitment ensures financial stability and allows us to plan for the future with confidence.
Overall Impact: The SketchUp project represents a strategic initiative leveraging technology to enhance organizational growth and operational efficiency during the relocation process. By carefully procuring resources tailored to our specific needs, we aim to ensure a smooth transition and maintain uninterrupted service delivery.

## Slide 5: Procurement Process
Identification of Requirements: Gather software needs from project manager, IT support staff, and end users.
Market Research: Conduct thorough market research to identify potential suppliers and assess available software.
Choosing a Vendor: Request proposals from suppliers and evaluate based on features, cost, and support
Risk Assessment of the Proposal: Compare vendor proposals to predetermined standards to select the best solution.
Preparing the Procurement Document: Define detailed specifications and requirements for software acquisition.
Conducting Procurement: Establish timelines for each step of the procurement process.
Setting Up Criteria for Evaluation: Develop a systematic framework for evaluating vendor proposals.
Contract Negotiation and Vendor Selection: Negotiate contract terms and select the best vendor based on preset standards.
Facilitating Seamless Software Acquisition and Implementation: Streamline software acquisition and implementation through comprehensive planning.
Negotiation of Contracts: Negotiate contract terms with chosen vendor to meet organizational needs and budget.
Managing and Concluding Procurement: Complete contracts with chosen vendors, including acceptance criteria.
Planning for Implementation: Create implementation plan with deployment deadlines and milestones.
Instruction and Distribution: Plan training sessions for end users and IT support staff to ensure efficient software use.
Notes: The procurement process involves several key steps, including identifying requirements, market research, vendor selection, risk assessment, preparing procurement documents, negotiation of contracts, managing procurement, planning for implementation, and monitoring and evaluation.
The Procurement Process within the SketchUp project plays a pivotal role in orchestrating the strategic acquisition of essential resources necessary for the seamless transition of the IT Support & Services Department (ISSD) to its new location.
Let's break down the acquisition procedure and its key components:
Identification of Requirements: Feedback from stakeholders such as the project manager, IT support staff, and end users is gathered to determine the software needs of the department.
Market Research: Thorough market research is conducted to identify potential suppliers and evaluate available software solutions based on features, cost, and support.
Choosing a Vendor: Proposals are requested from selected suppliers, and each proposal is evaluated to determine its suitability according to predetermined standards.
Risk Assessment of the Proposal: The vendor offering the best solution is selected by comparing proposals against predetermined standards.
Preparing the Procurement Document: A comprehensive procurement document is created, detailing the software's functional and technical requirements, timelines, and evaluation criteria.
Conducting Procurement: Well-defined timelines are established for each step of the procurement process, facilitating efficient resource allocation and timely completion of tasks.
Setting Up Criteria for Evaluation: A systematic framework for evaluating vendor proposals is established, guiding the vendor selection process.
Contract Negotiation and Vendor Selection: Contract terms and pricing are negotiated with the chosen vendor to ensure they meet organizational needs and budgetary restrictions.
Managing and Concluding the Procurement: Contracts are finalized, including terms and conditions, payment plans, and service level agreements, with chosen vendors.
Planning for Implementation: A thorough implementation plan is developed, outlining software deployment deadlines, milestones, and roles.
Instruction and Distribution: End-user and IT support staff training sessions are planned to ensure a smooth transition and efficient use of the new software.
By following these steps meticulously, the Procurement Process ensures the successful acquisition and implementation of software solutions tailored to the needs of the IT Support & Services Department, thereby enhancing operational efficiency and facilitating the relocation process.

## Slide 6: Procurement Risk Analysis
Risks | Consequences | Mitigation
Vendor Reliability | Delayed delivery, substandard products | Perform thorough vendor background checks.
Budget Overruns | Financial strain, project delays | Develop contingency plans, monitor expenses.
Compatibility Issues | System integration failures | Conduct compatibility tests, pilot phases.
Scope Creep | Project scope expansion | Establish clear scope boundaries, change control procedures.
Technical Challenges | Implementation setbacks | Engage technical experts, conduct risk assessments.
Regulatory Compliance | Legal penalties, reputational damage | Stay updated on regulations, seek legal counsel.
Staff Resistance | Low user adoption, productivity loss | Provide comprehensive training, address concerns proactively.
Notes: In the procurement risk analysis for the SketchUp project, various risks have been identified, along with their potential consequences and mitigation strategies. Vendor reliability presents a risk of delayed delivery or substandard products, which could impede project timelines and quality. To address this, thorough vendor background checks are proposed to ensure reliable and timely deliveries. Budget overruns pose another significant risk, potentially leading to financial strain and project delays. Mitigation strategies include developing contingency plans and closely monitoring project expenses to ensure adherence to budgetary constraints. Compatibility issues, such as system integration failures, may arise, necessitating comprehensive compatibility tests and pilot phases to ensure seamless software integration. Moreover, the risk of scope creep, technical challenges during implementation, regulatory compliance issues, and staff resistance to change are acknowledged. Strategies to mitigate these risks involve establishing clear scope boundaries, engaging technical experts early, staying updated on regulations, providing comprehensive staff training, and addressing concerns proactively. Through a systematic approach to risk assessment and mitigation, the SketchUp project aims to protect itself from setbacks and ensure the successful acquisition and deployment of software.

## Slide 7: Selection Criteria and Response Evaluation
The Selection Criteria and Response Evaluation process for the SketchUp project involves establishing specific criteria to assess vendor proposals. This ensures the selection of the most suitable solution, aligned with organizational objectives. Two tables outline the criteria and evaluate vendor responses for informed decision-making.
Criteria | Description
Functionality | Assessing the software's features and capabilities in meeting project requirements.
Cost | Evaluating the overall cost, including licensing, implementation, and maintenance fees.
Vendor Reputation | Reviewing the vendor's track record, reliability, and customer satisfaction ratings.
Support Services | Examining the quality and availability of vendor support, training, and troubleshooting services.
Scalability | Assessing the software's ability to scale with organizational growth and evolving needs.
Notes: The selection criteria and response evaluation process establish clear criteria for assessing vendor proposals and selecting the most suitable solution. Criteria include functionality, cost, vendor reputation, support services, and scalability, ensuring alignment with project objectives.
In the Selection Criteria and Response Evaluation process, we establish specific criteria to assess vendor proposals and choose the most suitable solution for the SketchUp project. Let's break down the process using two tables:
Functionality: We evaluate the software's features and capabilities to ensure they meet our project requirements.
Cost: This criterion involves assessing the overall cost, including licensing, implementation, and maintenance fees.
Vendor Reputation: We review the vendor's track record, reliability, and customer satisfaction ratings.
Support Services: This criterion examines the quality and availability of vendor support, training, and troubleshooting services.
Scalability: We assess the software's ability to scale with our organizational growth and evolving needs.
All vendor applicants must meet these basic criteria to be eligible for the selection process. Vendors should clearly understand our procurement requirements and be prepared to address any associated risks. Professionalism from vendors is essential, including professional communication, documentation, and procurement processes. We prioritize quality products and do not compromise on quality. Vendors are reminded that prices cannot be changed once the contract is finalized, so they should submit cost documentation accordingly.

## Slide 8: Estimated Budget
Item | Quantity | Per Unit Price ($) | Total Cost ($) | References
Software Licenses | - | - | 50,000 | Vendor Quotes, Market Research
Implementation Services | - | - | 30,000 | Vendor Quotes, Market Research
Training Sessions | - | - | 20,000 | Training Providers, Market Research
Hardware Upgrades | 100 | 400 | 40,000 | Vendor Quotes, Market Research
Laptops | 100 | 800 | 80,000 | Vendor Quotes, Market Research
Miscellaneous Expenses | - | - | 10,000 | Project Management Estimate
Tax (10%) | - | - | 158,960 | Tax Regulations, Government Guidelines
Total Budget (including tax) | - | - | 1,589,500 | 
Notes: The estimated budget outlines the projected costs for software licenses, implementation services, training sessions, hardware upgrades, laptops, and miscellaneous expenses. This budget ensures financial transparency and accountability throughout the procurement process.
Here's a breakdown of the budget for the SketchUp project:
Software Licenses: $50,000
Implementation Services: $30,000
Training Sessions: $20,000
Hardware Upgrades (100 units at $400 each): $40,000
Laptops (100 units at $800 each): $80,000
Miscellaneous Expenses: $10,000
Considering a tax rate of 10%: $158,960
Total Budget (including tax): $1,589,500
It's important to note that the total budget includes the cost of all items plus the applicable tax. The figures are based on vendor quotes, market research, training provider estimates, and project management estimates.

## Slide 9: Contract Type and Standards
Correctly utilizing procurement contracts is paramount for the success of the SketchUp project. The appropriate contract type must be selected to ensure smooth execution of the procurement process and software implementation.
Different contract types relate to the project:
Fixed-Price Contract: Suitable for obtaining specific components with clearly defined scopes, like licensing costs or certain implementation services. It provides cost certainty and motivates suppliers to meet deadlines and budget requirements.
Cost-Reimbursable Contract: Ideal for project components with less clear scopes or subject to change, such as customization or extra support services. This type of contract ensures the company is only charged for actual expenses incurred and offers flexibility in accommodating changes.
Time and Material Contract: Appropriate for services where the amount of work needed varies over time, like technical support or training sessions. It allows adaptability in resource utilization and permits modifications in response to changing project requirements.
Unit Price Contract: Involves paying a set price per unit for items like peripherals or hardware upgrades. This method ensures uniformity in prices for comparable items and simplifies pricing computations.
Notes: The contract type and standards section discusses different contract types, including fixed-price, cost-reimbursable, time and material, and unit price contracts. It also highlights common contract clauses related to scope of work, payment terms, intellectual property rights, confidentiality, and termination.
Understanding and appropriately utilizing procurement contracts is paramount for the success of the SketchUp project.
Let's explore the different contract types and their relevance to our project:
Fixed-Price Contract: This contract type is ideal for acquiring specific components with clearly defined scopes, such as licensing costs or certain implementation services. It offers cost certainty and incentivizes suppliers to meet deadlines and budget requirements effectively. Utilizing fixed-price contracts ensures predictability in project costs and minimizes financial risks.
Cost-Reimbursable Contract: For project components with less clear scopes or subject to change, such as customization or additional support services, cost-reimbursable contracts are the preferred choice. These contracts enable the company to only pay for actual expenses incurred, providing flexibility in accommodating changes throughout the project lifecycle. This flexibility ensures that the project can adapt to evolving requirements without incurring unnecessary costs.
Time and Material Contract: Services with varying workloads over time, such as technical support or training sessions, are best suited for time and material contracts. This contract type allows for adaptability in resource utilization and permits modifications in response to changing project requirements. By utilizing time and material contracts, we can ensure efficient resource allocation and responsiveness to project needs.
Unit Price Contract: Involving payment based on a set price per unit for items like peripherals or hardware upgrades, unit price contracts ensure uniformity in prices for comparable items and simplify pricing computations. This contract type streamlines the procurement process for standardized items, ensuring transparency and consistency in pricing across different vendors.
By selecting the appropriate contract type for each aspect of the SketchUp project, we can effectively manage project costs, mitigate risks, and ensure smooth execution of the procurement process and software implementation.

## Slide 10: Reference
Project Management: A Systems Approach to Planning, Scheduling, and Controlling, 13th edition. (2022, February 14). Wiley.com. https://www.wiley.com/en-ca/Project+Management:+A+Systems+Approach+to+Planning,+Scheduling,+and+Controlling,+13th+Edition-p-9781119805373
Purchasing Managers Index and CAPS Data Foundation for Supply Chain Strategy. (n.d.). https://www.ismworld.org/for-business/research-benchmarking/credible-data-for-supply-chain-strategy/?utm_campaign=Corporate_Program_FY23&utm_source=ppc&utm_medium=Bing&utm_term=PMI&msclkid=8898df86cd471c6924e1ba3c22d55442
Accredible. (n.d.). Accredible • Certificates, badges and blockchain. Accredible • Recipient Portal. https://credentials.cips.org/issuer/10000201/credentials
729-1983 - IEEE Standard Glossary of Software Engineering Terminology. (1983, February 18). IEEE Standard | IEEE Xplore. https://ieeexplore.ieee.org/document/7435207
ISO/IEC/IEEE 12207:2017. (n.d.). ISO. https://www.iso.org/standard/63712.html
Luitink, J., van de Riet, M., and Schotanus, F. (2016). Contracts in the supply chain: a literature review and research agenda. Supply Chain Management: An International Journal, 21(5), 638-652.
Notes: Here are the references used in preparing our procurement plan. They include reputable sources such as academic journals, industry publications, and standards organizations.

## Slide 11: Thank you
Group 10 | 
Divya Mathew S M Rakibul Basher Gihan Shamike Liyanage | 1192361 1168369 1142109
Notes: Thank you for your attention. If you have any questions this is the time to ask.