## Time Phase Budget
Time Phased Project WP Estimate
Description of your project (min 100 words)
WBS Code | Activity | 2012-12-20 | 2012-12-21 | 2012-12-22 | 2012-12-23 | 2012-12-24 | 2012-12-25 | 2012-12-26 | 2012-12-27 | 2012-12-28 | 2012-12-29 | 2012-12-30 | 2012-12-31 | 2013-01-01 | 2013-01-02 | 2013-01-03 | 2013-01-04 | 2013-01-05 | 2013-01-06 | 2013-01-07 | 2013-01-08 | 2013-01-09 | Total by Activity
1 | Project Wonder Deck
1.1 | Site Setup
1.1.1 | Apply and attain Building Permit | 212.495 | 212.495 | [19 empty] | 424.99
1.1.2 | Survey and stake site layout |  | 110 |  |  | 110 | 110 | [15 empty] | 330
1.2 | Site Prepped
1.2.1 | Design and Sketch Deck
1.2.2 | Remove Sod
1.3 | Post Foundation
1.3.1 | Protect Utility Lines
1.3.2 | Install Ledger board
1.3.3 | Place Batter Boards
1.3.4 | Place String lines to mark layout
1.3.5 | Layout Posts
1.3.6 | Dig Post Holes | [8 empty] | 506 |  |  | 506 | [9 empty] | 1012
Daily Subtotal of WP Cost Estimates |  | 212.495 | 322.495 | 0 | 0 | 110 | 110 | 0 | 0 | 506 | 0 | 0 | 506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766.99
Cumulative WP Total |  | 212.495 | 534.99 | 534.99 | 534.99 | 644.99 | 754.99 | 754.99 | 754.99 | 1260.99 | 1260.99 | 1260.99 | 1766.99 | 1766.99 | 1766.99 | 1766.99 | 1766.99 | 1766.99 | 1766.99 | 1766.99 | 1766.99 | 1766.99
WP Estimate S-Curve
Note on C2: Make sure you provide a minimum of 100 words to describe your project.
Note on H3: Schedule work on Christmas Day and other statutory holidays to keep things simpler
Note on K3: Use dates corresponding to the appropriate calendar year, not 2012 and 2013
Note on E4: Note there are no costs on the weekend because we are not working on weekends, but show weekend dates in case overtime is needed, shade your weekends to indicate normally they are non-working time.
Note on C6: Note, you have to use an Excel formula to link the costs on this budget from the source, a cell on row 37 in the Estimation Worksheet called 1.1.1, the orange worksheet tab. Also note the costs from the worksheet 1.1.1 were divided by 2, as this was a 2-day duration activity.
Note on Y37: Your horizontal subtotal should match your vertical subtotal, this is a cross-check.
Note on X38: Your cumulative subtotal should match your total on your S Curve Diagram, check to make sure this is the case.
Note on A43: Figure out where your WP Estimate chart is getting it's numbers from, and ensure if you add extra columns that the chart is using ALL the correct numbers FROM YOUR CUMULATIVE WP ROW -- check to verify YOUR TOTAL IN YOUR S- CURVE MATCHES THE TOTAL IN YOUR CUMULATIVE WP ROW.

## 1.1.1
ESTIMATE AND QUOTATION SHEET
Estimate performed by:
Project: Deck | Description: 1 level 206 square foot deck with railing and stairs
Activity WBS Code: 1.1.1
Activity Description: Get Building Permit
Internal Labour
Skill | Rate | Hours | Cost
Supervisor | 50 | 6 | 300
Other | 0 | 0 | 0
Other | 0 | 0 | 0
Other | 0 | 0 | 0
Other | 0 | 0 | 0
Other | 0 | 0 | 0
Subtotal, Hours and Cost |  | 6 | 300
Labour Contingency (3%) | 0.03 |  | 9
Total Labour, Hours and Costs |  |  | 309
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 309
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Materials (Specify) | 0 | 0 | 0
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 0
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 0
Expenses
Specify: Building Permit |  |  | 115.99
Total Expenses |  |  | 115.99
Total Gross Labour plus Material Costs and Expenses |  |  | 424.99
Justification: 2 hours to do paper work (based on previous jobs) and 11 days to get approval based on http://torontobuildingpermits.com/?page_id=20 Building Permits cost $5.36/square meter as per http://www1.toronto.ca/wps/portal/contentonly?vgnextoid=6d3ea41deefc0410VgnVCM10000071d60f89RCRD&vgnextchannel=6c661ba53b450410VgnVCM10000071d60f89RCRD#b. alterations and renovations fee-d8bdf14e5b4e0410VgnVCM10000071d60f89____ and deck is estimated at 19.15 meters + 13% HST = $115.99 Rationale for contingency: 3% Possibility that we do not provide all of the information necessary and will have to do permit again. Based on all permits we have filled out to date. and PERT calculations.
Assumptions: Assume gas to drive and drop off and pick up permits is covered under overhead rates.
Approved: | Date:
Note on B2: See WBS worksheet 1.4.1 for detailed comments

## 1.1.2
ESTIMATE AND QUOTATION SHEET
Estimate performed by:
Project: Deck | Description: 1 level 206 square foot deck with railing and stairs
Activity WBS Code: 1.1.2
Activity Description: Verifying Requirements & Specs
Internal Labour
Skill | Rate | Hours | Cost
Supervisor | 50 | 6 | 300
Labourer 1 | 0 | 3.5 | 0
Labourer 2 | 0 | 3.5 | 0
Other | 0 | 0 | 0
Other | 0 | 0 | 0
Other | 0 | 0 | 0
Subtotal, Hours and Cost |  | 13 | 300
Labour Contingency (10%) | 0.1 |  | 30
Total Labour, Hours and Costs |  |  | 330
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 330
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Materials (Specify) | 0 | 0 | 0
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 0
Material Contingency (%) |  | 0 | 0
Total Material Costs |  |  | 0
Expenses
Specify:
Total Expenses |  |  | 0
Total Gross Labour plus Material Costs and Expenses |  |  | 330
Justification: 1 initial meetings with customer to discuss deck plan 2 hours , 3 - 30 minute meetings with customer during deck construction to go over progress, 30 minute meetings with labourers daily for 5 days to review progress / work and discuss upcoming activities, 1 hour meeting with staff at end to document project documents and lessons learned. Based on previous projects. Rational for Contingency Rates: 10% - based on previous projects the time spent on Project Management varied from job to job by 10%
Assumptions: Assume gas to drive and meet with customers and staff is covered under overhead rates.
Approved: | Date:
Note on B2: See WBS worksheet 1.4.1 for detailed comments

## 1.4.1
ESTIMATE AND QUOTATION SHEET
Estimate performed by:
Project: Deck | Description: 1 level 206 square foot deck with railing and stairs
Activity WBS Code: 1.4.1
Activity Description: Dig post holes and place posts in hole
Internal Labour
Skill | Rate | Hours | Cost
Labourer 1 | 30 | 12 | 360
Labourer 2 | 30 | 12 | 360
Other | 0 | 0 | 0
Other | 0 | 0 | 0
Other | 0 | 0 | 0
Other | 0 | 0 | 0
Subtotal, Hours and Cost |  | 24 | 720
Labour Contingency (10%) | 0.1 |  | 72
Total Labour, Hours and Costs |  |  | 792
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 792
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Materials (Specify), 12, 4 by 4 posts, pressure treated | 15 | 12 | 180
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 180
Material Contingency (%) | 0.03 | 0 | 0
Total Material Costs |  |  | 180
Expenses
Specify: Delivery of posts (delivered separately from other materials) |  |  | 40
Total Expenses |  |  | 40
Total Gross Labour plus Material Costs and Expenses |  |  | 1012
Justifications: Based on information from http://www.landscapejuicenetwork.com/forum/topics/average-time-to-dig-fence-post the most likely time needed to dig holes is 12 posts x 30 minutes a post = 6 hours. The most optimistic would be 20 minutes / hole which would take 4 hours in total. Assuming the worst and that it rained for days on end and we had to redig the holes it would take 12 hours in total. Using PERT calculations gives us a TE of 6.64 hours. "Justifications: Based on information from http://www.landscapejuicenetwork.com/forum/topics/average-time-to-dig-fence-post the most likely time needed to dig holes is 12 posts x 30 minutes a post = 6 hours. The most optimistic would be 20 minutes / hole which would take 4 hours in total. Assuming the worst and that it rained for days on end and we had to redig the holes it would take 12 hours in total. Using PERT calculations gives us a TE of 6.64 hours. Rationale for Contingency: High likelihood that could run into rocks, class or other objects that could delay the digging of the holes" Rationale for Material Contingency: Cost of posts, pressure treated, from www.xxxxx.com, $15 per post. Rationale for Material Contingency: Low material contingency as price stable at store, and waste is usually nill for posts.
Assumptions: Two workers work at digging hole. Assume auger is owned by company and is included in overhead rates. Assuming posts are delivered separately, as change in post locations due to large boulders may dictate and change in the rest of the material order, which means a separate truck delivery.,
Approved: | Date:
Note on C8: You may estimate 12 hours of work for an activity, but the duration for the activity might be estimated at 4 days (it takes that long for various reasons such as having to wait for things). So note, in a Time Phased Table only 3 hours of work is being done in a day. 12hrs/4 days = 3hrs/day.
Note on D9: This is a formula.
Note on A16: Your may or may not need to enter a contingency % and rationale below.
Note on C22: This could be units, as in 12 posts are needed, or it could be in number of uses, e.g. I have to rent a piece of equipment 2 times.
Note on A23: You may or may not need to enter a material contingency % and rationale below.
Note on D23: This is a formula.
Note on A40: You may or may not need to enter a justification and rationale. If you do, ensure you provide the number(s) you extracted from the source. Provide a url, but ensure you list the numbers you used. For example post prices sourced from www.xxxxx.com. There were prices of $14.20 for Toronto, and $15.50 for Windsor. No pricing was available for London so $15 was used. You need paragraphs to back up the url's you use.