## Time Phase Budget
Time Phased Project WP Estimate
Description of your project (min 100 words) |  | Barn House Studios Wedding Reception Venue is a picturesque and versatile event space designed to transform couples' dreams into enchanting realities. Nestled within a beautifully restored barn, our venue offers a rustic yet elegant atmosphere, combining the warmth of wood and the sophistication of modern design. We specialize in hosting personalized and memorable wedding receptions, tailored to each couple's unique vision. From intimate gatherings to grand celebrations, our dedicated team ensures seamless coordination, exquisite decor, and top-notch catering. At Barn House Studios, we believe in crafting unforgettable experiences, making every wedding reception a masterpiece of love and joy.
WBS Code | Deliverable or Activity Name | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24 | 2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-12-30 | 2023-12-31 | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-06 | 2024-01-07 | 2024-01-08 | 2024-01-09 | 2024-01-10 | 2024-01-11 | 2024-01-12 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | Total by Activity
1 | Project Barn House Studios | [36 empty] | 0
1.1 | Project Start | [36 empty] | 0
1.1.1 | Design and Plan Venue Layout | 2023-12-20: 2183.3333; 2023-12-21: 2183.3333; 2023-12-22: 2183.3333 | 6550
1.1.2 | Apply and obtain Food Handling Permits | 2023-12-22: 1450; 2023-12-25: 1450 | 2900
1.1.3 | Apply and obtain Alcohol Licenses | 2023-12-22: 1400; 2023-12-25: 1400 | 2800
1.2 | Interior Finishing | [36 empty] | 0
1.2.1 | Build interior partition walls | 2023-12-25: 10420; 2023-12-26: 10420; 2023-12-27: 10420 | 31260
1.2.2 | Paint walls and ceiling | 2023-12-27: 4811.6667; 2023-12-28: 4811.6667; 2023-12-29: 4811.6667 | 14435
1.2.3 | Install Flooring and Carpeting | 2023-12-28: 6383.3333; 2023-12-29: 6383.3333; 2024-01-01: 6383.3333 | 19150
1.2.4 | Install Ambient Lighting System | 2024-01-02: 12850; 2024-01-03: 12850 | 25700
1.2.5 | Install Sound System | 2024-01-02: 11850; 2024-01-03: 11850 | 23700
1.2.6 | Install Internet & Wifi | 2024-01-04: 3865; 2024-01-05: 3865 | 7730
1.2.7 | Setup and Arrange Furniture | 2024-01-05: 23710 | 23710
1.2.8 | Install Drapery and Curtain | 2024-01-08: 10090 | 10090
1.2.9 | Setup Decor and Styling | 2024-01-08: 6710; 2024-01-09: 6710; 2024-01-10: 6710 | 20130
1.2.10 | Install Wall Arts and Murals | 2024-01-11: 8460 | 8460
1.3 | Catering and Bar Services | [36 empty] | 0
1.3.1 | Setup Kitchen and Install Equipments | 2024-01-12: 13080; 2024-01-15: 13080 | 26160
1.3.2 | Planning Menu and Preparing Catering | 2024-01-16: 12470 | 12470
1.3.3 | Setup Bar and arrange Beverages Selection | 2024-01-16: 17812 | 17812
1.4 | Guest Services and Amenities | [36 empty] | 0
1.4.1 | Train Guest Services for Staff | 2024-01-17: 1610; 2024-01-18: 1610 | 3220
1.4.2 | Setup Guest Amenities (restrooms, lounge areas) | 2024-01-19: 2456 | 2456
1.5 | Final Touches and Rehearsals | [36 empty] | 0
1.5.1 | Inspect Final Venue and Check Quality | 2024-01-22: 5970 | 5970
1.5.2 | Rehears Wedding | 2024-01-23: 9204 | 9204
1.6 | Project End | [36 empty] | 0
1.6.1 | Review outcome and end project | 2024-01-24: 1360 | 1360
0
0
Daily Subtotal of WP Estimate |  | 2183.3333 | 2183.3333 | 5033.3333 | 0 | 0 | 13270 | 10420 | 15231.6667 | 11195 | 11195 | 0 | 0 | 6383.3333 | 24700 | 24700 | 3865 | 27575 | 0 | 0 | 16800 | 6710 | 6710 | 8460 | 13080 | 0 | 0 | 13080 | 30282 | 1610 | 1610 | 2456 | 0 | 0 | 5970 | 9204 | 1360 | 275267
Cumulative WP Estimate |  | 2183.3333 | 4366.6667 | 9400 | 9400 | 9400 | 22670 | 33090 | 48321.6667 | 59516.6667 | 70711.6667 | 70711.6667 | 70711.6667 | 77095 | 101795 | 126495 | 130360 | 157935 | 157935 | 157935 | 174735 | 181445 | 188155 | 196615 | 209695 | 209695 | 209695 | 222775 | 253057 | 254667 | 256277 | 258733 | 258733 | 258733 | 264703 | 273907 | 275267 |  | WP Estimate Cost
WP Estimate S-Curve

## 1.1.1
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.1.1
Activity Description: Design and Plan Venue Layout
Internal Labour
Skill or Role | Rate | Hours | Cost
Interior Designer | 100 | 24 | 2400
Wedding Planner | 80 | 24 | 1920
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 48 | 4320
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 4320
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 4320
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Blueprint Printing | 210 | 3 | 630
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 630
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 630
Expenses
Travel Expenses for Site Visits, Consultation Fees |  |  | 1600
Total Expenses |  |  | 1600
Total Gross Labour plus Material Costs and Expenses |  |  | 6550
Assumptions: https://blueprintsprinting.com/pricing/
Approved: | Date: 2023/10/12

## 1.1.2
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.1.2
Activity Description: Apply and obtain Food Handling Permits
Internal Labour
Skill | Rate | Hours | Cost
Legal Consultant | 70 | 5 | 350
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 5 | 350
Labour Contingency (10%) |  |  | 0
Total Labour, Hours and Costs |  |  | 350
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 350
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Materials | 0 | 0 | 0
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 0
Material Contingency (%) |  | 0 | 0
Total Material Costs |  |  | 0
Expenses
Documentation, Local & State Health Department Permit Fees |  |  | 2550
Total Expenses |  |  | 2550
Total Gross Labour plus Material Costs and Expenses |  |  | 2900
Assumptions: https://www.touchbistro.com/blog/how-to-get-and-keep-a-food-handlers-permit/
Approved: | Date: 2023/10/12

## 1.1.3
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.1.3
Activity Description: Apply and obtain Alcohol Licenses
Internal Labour
Skill or Role | Rate | Hours | Cost
Legal Consultant | 70 | 5 | 350
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 5 | 350
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 350
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 350
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Materials | 0 | 0 | 0
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 0
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 0
Expenses
Documentation, Application Fees |  |  | 2450
Total Expenses |  |  | 2450
Total Gross Labour plus Material Costs and Expenses |  |  | 2800
Assumptions: https://www2.gov.bc.ca/gov/content/employment-business/business/liquor-regulation-licensing/liquor-licence-permits/apply-for-liquor-licence-permit
Approved: | Date: 2023/10/12

## 1.2.1
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.2.1
Activity Description: Build interior partition walls
Internal Labour
Skill or Role | Rate | Hours | Cost
Carpenters | 80 | 44 | 3520
Construction Workers | 60 | 44 | 2640
General Labourers | 20 | 40 | 800
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 128 | 6960
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 6960
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 6960
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Framing Material | 40 | 200 | 8000
Drywall Sheets | 35 | 90 | 3150
Joint Compound | 25 | 120 | 3000
Screws, and Tape | 8 | 500 | 4000
Primers | 35 | 150 | 5250
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 23400
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 23400
Expenses
Transpotation |  |  | 300
Wood Protection Materials |  |  | 600
Total Expenses |  |  | 900
Total Gross Labour plus Material Costs and Expenses |  |  | 31260
Assumptions: https://homeguide.com/costs/partition-wall-cost
Approved: | Date: 2023/10/12

## 1.2.2
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.2.2
Activity Description: Paint walls and ceiling
Internal Labour
Skill or Role | Rate | Hours | Cost
Professional Painters | 80 | 34 | 2720
General Labourers | 20 | 44 | 880
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 78 | 3600
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 3600
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 3600
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Paint (quality latex paint, quantity based on sq footage) | 40 | 100 | 4000
Brushes | 35 | 15 | 525
Rollers | 45 | 8 | 360
Drop cloths, painter's tape | 15 | 90 | 1350
Primer | 35 | 100 | 3500
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 9735
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 9735
Expenses
Transpotation |  |  | 300
Paint Sprayer Rental |  |  | 200
Paint Protection Materials |  |  | 600
Total Expenses |  |  | 1100
Total Gross Labour plus Material Costs and Expenses |  |  | 14435
Assumptions: https://homeguide.com/costs/cost-to-paint-a-ceiling
Approved: | Date: 2023/10/12

## 1.2.3
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.2.3
Activity Description: Install Flooring and Carpeting
Internal Labour
Skill or Role | Rate | Hours | Cost
Flooring Specialists | 80 | 20 | 1600
Flooring Installation Assistants | 60 | 20 | 1200
General Labourers | 20 | 50 | 1000
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 90 | 3800
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 3800
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 3800
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Hardwood Flooring | 40 | 150 | 6000
Carpeting | 35 | 250 | 8750
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 14750
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 14750
Expenses
Floor Protection Materials |  |  | 600
Total Expenses |  |  | 600
Total Gross Labour plus Material Costs and Expenses |  |  | 19150
Assumptions: https://www.forbes.com/home-improvement/flooring/carpet-installation-cost/
Approved: | Date: 2023/10/12

## 1.2.4
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.2.4
Activity Description: Install Ambient Lighting System
Internal Labour
Skill or Role | Rate | Hours | Cost
Lighting Specialists | 90 | 24 | 2160
Electrical Technicians | 70 | 32 | 2240
General Labourers | 20 | 32 | 640
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 88 | 5040
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 5040
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 5040
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Chandeliers | 670 | 12 | 8040
Fairy Lights | 45 | 40 | 1800
LED Strips | 28 | 90 | 2520
Mounting Hardware | 18 | 100 | 1800
Wiring, Cables, and Connectors | 30 | 90 | 2700
Dimmer Switches | 20 | 25 | 500
Wall Sconces | 75 | 30 | 2250
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 19610
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 19610
Expenses
Lighting Protectors and Surge Suppressors |  |  | 800
Power Source Upgrades |  |  | 250
Total Expenses |  |  | 1050
Total Gross Labour plus Material Costs and Expenses |  |  | 25700
Assumptions: https://www.amazon.com/ambient-lighting/s?k=ambient+lighting
Approved: | Date: 2023/10/12

## 1.2.5
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.2.5
Activity Description: Install Sound System
Internal Labour
Skill or Role | Rate | Hours | Cost
Audio Technicians | 90 | 24 | 2160
Installation Assistants | 80 | 24 | 1920
General Labourers | 20 | 36 | 720
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 84 | 4800
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 4800
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 4800
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Speakers and Subwoofers | 800 | 12 | 9600
Amplifiers and Receivers | 600 | 3 | 1800
Microphones and Stands | 300 | 5 | 1500
Sound Mixers | 1200 | 1 | 1200
Playback Devices | 600 | 2 | 1200
Speaker Cables, XLR Cables | 50 | 16 | 800
Mounting Hardware | 25 | 12 | 300
Audio Controllers and Equalizers | 1200 | 1 | 1200
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 17600
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 17600
Expenses
Acoustic Treatment |  |  | 1000
Setup and Calibration Tools |  |  | 300
Total Expenses |  |  | 1300
Total Gross Labour plus Material Costs and Expenses |  |  | 23700
Assumptions: https://www.amazon.ca/s?k=commercial+speaker+system&gclid=Cj0KCQjwsp6pBhCfARIsAD3GZuaomJbm6G9CQJDP_K8ClJbfEXMMqCF19G9OILZyJoMm_HmWw5y05zAaAv93EALw_wcB&hvadid=647601345767&hvdev=c&hvlocphy=9001071&hvnetw=g&hvqmt=b&hvrand=3717952644301176035&hvtargid=kwd-297527794974&hydadcr=29955_14625788&tag=googcana-20&ref=pd_sl_7no7xdkvcx_b
Approved: | Date: 2023/10/12

## 1.2.6
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.2.6
Activity Description: Install Internet & Wifi
Internal Labour
Skill or Role | Rate | Hours | Cost
Network Technician | 90 | 16 | 1440
Installation Assistants | 70 | 16 | 1120
General Labourers | 20 | 16 | 320
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 48 | 2880
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 2880
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 2880
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Routers | 400 | 1 | 400
Access Points | 550 | 3 | 1650
Network Switches | 950 | 2 | 1900
Ethernet Cables | 1 | 500 | 500
Connectors and Wall Plates | 5 | 20 | 100
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 4550
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 4550
Expenses
Power Backup |  |  | 300
Total Expenses |  |  | 300
Total Gross Labour plus Material Costs and Expenses |  |  | 7730
Assumptions: https://www.homedepot.ca/en/home/categories/building-materials/electrical/home-electronics-and-communications/wi-fi-and-networking-devices.html?eid=PS_GOOGLE_D27E_Corporate_GGL_Text_NB_EN_Smart-Home_Networking%20%26%20Wireless%20-%20BMM_b_%2Bnetwork%20%2Brouter_kwd-19730363019&gad_source=1&gclid=Cj0KCQjwsp6pBhCfARIsAD3GZuaD8qB4anZfbNIFmh_L5FyZSXLUXeQIw3X20eIBhWbjK2s3I3XgWwAaAjFgEALw_wcB&gclsrc=aw.ds
Approved: | Date: 2023/10/12

## 1.2.7
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.2.7
Activity Description: Setup and Arrange Furniture
Internal Labour
Skill or Role | Rate | Hours | Cost
Furniture Setup Crew | 40 | 8 | 320
Arrangement and Styling Specialist | 70 | 8 | 560
General Labourers | 20 | 16 | 320
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 32 | 1200
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 1200
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 1200
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Tables | 150 | 20 | 3000
Chairs | 80 | 150 | 12000
Dining Sets | 200 | 10 | 2000
Cocktail Tables | 100 | 15 | 1500
Lounge Furniture (Sofas, Ottomans, etc.) | 300 | 5 | 1500
Chair Covers and Sashes | 7 | 170 | 1190
Cupboards | 170 | 6 | 1020
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 22210
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 22210
Expenses
Transportation of Furniture |  |  | 300
Total Expenses |  |  | 300
Total Gross Labour plus Material Costs and Expenses |  |  | 23710
Assumptions: https://www.ashleyfurniture.com/c/deals/furniture-price-cuts/
Approved: | Date: 2023/10/12

## 1.2.8
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.2.8
Activity Description: Install Drapery and Curtain
Internal Labour
Skill or Role | Rate | Hours | Cost
Professional Installers | 70 | 8 | 560
General Labourers | 20 | 16 | 320
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 24 | 880
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 880
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 880
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Fabric for Drapery and Curtains | 20 | 300 | 6000
Curtain Rods and Hardware | 30 | 20 | 600
Tiebacks and Holdbacks | 15 | 20 | 300
Curtain Rings | 10 | 120 | 1200
Clips | 8 | 120 | 960
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 9060
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 9060
Expenses
Ladder and Safety Equipment |  |  | 150
Total Expenses |  |  | 150
Total Gross Labour plus Material Costs and Expenses |  |  | 10090
Assumptions: https://www.serenashades.ca/products/?gad_source=1&gclid=Cj0KCQjwsp6pBhCfARIsAD3GZuZ_WBu6Lw7xpktWm7WNtvw1O7Jc045Sv-ZtE_vygGdOfOqoaqkuQlIaAn1WEALw_wcB&gclsrc=aw.ds
Approved: | Date: 2023/10/12

## 1.2.9
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.2.9
Activity Description: Setup Decor and Styling
Internal Labour
Skill or Role | Rate | Hours | Cost
Decorators and Stylists | 100 | 24 | 2400
Decorate Helpers | 20 | 24 | 480
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 48 | 2880
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 2880
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 2880
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Flowers for Floral Arrangements | 3.5 | 2000 | 7000
Decorative light bulbs | 7.5 | 500 | 3750
Centerpieces and Table Decor | 28 | 75 | 2100
Cloth | 6.5 | 600 | 3900
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 16750
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 16750
Expenses
Transportation of Decor Items |  |  | 500
Total Expenses |  |  | 500
Total Gross Labour plus Material Costs and Expenses |  |  | 20130
Assumptions: https://www.amazon.ca/s?k=decoration+prices&gclid=Cj0KCQjwsp6pBhCfARIsAD3GZuZtiEINtxJNKbCpO9KY_0076F8HexJv9q6aB8mxVWTod0cc7NzvU5UaAqaTEALw_wcB&hvadid=667665274775&hvdev=c&hvlocphy=9001071&hvnetw=g&hvqmt=e&hvrand=9252946916710037397&hvtargid=kwd-430310229525&hydadcr=1756_13630532&tag=googcana-20&ref=pd_sl_4br6b9ozot_e
Approved: | Date: 2023/10/12

## 1.2.10
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.2.10
Activity Description: Install Wall Arts and Murals
Internal Labour
Skill or Role | Rate | Hours | Cost
Professional Artists and Installers | 90 | 8 | 720
General Labourers | 20 | 32 | 640
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 40 | 1360
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 1360
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 1360
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Canvas Paintings | 200 | 10 | 2000
Custom Murals | 800 | 3 | 2400
Frames and Mounts | 50 | 20 | 1000
Protective Sealant | 100 | 2 | 200
Art Display Lights | 150 | 10 | 1500
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 7100
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 7100
Expenses
Total Expenses |  |  | 0
Total Gross Labour plus Material Costs and Expenses |  |  | 8460
Assumptions: https://www.amazon.ca/s?k=Wall+Arts+and+Murals&crid=3GTBDBVV795MK&sprefix=wall+arts+and+murals%2Caps%2C224&ref=nb_sb_noss_2
Approved: | Date: 2023/10/12

## 1.3.1
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.3.1
Activity Description: Setup Kitchen and Install Equipments
Internal Labour
Skill or Role | Rate | Hours | Cost
Professional Installers | 90 | 16 | 1440
General Labourers | 20 | 32 | 640
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 48 | 2080
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 2080
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 2080
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Commercial Refrigerator | 2500 | 2 | 5000
Commercial Oven and Stove | 3000 | 2 | 6000
Food Preparation Counters | 800 | 3 | 2400
Industrial Sink and Dishwashing Station | 1200 | 2 | 2400
Small Kitchen Appliances (Blenders, Mixers, etc.) | 300 | 5 | 1500
Kitchen Utensils, Cookware | 450 | 6 | 2700
Cleaning Supplies | 120 | 4 | 480
| 0 | 0 | 0
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 20480
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 20480
Expenses
Plumbing and Electrical Work |  |  | 1600
Fire Suppression System |  |  | 2000
Total Expenses |  |  | 3600
Total Gross Labour plus Material Costs and Expenses |  |  | 26160
Assumptions: https://homeguide.com/costs/appliance-installation-costs
Approved: | Date: 2023/10/12

## 1.3.2
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.3.2
Activity Description: Planning Menu and Preparing Catering
Internal Labour
Skill or Role | Rate | Hours | Cost
Chef/Caterer | 70 | 8 | 560
Kitchen Assistants | 50 | 8 | 400
Serving Staff | 30 | 8 | 240
Bartenders and Bar Staff | 50 | 8 | 400
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 32 | 1600
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 1600
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 1600
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Chafing Dishes | 12 | 150 | 1800
Serving Utensils | 8 | 200 | 1600
Tableware | 18 | 40 | 720
Disposable Plates, Cups | 12 | 200 | 2400
Cutlery | 9 | 450 | 4050
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 10570
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 10570
Expenses
Transportation of Catering Equipment and Supplies |  |  | 300
Total Expenses |  |  | 300
Total Gross Labour plus Material Costs and Expenses |  |  | 12470
Assumptions: https://www.canadiantire.ca/en/cat/home-pets/kitchen-dining/dining-entertaining/cutlery-DC0001011.html?&&&&ds_rl=1283573&ds_rl=1283573&gclid=Cj0KCQjwsp6pBhCfARIsAD3GZuYt73nuF1g-WuKMdPdj_nrGsf6q2JefY38NgOFFavcYPpAFuTsZczUaAhnkEALw_wcB&gclsrc=aw.ds
Approved: | Date: 2023/10/12

## 1.3.3
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.3.3
Activity Description: Setup Bar and arrange Beverages Selection
Internal Labour
Skill or Role | Rate | Hours | Cost
Bartenders | 34 | 8 | 272
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 8 | 272
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 272
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 272
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Bar Counters and Backdrop | 1000 | 2 | 2000
Bar Tools (Shakers, Strainers, Jiggers, etc.) | 300 | 8 | 2400
Glassware (Wine Glasses, Beer Mugs, Cocktail Glasses, etc.) | 12 | 120 | 1440
Ice and Cooling Systems | 400 | 2 | 800
Non-Alcoholic Beverages (Soft Drinks, Juices, Water, etc.) | 40 | 80 | 3200
Alcoholic Beverages (Wine, Beer, Spirits, Cocktails, etc. | 80 | 90 | 7200
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 17040
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 17040
Expenses
Cocktail Ingredients (Mixers, Garnishes, etc.) |  |  | 500
Total Expenses |  |  | 500
Total Gross Labour plus Material Costs and Expenses |  |  | 17812
Assumptions: https://www.seriouseats.com/how-to-organize-your-home-bar-design-ergonomics-supplies-mise-en-place
Approved: | Date: 2023/10/12

## 1.4.1
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.4.1
Activity Description: Train Guest Services for Staff
Internal Labour
Skill | Rate | Hours | Cost
Trainer | 80 | 24 | 1920
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 24 | 1920
Labour Contingency (10%) |  |  | 0
Total Labour, Hours and Costs |  |  | 1920
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 1920
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Training Material | 8 | 40 | 320
Refreshments for Training Sessions | 12 | 40 | 480
| 0 | 0 | 0
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 800
Material Contingency (%) |  | 0 | 0
Total Material Costs |  |  | 800
Expenses
Transportation for Trainers |  |  | 200
Training Venue Rental |  |  | 300
Total Expenses |  |  | 500
Total Gross Labour plus Material Costs and Expenses |  |  | 3220
Assumptions:
Approved: | Date: 2023/10/12

## 1.4.2
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.4.2
Activity Description: Setup Guest Amenities (restrooms, lounge areas)
Internal Labour
Skill or Role | Rate | Hours | Cost
Supervisors | 25 | 8 | 200
General Labourers | 20 | 16 | 320
Lounge Area Attendants | 22 | 8 | 176
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 32 | 696
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 696
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 696
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Toiletries | 12 | 30 | 360
Supplies for Restrooms | 30 | 20 | 600
Guest Amenities (Hand Towels, Soap, etc.) | 25 | 20 | 500
| 0 | 0 | 0
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 1460
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 1460
Expenses
Transpotation |  |  | 300
Total Expenses |  |  | 300
Total Gross Labour plus Material Costs and Expenses |  |  | 2456
Assumptions: https://www.homedepot.ca/en/home/shop-by-room/bathroom.html?eid=PS_GOOGLE_D00_Corporate_GGL_Text_NB_EN_Shop-By-Room_BMM_Shop%20By%20Room_NB_EN_Bathroom_b_%2Bbathroom%20%2Baccessories_kwd-18551004277&gad_source=1&gclid=Cj0KCQjwsp6pBhCfARIsAD3GZubJydxSJ805sKHj0NAHaFFXFORmQGLPCXcY4EirzMZh_ARfRx1eA9gaAuLFEALw_wcB&gclsrc=aw.ds
Approved: | Date: 2023/10/12

## 1.5.1
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.5.1
Activity Description: Inspect Final Venue and Check Quality
Internal Labour
Skill or Role | Rate | Hours | Cost
Venue Staff for Assistance during Inspection | 20 | 32 | 640
Inspectors | 90 | 32 | 2880
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 64 | 3520
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 3520
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 3520
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Quality Check Forms | 20 | 25 | 500
| 0 | 0 | 0
| 0 | 0 | 0
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 500
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 500
Expenses
Refreshments for Inspection Team |  |  | 150
Transportation for Inspectors |  |  | 300
Inspection Company Fee |  |  | 1500
Total Expenses |  |  | 1950
Total Gross Labour plus Material Costs and Expenses |  |  | 5970
Assumptions: https://www.officedepot.com/l/print-and-copy/print-services
Approved: | Date: 2023/10/12

## 1.5.2
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.5.2
Activity Description: Rehears Wedding
Internal Labour
Skill or Role | Rate | Hours | Cost
Rehearsal Coordinator | 38 | 8 | 304
Chef/Caterer | 70 | 16 | 1120
Kitchen Assistants | 50 | 24 | 1200
Serving Staff | 30 | 36 | 1080
Bartenders and Bar Staff | 50 | 16 | 800
Supervisor | 25 | 8 | 200
Subtotal, Hours and Cost |  | 108 | 4704
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 4704
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 4704
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Food | 25 | 100 | 2500
Drinks | 18 | 100 | 1800
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 4300
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 4300
Expenses
Transportation |  |  | 200
Total Expenses |  |  | 200
Total Gross Labour plus Material Costs and Expenses |  |  | 9204
Assumptions:
Approved: | Date: 2023/10/12

## 1.6.1
ESTIMATE AND QUOTATION SHEET
Estimate performed by: | Gihan Liyanage
Project: Barn House Studios
Activity WBS Code: 1.6.1
Activity Description: Review outcome and end project
Internal Labour
Skill or Role | Rate | Hours | Cost
Accountant | 70 | 8 | 560
Accounts Assistant | 50 | 8 | 400
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Subtotal, Hours and Cost |  | 16 | 960
Labour Contingency (3%) |  |  | 0
Total Labour, Hours and Costs |  |  | 960
Overhead (0%) | (included in rate) | 0 | 0
Gross Labour Cost |  |  | 960
Material Costs
Material | Cost per unit or use of the Material | Units | Cost
Printing materials | 10 | 20 | 200
Tools | 0 | 0 | 0
Services | 0 | 0 | 0
Facilities | 0 | 0 | 0
Subcontractors
Subtotal |  |  | 200
Material Contingency (0%) |  | 0 | 0
Total Material Costs |  |  | 200
Expenses
Documentation |  |  | 200
Total Expenses |  |  | 200
Total Gross Labour plus Material Costs and Expenses |  |  | 1360
Assumptions: https://www.officedepot.com/l/print-and-copy/print-services
Approved: | Date:2023/10/12