## Time Phased Budget
WBS | Task Name | Activity Budget | WP Budget | Phase Budget | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22
WBS | Task Name
1 | Project Build Treehouse (Bunkie) |  |  | 21322
1.1 | Preparation |  | 6610
1.1.1 | Design Treehouse
1.1.1.1 | Research and sketch treehouse |  |  |  | 2023-01-22: 1600
1.1.1.2 | Engage architect for custom design | 1760 |  |  | 2023-01-22: 1760
1.1.1.3 | Finalize treehouse design |  | 0
1.1.2 | Resource and Cost Planning | 0 |  |  | 2023-01-23: 0
1.1.2.1 | Identify materials and estimates cost |  | 400 |  | 2023-01-22: $200.00; 2023-01-26: 200
1.1.2.2 | Develop resource and cost plan | 400 |  |  | 2023-01-23: 0; 2023-01-24: 0; 2023-01-25: 0; 2023-01-26: 400
1.1.2.3 | Resource and cost planning complete | 0 |  |  | 2023-01-26: 0
1.1.3 | Project Kick-off | 2450
1.1.3.1 | Review goals, scope, and timelines |  |  | 1500 | 2023-01-26: 1500
1.1.3.2 | Conduct project kick-off meeting |  | 800 |  | 2023-01-26: 800
1.1.3.3 | Preparation complete | 0 |  |  | 2023-01-26: 0; 2023-01-29: 0; 2023-01-30: 0; 2023-01-31: 0
1.2 | Execution | 9632 |  |  | 2023-01-26: 0; 2023-01-29: 0; 2023-01-30: 0; 2023-01-31: 0
1.2.1 | Buying Resources | 5478 |  |  | 2023-02-01: 0
1.2.1.1 | Get quotations and select suppliers | 800 |  |  | 2023-01-26: 800
1.2.1.2 | Purchase materials & equipments |  | 490 |  | 2023-02-01: $367.5; 2023-02-06: 122.5
1.2.1.3 | Resources acquisition complete | 0 |  |  | 2023-02-02: 120.13; 2023-02-05: 120.13; 2023-02-06: 120.13; 2023-02-07: 120.13
1.2.2 | Custom Steel Bracket Construction | 562.48 |  |  | 2023-02-08: 0
1.2.2.1 | Design bracket |  | 400 |  | 2023-02-01: $200; 2023-02-06: 200
1.2.2.2 | Fabricate custom brackets | 100 |  |  | 2023-02-06: 100; 2023-02-08: 0
1.2.3 | Treehouse Construction | 982 |  |  | 2023-02-05: 0; 2023-02-06: 0; 2023-02-07: 0; 2023-02-08: 0
1.2.3.1 | Prepare site and build structure |  | 50 |  | 2023-02-06: 25; 2023-02-12: $25
1.2.3.2 | Wall installation | 25 |  |  | 2023-02-08: 0
1.2.3.3 | Roof and floor installation | 0 |  |  | 2023-02-12: $35
1.2.3.4 | Interior finishing |  |  | 800 | 2023-02-12: 800
1.2.3.5 | Treehouse construction complete |  | 4769.92
1.2.4 | Suspension Bridge Construction | 2609.92 |  |  | 2023-02-05: 0; 2023-02-06: 0; 2023-02-07: 0; 2023-02-08: 0
1.2.4.1 | Design and plan bridge | 1760 |  |  | 2023-02-06: $1760; 2023-02-08: 0; 2023-02-09: 0; 2023-02-12: 0; 2023-02-13: 0
1.2.4.2 | Bridge construction | 400 |  |  | 2023-02-12: $400
1.2.4.3 | Bridge construction complete |  | 0
1.3 | Monitoring and Controlling | 3880 |  |  | 2023-02-08: 0; 2023-02-09: 0; 2023-02-12: 0; 2023-02-13: 0
1.3.1 | Quality Control | 3280 |  |  | 2023-02-14: 3280
1.3.1.1 | Inspect materials and workmanship |  | 2400 |  | 2023-02-16: $1200; 2023-02-21: $1200
1.3.1.2 | Ensure adherence to safety regulations | 880 |  |  | 2023-02-14: 711.6; 2023-02-16: $880
1.3.2 | Issue Resolution | 600 |  |  | 2023-02-14: 694.74
1.3.2.1 | Identify and resolve project issues | 400 |  |  | 2023-02-16: $200; 2023-02-21: $200
1.3.2.2 | Address quality issues |  | 200 |  | 2023-02-16: $50; 2023-02-21: $150
1.3.2.3 | Inspections and controlling complete | 0
1.4 | Closing | 1200
1.4.1 | Customer Acceptance & Project Closure
1.4.1.1 | Walkthrough with owner | 400 |  |  | 2023-02-21: $400
1.4.1.2 | Review final outcome and end project | 800 |  |  | 2023-02-21: $800
| Total | 38399.4 | 16119.92 | 3057 | 3360 | 0 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 120.13 | 0 | 0 | 120.13 | 567.63 | 120.13 | 0 | 0 | 0 | 0 | 800 | 0 | 4686.34 | 13455 | 17345 | 32678 | 0 | 0 | 39064 | 44978 | 57575
| CumulativeTotal |  |  |  | 3360 | 3360 | 3360 | 3360 | 7060 | 7060 | 7060 | 7060 | 7060 | 7060 | 7060 | 7180.13 | 7180.13 | 7180.13 | 7300.26 | 7867.89 | 7988.02 | 7988.02 | 7988.02 | 7988.02 | 7988.02 | 8788.02 | 8788.02 | 13474.36 | 26929.36 | 34576 | 39064 | 0 | 0 | 39064 | 57575 | 57575

## Resource Usage
WBS | Resource Name |  | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19 | 2023-02-20 | 2023-02-21
|  | Human Resource Imbalance | 0 | 0 | 0 | 0 | 28.2 | 39 | 0 | 2 | 2 | 2 | 31 | 0 | 0 | 0 | 0 | 27 | 0 | 4 | 0 | 0 | 60.84 | 0 | 0 | 2 | 0 | 12 | 0 | 0 | 0 | 0 | 4
Work
WBS | Resource Name | Work | 0 | 0 | 0 | 0 | 5.2 | 2 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 4 | 0 | 0 | 16 | 0 | 0 | 0
1.1.1.3 | Finalize treehouse design | 0 hrs | 2023-01-22: $0.00; 2023-01-23: 0; 2023-01-24: 0; 2023-01-25: 0; 2023-01-26: 0
1.1.2.3 | Resource and cost planning complete | 0 hrs | 2023-01-22: $0.00
1.1.3.3 | Preparation complete | 0 hrs | 2023-01-22: $0.00
1.2.1.3 | Resources acquisition complete | 0 hrs | 2023-01-22: $0.00
1.2.3.5 | Treehouse construction complete | 0 hrs | 2023-01-22: $0.00
1.2.4.3 | Bridge construction complete | 0 hrs | 2023-01-22: $0.00
1.3.2.3 | Inspections and controlling complete | 0 hrs | 2023-01-22: $0.00
| Yel | 48 hrs | 2023-01-26: 4; 2023-02-01: 4; 2023-02-06: 8; 2023-02-11: 16; 2023-02-16: 12; 2023-02-21: 4
1.1.3.2 | Conduct project kick-off meeting | 4 hrs | 2023-01-26: 1.2
1.2.2.1 | Design bracket | 8 hrs | 2023-02-01: 4; 2023-02-06: 4
1.2.2.2 | Fabricate custom brackets | 4 hrs | 2023-02-02: 0; 2023-02-05: 0; 2023-02-06: 4; 2023-02-07: 0
1.2.4.2 | Bridge construction | 16 hrs | 2023-02-08: 4
1.3.2.1 | Identify and resolve project issues | 16 hrs | 2023-02-08: 0; 2023-02-16: 12; 2023-02-21: 4
| Refas | 16 hrs | 2023-01-27: 2; 2023-02-01: 2; 2023-02-06: 4; 2023-02-14: 0; 2023-02-16: 2
1.1.3.2 | Conduct project kick-off meeting | 2 hrs
1.2.2.1 | Design bracket | 4 hrs |  | 0 | 0 | 0 | 8 | 37 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 2
1.2.2.2 | Fabricate custom brackets | 2 hrs | 2023-01-26: 2; 2023-01-29: 2; 2023-01-30: 2; 2023-01-31: 2
1.3.2.2 | Address quality issues | 8 hrs | 2023-02-08: 0; 2023-02-09: 0; 2023-02-12: 0; 2023-02-13: 0; 2023-02-16: 2; 2023-02-21: 6
| Tecan | 99 hrs | 2023-01-27: 37; 2023-02-08: 0; 2023-02-09: 0; 2023-02-11: 8; 2023-02-12: 0; 2023-02-13: 0; 2023-02-16: 18; 2023-02-20: 18
1.1.1.1 | Research and sketch treehouse | 16 hrs | 2023-01-22: 16; 2023-02-14: 0.8
1.1.2.1 | Identify materials and estimates cost | 4 hrs | 2023-01-22: 2; 2023-01-26: 2; 2023-02-14: 1.2
1.1.2.2 | Develop resource and cost plan | 4 hrs | 2023-01-26: 4
1.1.3.1 | Review goals, scope, and timelines | 15 hrs | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.84 | 0 | 0 | 0
1.1.3.2 | Conduct project kick-off meeting | 8 hrs | 2023-01-22: 0; 2023-01-26: 8
1.2.1.1 | Get quotations and select suppliers | 8 hrs | 2023-01-22: 0; 2023-01-26: 8
1.2.3.4 | Interior finishing | 8 hrs | 2023-02-11: 8
1.3.1.1 | Inspect materials and workmanship | 24 hrs | 2023-01-23: 2
1.4.1.1 | Walkthrough with owner | 4 hrs | 2023-02-21: 4
1.4.1.2 | Review final outcome and end project | 8 hrs
| Spark | 14.8 hrs | 2023-02-05: 0; 2023-02-06: 2.96; 2023-02-07: 0; 2023-02-08: 0; 2023-02-11: 11.84
1.2.2.2 | Fabricate custom brackets | 2.96 hrs | 2023-02-08: 0.16
1.2.4.2 | Bridge construction | 11.84 hrs | 2023-02-11: 16
| Architect | 40 hrs | 2023-01-22: 16; 2023-02-06: 16; 2023-02-16: 8
1.1.1.2 | Engage architect for custom design | 16 hrs | 2023-01-22: 16
1.2.4.1 | Design and plan bridge | 16 hrs | 2023-02-06: 16
1.3.1.2 | Ensure adherence to safety regulations | 8 hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| Steel Plate | 15 Sheet | 2023-01-26: 0; 2023-01-29: 0; 2023-01-30: 0; 2023-01-31: 0; 2023-02-01: 10.5; 2023-02-06: 3.5; 2023-02-11: 1
1.2.1.2 | Purchase materials & equipments | 14 Sheet | 2023-02-01: 10.5; 2023-02-05: 0; 2023-02-06: 3.5; 2023-02-07: 0; 2023-02-08: 0
1.2.3.3 | Roof and floor installation | 1 Sheet | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.25 |  | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| Wood | 70 Board Feet | 2023-01-26: 0; 2023-01-29: 0; 2023-01-30: 0; 2023-01-31: 0; 2023-02-01: 52.5; 2023-02-06: 17.5
1.2.1.2 | Purchase materials & equipments | 70 Board Feet | 2023-02-01: 3.75; 2023-02-05: 2.5; 2023-02-06: 17.5; 2023-02-07: 2.5; 2023-02-08: 2.5
| Nails | 5 Boxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.75 |  | 0 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.2 | Purchase materials & equipments | 5 Boxes | 2023-01-26: 0; 2023-01-29: 0; 2023-01-30: 0; 2023-01-31: 0; 2023-02-01: 3.75; 2023-02-06: 1.25
| Screws | 8 Boxes | 2023-01-26: 0; 2023-01-29: 0; 2023-01-30: 0; 2023-01-31: 0; 2023-02-01: 6; 2023-02-06: 2
1.2.1.2 | Purchase materials & equipments | 8 Boxes | 2023-01-26: 0; 2023-01-29: 0; 2023-01-30: 0; 2023-01-31: 0; 2023-02-01: 6; 2023-02-06: 2
| Clips | 50 Pieces | 2023-01-26: 0; 2023-01-29: 0; 2023-01-30: 0; 2023-01-31: 0; 2023-02-01: 37.5; 2023-02-06: 12.5; 2023-02-08: 5; 2023-02-14: 5
1.2.1.2 | Purchase materials & equipments | 50 Pieces | 2023-01-26: 0; 2023-01-29: 0; 2023-01-30: 0; 2023-01-31: 0; 2023-02-01: 37.5; 2023-02-06: 12.5
| Staples | 3 Boxes | 2023-02-01: 2.25; 2023-02-06: 0.75; 2023-02-08: 5
1.2.1.2 | Purchase materials & equipments | 3 Boxes | 2023-02-01: 2.25; 2023-02-06: 0.75; 2023-02-14: 5
| Steel Cables | 5 Rolls | 2023-02-01: 2.25; 2023-02-06: 1.25
1.2.1.2 | Purchase materials & equipments | 3 Rolls | 2023-02-01: 2.25; 2023-02-08: 0.25; 2023-02-09: 0.25; 2023-02-12: 0.25; 2023-02-13: 0.25
1.2.3.1 | Prepare site and build structure | 1 Rolls | 2023-02-02: 0.75; 2023-02-06: 0.5; 2023-02-08: 0; 2023-02-09: 0; 2023-02-11: 0.5; 2023-02-12: 0.25; 2023-02-13: 0.25
1.2.3.3 | Roof and floor installation | 1 Rolls | 2023-02-01: 4; 2023-02-02: 0.5; 2023-02-05: 1; 2023-02-06: 1; 2023-02-07: 1; 2023-02-08: 1; 2023-02-14: 5
| Wooden Planks | 20 Pieces | 2023-02-01: 4
1.2.1.2 | Purchase materials & equipments | 20 Pieces | bar: 2023-02-05 to 2023-02-08
| Connectors | 3 Sets | 2023-02-14: 4
1.2.1.2 | Purchase materials & equipments | 3 Sets | bar: 2023-02-14
Hoist Rental | bar: 2023-02-05 to 2023-02-08; 2023-02-14
1.2.1.2 | Purchase materials & equipments | bar: 2023-02-05 to 2023-02-08
| Concrete | 4 Cubic Yards | bar: 2023-02-14
1.2.1.2 | Purchase materials & equipments | 4 Cubic Yards | 2023-02-14: 3.75
| Paints and Stains | 8 Gallons | 2023-02-14: 3.75
1.2.1.2 | Purchase materials & equipments | 8 Gallons | 2023-02-02: 0.25; 2023-02-05: 0.25; 2023-02-06: 0.25; 2023-02-07: 0.25
| Waterproof Sealant | 5 Gallons | 2023-02-02: 0.25; 2023-02-05: 0.25; 2023-02-06: 0.25; 2023-02-07: 0.25
1.2.1.2 | Purchase materials & equipments | 5 Gallons | 2023-02-08: 10
| Insulation Material | 3 Rolls | 2023-02-08: 10
1.2.1.2 | Purchase materials & equipments | 3 Rolls
| LED Lighting | 4 Sets
1.2.1.2 | Purchase materials & equipments | 4 Sets
| Glass Windows | 5 Pieces
1.2.1.2 | Purchase materials & equipments | 5 Pieces | 2023-02-01: 1; 2023-02-05: 0.25; 2023-02-06: 0.25; 2023-02-07: 0.25; 2023-02-08: 0.25
| Roofing Shingles | 9 Bundles | bar: 2023-02-01
1.2.1.2 | Purchase materials & equipments | 8 Bundles | 2023-02-05: 0.25; 2023-02-06: 0.25; 2023-02-07: 0.25; 2023-02-08: 0.25
1.2.3.2 | Wall installation | 1 Bundles
| Ladder |  | 2023-01-26: 0.25; 2023-01-29: 0.25; 2023-01-30: 0.25; 2023-01-31: 0.25
1.2.1.2 | Purchase materials & equipments |  | 2023-01-26: 0.25; 2023-01-29: 0.25; 2023-01-30: 0.25; 2023-01-31: 0.25
| Safety Harnesses |  | 2023-02-01: 2.25; 2023-02-06: 1
1.2.1.2 | Purchase materials & equipments |  | 2023-02-01: 2.25; 2023-02-06: 1; 2023-02-08: 0.25; 2023-02-09: 0.25; 2023-02-12: 0.25; 2023-02-13: 0.25
1.2.3.2 | Wall installation |  | 2023-02-06: 2; 2023-02-08: 0.25; 2023-02-09: 0.25; 2023-02-12: 0.25; 2023-02-13: 0.25
| Miscellaneous Hardware Chest Refills |  | 2023-01-26: 0.25; 2023-01-29: 0.25; 2023-01-30: 0.25; 2023-01-31: 0.25; 2023-02-06: 2; 2023-02-08: 1
1.2.1.2 | Purchase materials & equipments |  | 2023-01-26: 0.25; 2023-01-29: 0.25; 2023-01-30: 0.25; 2023-01-31: 0.25; 2023-02-01: 15; 2023-02-06: 1.25
| Wires | 3 Rolls | 2023-02-01: 15; 2023-02-06: 1.25; 2023-02-08: 1
1.2.1.2 | Purchase materials & equipments | 3 Rolls | 2023-02-01: 2.25; 2023-02-02: 1.75; 2023-02-05: 3.5; 2023-02-06: 0.75; 2023-02-07: 3.5; 2023-02-08: 1.75
| Plywood Sheets | 15 Sheets | 2023-02-01: 2.25; 2023-02-02: 1.75; 2023-02-05: 1.75; 2023-02-06: 1; 2023-02-07: 1.75
1.2.1.2 | Purchase materials & equipments | 15 Sheets | 2023-02-01: 3; 2023-02-05: 1.75; 2023-02-06: 1; 2023-02-07: 1.75; 2023-02-08: 1.75
| Sand | 2 Cubic Yards | 2023-01-26: 0.25; 2023-01-29: 0.25; 2023-01-30: 0.25; 2023-01-31: 0.25; 2023-02-01: 3; 2023-02-06: 1.25
1.2.1.2 | Purchase materials & equipments | 2 Cubic Yards | 2023-01-26: 0.25; 2023-01-29: 0.25; 2023-01-30: 0.25; 2023-01-31: 0.25; 2023-02-01: 3.75; 2023-02-06: 1.25
| Varnish | 5 Gallons | 2023-01-26: 0.25; 2023-01-29: 0.25; 2023-01-30: 0.25; 2023-01-31: 0.25; 2023-02-01: 6; 2023-02-06: 2
1.2.1.2 | Purchase materials & equipments | 4 Gallons | 2023-01-26: 0.25; 2023-01-29: 0.25; 2023-01-30: 0.25; 2023-01-31: 0.25; 2023-02-01: 6; 2023-02-06: 2
1.2.3.4 | Interior finishing | 1 Gallons
| Light switches | 6 Pieces | 2023-02-06: 1.5
1.2.1.2 | Purchase materials & equipments | 6 Pieces | 2023-02-01: 4.5; 2023-02-06: 1.5
| Lumber (2x4) | 40 Board Feet | 2023-02-01: 30; 2023-02-06: 10
1.2.1.2 | Purchase materials & equipments | 40 Board Feet | 2023-02-01: 30; 2023-02-06: 10
WBS | Resource Name | Work | 2023-01-22: Cost

## Project Budget Worksheet
Project Contract Pricing and Project Budget | 57575.1312
| % | $ | $
Workpackage Estimate |  |  | 22580
Contingency Reserve (% of WP estimate) | 19% | 4290.2
Cost Baseline |  |  | 26870.2
Management Reserve (% of Cost Baseline) | 18.5% | 4970.987
Project Budget in CDN$ |  |  | 31841.187
Profit (% of Project Budget) | 29% | 9233.9442
Customer Price |  |  | 41075.1312
CR Approved to be paid by customer |  | 6600
CR Approved to be paid by customer |  | 9900
Total CR approved to be paid by customer |  | 16500
Total Contract Price |  |  | 57575.1312