## Sheet1
Team Participation Minutes
This file is to be attached and sent with all group work assignments or the assignment may not be marked or marks will be deducted
Team #: |  | 8
Meeting Facilitator |  | Muhammad Haider Kayani |  |  |  | Meeting Facilitator | Muhammad Haider Kayani |  | Meeting Facilitator
Planning Meeting: | [5 empty] | Additional Meeting |  |  | Additional Meeting
Date |  | 2023-11-25 |  |  |  | Date | 2023-12-03 |  | Date
Time |  | 12:00pm |  |  |  | Time | 11:00 |  | Time
Location |  | B Building, Fanshawe College |  | Not present |  | Location | J Building | Not present | Location | Not present
Attendees |  | Muhammad Haider Kayani (ID: 1170868) |  |  |  | Attendees | Muhammad Haider Kayani (ID:1170868) |  | Attendees
|  | Gihan Shamike Liyanage - (ID: 1142109) |  |  |  |  | Gihan Shamike Liyanage - (ID1142109)
|  | Jharana Ghimire - (ID: 1187000) |  |  |  |  | Jharana Ghimire - (ID: 1187000)
Tasks: |  |  | Use - Accountable -A and Responsible -R
|  | Tasks or Activities | Team Member Names | Group Internal Due date | % Completed on time | Additional Notes and Comments on Work Performed by team members
| 1 | Discussion Meeting | Gihan-A, Kayani-R, Jharana-R | Jan 7, 9PM | 100% | Everyone Tried there best to Complete the project, There might be some errors, But everyone gave there 100 percent, As we were only 3 in Group, Our 4th member was not in the course.
| 2 | Sketches | Jharana-A | Nov 19, 7PM | 100% | Jharana did a great work on sketches
| 3 | MS Project Work | Gihan-A, Kayani-R | Nov 27, 4 PM | 100% | Sushan and Maitri were internally grouped together to assist each other on their respective tasks
| 4 | MS Excel Work | Gihan-A, Jharana, Kayani-R | Dec 3, 2 PM | 90% | Some mistakes were done in start which we tried to figure out and corrected them to our level best
| 5 | Assignment work plan | Kayani-A,Jharana | Dec 3, 2 PM | 100% | Kayani and jharana discussed this and completed the task
| 6 | Final Powerpoint presentation | Jharana-A, Kayani-A | Dec 4, 10 PM | 80% | The final powerpoint presentation was to be finalized after checklist review.
| 7 | Team participation minutes | Jharana-A, Kayani-A,Gihan-A | Dec 2, 5 PM | 100% | Completed on time
| 8 | Checklist Review of final deliverables | Gihan-A | Dec 4, 3 PM | 100% | It was fun.
| 9 | Final Submission | Kayani-R | Dec 5, 9 pm | 100% | kayani uploaded them after giving all titles an overview.
10
11
12
Note on A9: Mckenna, David: This position is rotated week over week. The role of meeing facilitator may be different than the group leader.
Note on C9: Name of meeting facilitator. This position is rotated week over week. The president of the team ensure compliance
Note on H9: Mckenna, David: This position is rotated week over week. The role of meeing facilitator may be different than the group leader.
Note on J9: Name of meeting facilitator. This position is rotated week over week. The president of the team ensure compliance
Note on N9: Mckenna, David: This position is rotated week over week. The role of meeing facilitator may be different than the group leader.
Note on P9: Name of meeting facilitator. This position is rotated week over week. The president of the team ensure compliance
Note on C12: Date of meeting
Note on J12: Date of meeting
Note on P12: Date of meeting
Note on C13: Time of meeting and duration (i.e. 1:00 pm to 1:30 pm)
Note on J13: Time of meeting and duration (i.e. 1:00 pm to 1:30 pm)
Note on P13: Time of meeting and duration (i.e. 1:00 pm to 1:30 pm)
Note on C14: Physical location of meeting (D cafeteria)
Note on E14: Hemington, Derek: Group members could attend the meeting virtually, e.g. via the web
Note on J14: Physical location of meeting (D cafeteria)
Note on L14: Hemington, Derek: Group members could attend the meeting virtually, e.g. via the web
Note on P14: Physical location of meeting (D cafeteria)
Note on R14: Hemington, Derek: Group members could attend the meeting virtually, e.g. via the web
Note on C15: List all of the attendee that are present at the meeting. If some members are not present this is noted. Those not present are still assigned tasks for the assignment
Note on E15: List names of members of the team that do not attend meeting. If a member does not attend they still are given a task to complete
Note on J15: List all of the attendee that are present at the meeting. If some members are not present this is noted. Those not present are still assigned tasks for the assignment
Note on L15: List names of members of the team that do not attend meeting. If a member does not attend they still are given a task to complete
Note on P15: List all of the attendee that are present at the meeting. If some members are not present this is noted. Those not present are still assigned tasks for the assignment
Note on R15: List names of members of the team that do not attend meeting. If a member does not attend they still are given a task to complete
Note on C23: Describe the tasks or activities to be completed by the individual
Note on D23: Name of the person accountable for the task to be completed
Note on F23: This is the accountability of the facilitator. If the task is not compled by the due date the task is considered not completed, and a % complete less than 100 would be entered