## WBS Data Dictionary
Duration Estimates in days
WBS Code | Activity | O | M | P | PERT Calculation | Revised PERT Rounded Up or Minimum | Hours of work planned per day used in the M Duration | Total hours of work based on M days | Work Hours/day based on Revised PERT duration | Units for mpp Resource assignment to the Activity | Cross-check, total hours of work based on PERT duration
1 | Island Cottage Enhancement Project
1.1 | Preparation
1.1.1 | Planning and Design
1.1.1.1 | Design and plan outdoor amenities layout | 1 | 2 | 3 | 2 | 2 | 8 | 16 | 8 | 100% | 16
1.1.1.2 | Develop detailed blueprints | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.1.1.3 | Apply and obtain Regulatory approvals | 0.5 | 1 | 2 | 1.0833 | 2 | 8 | 8 | 4 | 50% | 8
1.1.2 | Survey and Assessment
1.1.2.1 | Research erosion control methods | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.1.2.2 | Obtain quotes from erosion control specialists | 0.5 | 1 | 2 | 1.0833 | 2 | 8 | 8 | 4 | 50% | 8
1.1.2.3 | Analyze survey results and assess erosion risk areas | 0.5 | 1 | 2.5 | 1.1667 | 2 | 8 | 8 | 4 | 50% | 8
1.1.3 | Project Kickoff
1.1.3.1 | Review Project Plan and Timeline | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.1.3.2 | Officially launch the project. | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.2 | Buying Resources
1.2.1 | Cost Estimation
1.2.1.1 | Estimate cost for outdoor amenities | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.2.1.2 | Finalize cost | 1 | 1 | 1 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.2.2 | Materials and Equipments
1.2.2.1 | Create a list of preferred suppliers | 1 | 2 | 3 | 2 | 2 | 8 | 16 | 8 | 100% | 16
1.2.2.2 | Get quotations from selected suppliers | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.2.2.3 | Purchase materials | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.2.2.4 | Procure equipments | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.2.2.5 | Coordinate delivery | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.2.3 | Manpower
1.2.3.1 | Select qualified contractor | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.2.3.2 | Share detailed scope of work and expectations | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.2.3.3 | Finalize contracts and agreements | 0.5 | 1 | 2 | 1.0833 | 2 | 8 | 8 | 4 | 50% | 8
1.2.3.4 | Resources acquire complete
1.3 | Construction
1.3.1 | Stone Stairs
1.3.1.1 | Excavate the soil | 1 | 2 | 3 | 2 | 2 | 8 | 16 | 8 | 100% | 16
1.3.1.2 | Build Stairs | 2 | 3 | 3.5 | 2.9167 | 3 | 8 | 24 | 8 | 100% | 24
1.3.1.3 | Grouting and Finishing | 0.5 | 1 | 2 | 1.0833 | 2 | 8 | 8 | 4 | 50% | 8
1.3.2 | Boat Dock 1
1.3.2.1 | Excavate the lakebed | 1 | 2 | 2 | 1.8333 | 2 | 8 | 16 | 8 | 100% | 16
1.3.2.2 | Assemble and install the dock structure | 1 | 2 | 2.5 | 1.9167 | 2 | 8 | 16 | 8 | 100% | 16
1.3.2.3 | Attach necessary accessories (bumpers, and safety ladders) | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.3.3 | Boat Dock 2
1.3.3.1 | Excavate the lakebed | 0.5 | 1 | 2 | 1.0833 | 2 | 8 | 8 | 4 | 50% | 8
1.3.3.2 | Assemble and install the dock structure | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.3.3.3 | Attach necessary accessories (bumpers, and safety ladders) | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.3.4 | Floating Dock
1.3.4.1 | Assemble the individual floating dock sections | 1 | 1 | 2 | 1.1667 | 2 | 8 | 8 | 4 | 50% | 8
1.3.4.2 | Install the necessary connectors and hinges | 1 | 2 | 3 | 2 | 2 | 8 | 16 | 8 | 100% | 16
1.3.4.3 | Anchor the floating dock to the lakebed | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.3.5 | Tent Pitching Area
1.3.5.1 | Level the ground surface | 2 | 3 | 3.5 | 2.9167 | 3 | 8 | 24 | 8 | 100% | 24
1.3.5.2 | Install tent platforms | 1 | 2 | 3 | 2 | 2 | 8 | 16 | 8 | 100% | 16
1.3.5.3 | Set up designated fire pit area | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.3.6 | Rustic Swing Set
1.3.6.1 | Create frame | 0.5 | 1 | 2.5 | 1.1667 | 2 | 8 | 8 | 4 | 50% | 8
1.3.6.2 | Install swing set | 0.5 | 1 | 1 | 0.91667 | 1 | 8 | 8 | 8 | 100% | 8
1.3.7 | Erosion Control
1.3.7.1 | Install physical erosion control structures | 1 | 2 | 3 | 2 | 2 | 8 | 16 | 8 | 100% | 16
1.3.7.2 | Plant erosion-resistant vegetation | 0.5 | 1 | 1.4 | 0.98333 | 1 | 8 | 8 | 8 | 100% | 8
1.3.7.3 | Monitor the effectiveness | 3 | 4 | 4.5 | 3.9167 | 4 | 8 | 32 | 8 | 100% | 32
1.3.7.4 | Construction complete
1.4 | Final Touches
1.4.1 | Lanscaping and Pathways
1.4.1.1 | Preparing soil | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.4.1.2 | Plant native plants and shrubs for shoreline | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.4.1.3 | Install irrigation system | 0.5 | 1 | 2 | 1.0833 | 2 | 8 | 8 | 4 | 50% | 8
1.4.1.4 | Install hardscaping elements | 1 | 2 | 3 | 2 | 2 | 8 | 16 | 8 | 100% | 16
1.4.1.5 | Place outdoor decors | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.4.2 | Outdoor Lighting
1.4.2.1 | Install outdoor lighting along paths | 0.5 | 1 | 2 | 1.0833 | 2 | 8 | 8 | 4 | 50% | 8
1.4.2.2 | Install lights near recreational areas | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.4.2.3 | Install lights in tent pitching area | 0.5 | 1 | 1 | 0.91667 | 1 | 8 | 8 | 8 | 100% | 8
1.4.3 | Cleaning and Grading
1.4.3.1 | Clear debris and unwanted vegetation | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.4.3.2 | Dispose debris | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.4.3.3 | Final touches complete
1.5 | Project End
1.5.1 | Final Inspection
1.5.1.1 | Test outdoor lighting | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.5.1.2 | Test irrigation system | 1 | 2 | 2.5 | 1.9167 | 2 | 8 | 16 | 8 | 100% | 16
1.5.1.3 | Check quality of construction work | 0.5 | 1 | 1.5 | 1 | 1 | 8 | 8 | 8 | 100% | 8
1.5.2 | Review Outcome
1.5.2.1 | Review final outcome and end project | 0.5 | 1 | 1 | 0.91667 | 1 | 8 | 8 | 8 | 100% | 8
[7 empty] | Total | 552 |  | Total | 552

## Simple Gantt
WBS | Activity | Dur (days) | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24
1.1.1.1 | Design and plan outdoor amenities layout | 2 | bar: 2023-10-17 to 2023-10-18
1.1.1.2 | Develop detailed blueprints | 1 | bar: 2023-10-19
1.1.1.3 | Apply and obtain Regulatory approvals | 2 | bar: 2023-10-18 to 2023-10-19
1.1.2.1 | Research erosion control methods | 1 | bar: 2023-10-19
1.1.2.2 | Obtain quotes from erosion control specialists | 2 | bar: 2023-10-20 to 2023-10-23
1.1.2.3 | Analyze survey results and assess erosion risk areas | 2 | bar: 2023-10-20 to 2023-10-23
1.1.3.1 | Review Project Plan and Timeline | 1 | bar: 2023-10-24
1.1.3.2 | Officially launch the project. | 1 | bar: 2023-10-25
1.2.1.1 | Estimate cost for outdoor amenities | 1 | bar: 2023-10-26
1.2.1.2 | Finalize cost | 1 | bar: 2023-10-27
1.2.2.1 | Create a list of preferred suppliers | 2 | bar: 2023-10-25 to 2023-10-26
1.2.2.2 | Get quotations from selected suppliers | 1 | bar: 2023-10-27
1.2.2.3 | Purchase materials | 1 | bar: 2023-10-30
1.2.2.4 | Procure equipments | 1 | bar: 2023-10-30
1.2.2.5 | Coordinate delivery | 1 | bar: 2023-10-31
1.2.3.1 | Select qualified contractor | 1 | bar: 2023-10-30
1.2.3.2 | Share detailed scope of work and expectations | 1 | bar: 2023-10-31
1.2.3.3 | Finalize contracts and agreements | 2 | bar: 2023-10-31 to 2023-11-01
1.3.1.1 | Excavate the soil | 2 | bar: 2023-11-02 to 2023-11-03
1.3.1.2 | Build Stairs | 3 | bar: 2023-11-03 to 2023-11-07
1.3.1.3 | Grouting and Finishing | 2 | bar: 2023-11-06 to 2023-11-07
1.3.2.1 | Excavate the lakebed | 2 | bar: 2023-11-02 to 2023-11-03
1.3.2.2 | Assemble and install the dock structure | 2 | bar: 2023-11-06 to 2023-11-07
1.3.2.3 | Attach necessary accessories (bumpers, and safety ladders) | 1 | bar: 2023-11-08
1.3.3.1 | Excavate the lakebed | 2 | bar: 2023-11-02 to 2023-11-03
1.3.3.2 | Assemble and install the dock structure | 1 | bar: 2023-11-06
1.3.3.3 | Attach necessary accessories (bumpers, and safety ladders) | 1 | bar: 2023-11-07
1.3.4.1 | Assemble the individual floating dock sections | 2 | bar: 2023-11-02 to 2023-11-03
1.3.4.2 | Install the necessary connectors and hinges | 2 | bar: 2023-11-06 to 2023-11-07
1.3.4.3 | Anchor the floating dock to the lakebed | 1 | bar: 2023-11-06
1.3.5.1 | Level the ground surface | 3 | bar: 2023-11-02 to 2023-11-06
1.3.5.2 | Install tent platforms | 2 | bar: 2023-11-07 to 2023-11-08
1.3.5.3 | Set up designated fire pit area | 1 | bar: 2023-11-09
1.3.6.1 | Create frame | 2 | bar: 2023-11-08 to 2023-11-09
1.3.6.2 | Install swing set | 1 | bar: 2023-11-10
1.3.7.1 | Install physical erosion control structures | 2 | bar: 2023-11-02 to 2023-11-03
1.3.7.2 | Plant erosion-resistant vegetation | 1 | bar: 2023-11-06
1.3.7.3 | Monitor the effectiveness | 4 | bar: 2023-11-07 to 2023-11-10
1.4.1.1 | Preparing soil | 1 | bar: 2023-11-13
1.4.1.2 | Plant native plants and shrubs for shoreline | 1 | bar: 2023-11-14
1.4.1.3 | Install irrigation system | 2 | bar: 2023-11-14 to 2023-11-15
1.4.1.4 | Install hardscaping elements | 2 | bar: 2023-11-15 to 2023-11-16
1.4.1.5 | Place outdoor decors | 1 | bar: 2023-11-16
1.4.2.1 | Install outdoor lighting along paths | 2 | bar: 2023-11-16 to 2023-11-17
1.4.2.2 | Install lights near recreational areas | 1 | bar: 2023-11-17
1.4.2.3 | Install lights in tent pitching area | 1 | bar: 2023-11-17
1.4.3.1 | Clear debris and unwanted vegetation | 1 | bar: 2023-11-17
1.4.3.2 | Dispose debris | 1 | bar: 2023-11-20
1.5.1.1 | Test outdoor lighting | 1 | bar: 2023-11-21
1.5.1.2 | Test irrigation system | 2 | bar: 2023-11-21 to 2023-11-22
1.5.1.3 | Check quality of construction work | 1 | bar: 2023-11-23
1.5.2.1 | Review final outcome and end project | 1 | bar: 2023-11-24

## Medium Complexity Gantt
WBS | Activity | Dur (days) | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24
1 | Island Cottage Enhancement Project | 29
1.1 | Preparation | 7
1.1.1 | Planning and Design | 3 | bar: 2023-10-17 to 2023-10-19
1.1.1.1 | Design and plan outdoor amenities layout | 2 | bar: 2023-10-17 to 2023-10-18
1.1.1.2 | Develop detailed blueprints | 1 | bar: 2023-10-19
1.1.1.3 | Apply and obtain Regulatory approvals | 2 | bar: 2023-10-18 to 2023-10-19
1.1.2 | Survey and Assessment | 3 | bar: 2023-10-19 to 2023-10-20; 2023-10-23
1.1.2.1 | Research erosion control methods | 1 | bar: 2023-10-19
1.1.2.2 | Obtain quotes from erosion control specialists | 2 | bar: 2023-10-20 to 2023-10-23
1.1.2.3 | Analyze survey results and assess erosion risk areas | 2 | bar: 2023-10-20 to 2023-10-23
1.1.3 | Project Kickoff | 2 | bar: 2023-10-24 to 2023-10-25
1.1.3.1 | Review Project Plan and Timeline | 1 | bar: 2023-10-24
1.1.3.2 | Officially launch the project. | 1 | bar: 2023-10-25
1.2 | Buying Resources | 6
1.2.1 | Cost Estimation | 2 | bar: 2023-10-26 to 2023-10-27
1.2.1.1 | Estimate cost for outdoor amenities | 1 | bar: 2023-10-26
1.2.1.2 | Finalize cost | 1 | bar: 2023-10-27
1.2.2 | Materials and Equipments | 5 | bar: 2023-10-25 to 2023-10-27; 2023-10-30 to 2023-10-31
1.2.2.1 | Create a list of preferred suppliers | 2 | bar: 2023-10-25 to 2023-10-26
1.2.2.2 | Get quotations from selected suppliers | 1 | bar: 2023-10-27
1.2.2.3 | Purchase materials | 1 | bar: 2023-10-30
1.2.2.4 | Procure equipments | 1 | bar: 2023-10-30
1.2.2.5 | Coordinate delivery | 1 | bar: 2023-10-31
1.2.3 | Manpower | 3 | bar: 2023-10-30 to 2023-11-01
1.2.3.1 | Select qualified contractor | 1 | bar: 2023-10-30
1.2.3.2 | Share detailed scope of work and expectations | 1 | bar: 2023-10-31
1.2.3.3 | Finalize contracts and agreements | 2 | bar: 2023-10-31 to 2023-11-01
1.2.3.4 | Resources acquire complete | 0 | bar: 2023-11-01
1.3 | Construction | 7
1.3.1 | Stone Stairs | 4 | bar: 2023-11-02 to 2023-11-03; 2023-11-06 to 2023-11-07
1.3.1.1 | Excavate the soil | 2 | bar: 2023-11-02 to 2023-11-03
1.3.1.2 | Build Stairs | 3 | bar: 2023-11-03 to 2023-11-07
1.3.1.3 | Grouting and Finishing | 2 | bar: 2023-11-06 to 2023-11-07
1.3.2 | Boat Dock 1 | 5 | bar: 2023-11-02 to 2023-11-03; 2023-11-06 to 2023-11-08
1.3.2.1 | Excavate the lakebed | 2 | bar: 2023-11-02 to 2023-11-03
1.3.2.2 | Assemble and install the dock structure | 2 | bar: 2023-11-06 to 2023-11-07
1.3.2.3 | Attach necessary accessories (bumpers, and safety ladders) | 1 | bar: 2023-11-08
1.3.3 | Boat Dock 2 | 4 | bar: 2023-11-02 to 2023-11-03; 2023-11-06 to 2023-11-07
1.3.3.1 | Excavate the lakebed | 2 | bar: 2023-11-02 to 2023-11-03
1.3.3.2 | Assemble and install the dock structure | 1 | bar: 2023-11-06
1.3.3.3 | Attach necessary accessories (bumpers, and safety ladders) | 1 | bar: 2023-11-07
1.3.4 | Floating Dock | 4 | bar: 2023-11-02 to 2023-11-03; 2023-11-06 to 2023-11-07
1.3.4.1 | Assemble the individual floating dock sections | 2 | bar: 2023-11-02 to 2023-11-03
1.3.4.2 | Install the necessary connectors and hinges | 2 | bar: 2023-11-06 to 2023-11-07
1.3.4.3 | Anchor the floating dock to the lakebed | 1 | bar: 2023-11-06
1.3.5 | Tent Pitching Area | 6 | bar: 2023-11-02 to 2023-11-03; 2023-11-06 to 2023-11-09
1.3.5.1 | Level the ground surface | 3 | bar: 2023-11-02 to 2023-11-06
1.3.5.2 | Install tent platforms | 2 | bar: 2023-11-07 to 2023-11-08
1.3.5.3 | Set up designated fire pit area | 1 | bar: 2023-11-09
1.3.6 | Rustic Swing Set | 3 | bar: 2023-11-08 to 2023-11-10
1.3.6.1 | Create frame | 2 | bar: 2023-11-08 to 2023-11-09
1.3.6.2 | Install swing set | 1 | bar: 2023-11-10
1.3.7 | Erosion Control | 7 | bar: 2023-11-02 to 2023-11-03; 2023-11-06 to 2023-11-10
1.3.7.1 | Install physical erosion control structures | 2 | bar: 2023-11-02 to 2023-11-03
1.3.7.2 | Plant erosion-resistant vegetation | 1 | bar: 2023-11-06
1.3.7.3 | Monitor the effectiveness | 4 | bar: 2023-11-07 to 2023-11-10
1.3.7.4 | Contruction complete | 0 | bar: 2023-11-10
1.4 | Final Touches | 6
1.4.1 | Lanscaping and Pathways | 4 | bar: 2023-11-13 to 2023-11-16
1.4.1.1 | Preparing soil | 1 | bar: 2023-11-13
1.4.1.2 | Plant native plants and shrubs for shoreline | 1 | bar: 2023-11-14
1.4.1.3 | Install irrigation system | 2 | bar: 2023-11-14 to 2023-11-15
1.4.1.4 | Install hardscaping elements | 2 | bar: 2023-11-15 to 2023-11-16
1.4.1.5 | Place outdoor decors | 1 | bar: 2023-11-16
1.4.2 | Outdoor Lighting | 2 | bar: 2023-11-16 to 2023-11-17
1.4.2.1 | Install outdoor lighting along paths | 2 | bar: 2023-11-16 to 2023-11-17
1.4.2.2 | Install lights near recreational areas | 1 | bar: 2023-11-17
1.4.2.3 | Install lights in tent pitching area | 1 | bar: 2023-11-17
1.4.3 | Cleaning and Grading | 2 | bar: 2023-11-17; 2023-11-20
1.4.3.1 | Clear debris and unwanted vegetation | 1 | bar: 2023-11-17
1.4.3.2 | Dispose debris | 1 | bar: 2023-11-20
1.4.3.3 | Final touches complete | 0 | bar: 2023-11-20
1.5 | Project End | 4
1.5.1 | Final Inspection | 3 | bar: 2023-11-21 to 2023-11-23
1.5.1.1 | Test outdoor lighting | 1 | bar: 2023-11-21
1.5.1.2 | Test irrigation system | 2 | bar: 2023-11-21 to 2023-11-22
1.5.1.3 | Check quality of construction work | 1 | bar: 2023-11-23
1.5.2 | Review Outcome | 1 | bar: 2023-11-24
1.5.2.1 | Review final outcome and end project | 1 | bar: 2023-11-24