## Simple Resource Usage 1
WBS Code | Resource Name | Work | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-06 | 2024-01-07 | 2024-01-08 | 2024-01-09 | 2024-01-10 | 2024-01-11 | 2024-01-12 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02
| Spike | 114 hrs | bar: 2024-01-01 to 2024-01-04; 2024-01-08 to 2024-01-10; 2024-01-15 to 2024-01-19; 2024-01-22 to 2024-01-26; 2024-01-29; 2024-02-02
| Bronia | 92 hrs | bar: 2024-01-01 to 2024-01-05; 2024-01-08 to 2024-01-12; 2024-01-15 to 2024-01-19; 2024-01-22; 2024-01-24 to 2024-01-26; 2024-01-29 to 2024-01-31; 2024-02-02
| Tolu | 42 hrs | bar: 2024-01-01 to 2024-01-05; 2024-01-10 to 2024-01-11; 2024-01-17 to 2024-01-19; 2024-01-22 to 2024-01-26; 2024-01-29 to 2024-02-02
| Concrete Base | 12 pcs | 2024-01-04: 12
| Base wooden frames | 1 lot | 2024-01-02: 0.25; 2024-01-03: 0.25; 2024-01-04: 0.25; 2024-01-05: 0.25
| Wire mesh | 36 Square Feet | 2024-01-08: 12; 2024-01-09: 12; 2024-01-10: 12
| Nail gun and Compressor | 4 lot | 2024-01-10: 0.5; 2024-01-11: 0.5; 2024-01-15: 0.25; 2024-01-16: 0.25; 2024-01-17: 0.5; 2024-01-18: 0.5; 2024-01-19: 0.75; 2024-01-22: 0.75
| Ladder | 1 lot | 2024-01-15: 0.5; 2024-01-16: 0.5
| Plywood | 177 Square Feet | 2024-01-11: 18; 2024-01-12: 18; 2024-01-15: 30; 2024-01-16: 30; 2024-01-19: 40.5; 2024-01-22: 40.5
| Roof rafter woods | 1 lot | 2024-01-15: 0.25; 2024-01-16: 0.25; 2024-01-17: 0.25; 2024-01-18: 0.25
| Wall structure woods | 1 lot | 2024-01-10: 0.5; 2024-01-11: 0.5
| Aluminium roofing sheet | 81 Square Feet | 2024-01-17: 20.25; 2024-01-18: 20.25; 2024-01-19: 20.25; 2024-01-22: 20.25
| Asphalt felt | 81 sqaure feet | 2024-01-17: 20.25; 2024-01-18: 20.25; 2024-01-19: 20.25; 2024-01-22: 20.25
| Window | 3 lot | 2024-01-23: 3
| Door | 1 lot | bar: 2024-01-24
| G-Saw | 1 | 2024-01-09: 0.25; 2024-01-10: 0.25; 2024-01-11: 0.25; 2024-01-12: 0.25
| Rockwool | 81 Square Feet | 2024-01-25: 81
| Cedar shakes | 81 Square Feet | 2024-01-29: 20.25; 2024-01-30: 20.25; 2024-01-31: 20.25; 2024-02-01: 20.25
| T&G wood panels | 81 Square Feet | 2024-01-23: 20.25; 2024-01-24: 20.25; 2024-01-25: 20.25; 2024-01-26: 20.25
| Wood stoves and chimney | 1 lot | 2024-01-26: 0.25; 2024-01-29: 0.25; 2024-01-30: 0.25; 2024-01-31: 0.25
| Plastic climbing rocks | 1 lot | 2024-01-24: 0.25; 2024-01-25: 0.25; 2024-01-26: 0.25; 2024-01-29: 0.25
| Floor insulation | 36 Square Feet | 2024-01-11: 18; 2024-01-12: 18
| Miscelleneous (5% of $1000) | 15 |  | 0.25 | 0.25 | 0.25 | 0.25 |  |  | 0.33 | 0.58 | 1.08 | 1.25 | 0.75 |  |  | 0.75 | 0.75 | 0.5 | 0.5 | 0.75 |  |  | 0.75 | 0.25 | 1.5 | 1.5 | 0.75 |  |  | 0.75 | 0.5 | 0.5 | 0.25

## Simple Resource Usage 2
WBS Code | Resource Name | Work | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-06 | 2024-01-07 | 2024-01-08 | 2024-01-09 | 2024-01-10 | 2024-01-11 | 2024-01-12 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02
| Spike | 114 hrs | bar: 2024-01-01 to 2024-01-04; 2024-01-08 to 2024-01-10; 2024-01-15 to 2024-01-19; 2024-01-22 to 2024-01-26; 2024-01-29; 2024-02-02
1.1.1.1 | Gather requirement and plan | 6 hrs | bar: 2024-01-01
1.1.2.1 | Generate budget | 12 hrs | bar: 2024-01-02 to 2024-01-03
1.1.3.1 | Position concrete base | 6 hrs | bar: 2024-01-04
1.1.4.1 | Install wire mesh and floor insulations | 18 hrs | bar: 2024-01-08 to 2024-01-10
1.1.5.2 | Install wall boards | 12 hrs | bar: 2024-01-15 to 2024-01-16
1.1.6.4 | Install roof insualtion (asphalt felt) | 24 hrs | bar: 2024-01-17 to 2024-01-19; 2024-01-22
1.1.7.1 | Install fabricated aluminium windown | 6 hrs | bar: 2024-01-23
1.1.9.3 | Install climbing wall | 24 hrs | bar: 2024-01-24 to 2024-01-26; 2024-01-29
1.1.11.1 | Inspection and Sign off | 6 hrs | bar: 2024-02-02
| Bronia | 92 hrs | bar: 2024-01-01 to 2024-01-05; 2024-01-08 to 2024-01-12; 2024-01-15 to 2024-01-19; 2024-01-22; 2024-01-24 to 2024-01-26; 2024-01-29 to 2024-01-31; 2024-02-02
1.1.1.1 | Gather requirement and plan | 4 hrs | bar: 2024-01-01
1.1.2.1 | Generate budget | 8 hrs | bar: 2024-01-02 to 2024-01-03
1.1.2.2 | Purchase material | 12 hrs | bar: 2024-01-04 to 2024-01-05; 2024-01-08
1.1.6.1 | Measure and cut rafter to size | 16 hrs | bar: 2024-01-09 to 2024-01-12
1.1.6.2 | Install rafter | 16 hrs | bar: 2024-01-15 to 2024-01-18
1.1.6.3 | Install roof boards | 8 hrs | bar: 2024-01-19; 2024-01-22
1.1.8.1 | Install wooden seethrough door | 4 hrs | bar: 2024-01-24
1.1.9.1 | Install rockwool | 4 hrs | bar: 2024-01-25
1.1.9.4 | Install wood stove and chimney | 16 hrs | bar: 2024-01-26; 2024-01-29 to 2024-01-31
1.1.11.1 | Inspection and Sign off | 4 hrs | bar: 2024-02-02
| Tolu | 42 hrs | bar: 2024-01-01 to 2024-01-05; 2024-01-10 to 2024-01-11; 2024-01-17 to 2024-01-19; 2024-01-22 to 2024-01-26; 2024-01-29 to 2024-02-02
1.1.1.1 | Gather requirement and plan | 2 hrs | bar: 2024-01-01
1.1.3.2 | Install base frames | 8 hrs | bar: 2024-01-02 to 2024-01-05
1.1.5.1 | Assemble and install wall frame | 4 hrs | bar: 2024-01-10 to 2024-01-11
1.1.6.5 | Install aluminium roofing sheet | 8 hrs | bar: 2024-01-17 to 2024-01-19; 2024-01-22
1.1.9.1 | Install rockwool | 2 hrs | bar: 2024-01-25
1.1.9.2 | Instal T&G wood panel | 8 hrs | bar: 2024-01-23 to 2024-01-26
1.1.10.1 | Install cedar shakes | 8 hrs | bar: 2024-01-29 to 2024-02-01
1.1.11.1 | Inspection and Sign off | 2 hrs | bar: 2024-02-02
| Concrete Base | 12 pcs | 2024-01-04: 12
1.1.3.1 | Position concrete base | 12 pcs | 2024-01-04: 12
| Base wooden frames | 1 lot | 2024-01-02: 0.25; 2024-01-03: 0.25; 2024-01-04: 0.25; 2024-01-05: 0.25
1.1.3.2 | Install base frames | 1 lot | 2024-01-02: 0.25; 2024-01-03: 0.25; 2024-01-04: 0.25; 2024-01-05: 0.25
| Wire mesh | 36 Square Feet | 2024-01-08: 12; 2024-01-09: 12; 2024-01-10: 12
1.1.4.1 | Install wire mesh and floor insulations | 36 Square Feet | 2024-01-08: 12; 2024-01-09: 12; 2024-01-10: 12
| Nail gun and Compressor | 4 lot | 2024-01-10: 0.5; 2024-01-11: 0.5; 2024-01-15: 0.25; 2024-01-16: 0.25; 2024-01-17: 0.5; 2024-01-18: 0.5; 2024-01-19: 0.75; 2024-01-22: 0.75
1.1.5.1 | Assemble and install wall frame | 1 lot | 2024-01-10: 0.5; 2024-01-11: 0.5
1.1.6.2 | Install rafter | 1 lot | 2024-01-15: 0.25; 2024-01-16: 0.25; 2024-01-17: 0.25; 2024-01-18: 0.25
1.1.6.3 | Install roof boards | 1 lot | 2024-01-19: 0.5; 2024-01-22: 0.5
1.1.6.5 | Install aluminium roofing sheet | 1 lot | 2024-01-17: 0.25; 2024-01-18: 0.25; 2024-01-19: 0.25; 2024-01-22: 0.25
| Ladder | 1 lot | 2024-01-15: 0.5; 2024-01-16: 0.5
1.1.5.2 | Install wall boards | 1 lot | 2024-01-15: 0.5; 2024-01-16: 0.5
| Plywood | 177 Square Feet | 2024-01-11: 18; 2024-01-12: 18; 2024-01-15: 30; 2024-01-16: 30; 2024-01-19: 40.5; 2024-01-22: 40.5
1.1.4.2 | Install floor board | 36 Square Feet | 2024-01-11: 18; 2024-01-12: 18
1.1.5.2 | Install wall boards | 60 Square Feet | 2024-01-15: 30; 2024-01-16: 30
1.1.6.3 | Install roof boards | 81 Square Feet | 2024-01-19: 40.5; 2024-01-22: 40.5
| Roof rafter woods | 1 lot | 2024-01-15: 0.25; 2024-01-16: 0.25; 2024-01-17: 0.25; 2024-01-18: 0.25
1.1.6.2 | Install rafter | 1 lot | 2024-01-15: 0.25; 2024-01-16: 0.25; 2024-01-17: 0.25; 2024-01-18: 0.25
| Wall structure woods | 1 lot | 2024-01-10: 0.5; 2024-01-11: 0.5
1.1.5.1 | Assemble and install wall frame | 1 lot | 2024-01-10: 0.5; 2024-01-11: 0.5
| Aluminium roofing sheet | 81 Square Feet | 2024-01-17: 20.25; 2024-01-18: 20.25; 2024-01-19: 20.25; 2024-01-22: 20.25
1.1.6.5 | Install aluminium roofing sheet | 81 Square Feet | 2024-01-17: 20.25; 2024-01-18: 20.25; 2024-01-19: 20.25; 2024-01-22: 20.25
| Asphalt felt | 81 sqaure feet | 2024-01-17: 20.25; 2024-01-18: 20.25; 2024-01-19: 20.25; 2024-01-22: 20.25
1.1.6.4 | Install roof insualtion (asphalt felt) | 81 sqaure feet | 2024-01-17: 20.25; 2024-01-18: 20.25; 2024-01-19: 20.25; 2024-01-22: 20.25
| Window | 3 lot | 2024-01-23: 3
1.1.7.1 | Install fabricated aluminium windown | 3 lot | 2024-01-23: 3
| Door | 1 lot | bar: 2024-01-24
1.1.8.1 | Install wooden seethrough door | 1 lot | bar: 2024-01-24
| G-Saw | 1 | 2024-01-09: 0.25; 2024-01-10: 0.25; 2024-01-11: 0.25; 2024-01-12: 0.25
1.1.6.1 | Measure and cut rafter to size | 1 | 2024-01-09: 0.25; 2024-01-10: 0.25; 2024-01-11: 0.25; 2024-01-12: 0.25
| Rockwool | 81 Square Feet | 2024-01-25: 81
1.1.9.1 | Install rockwool | 81 Square Feet | 2024-01-25: 81
| Cedar shakes | 81 Square Feet | 2024-01-29: 20.25; 2024-01-30: 20.25; 2024-01-31: 20.25; 2024-02-01: 20.25
1.1.10.1 | Install cedar shakes | 81 Square Feet | 2024-01-29: 20.25; 2024-01-30: 20.25; 2024-01-31: 20.25; 2024-02-01: 20.25
| T&G wood panels | 81 Square Feet | 2024-01-23: 20.25; 2024-01-24: 20.25; 2024-01-25: 20.25; 2024-01-26: 20.25
1.1.9.2 | Instal T&G wood panel | 81 Square Feet | 2024-01-23: 20.25; 2024-01-24: 20.25; 2024-01-25: 20.25; 2024-01-26: 20.25
| Wood stoves and chimney | 1 lot | 2024-01-26: 0.25; 2024-01-29: 0.25; 2024-01-30: 0.25; 2024-01-31: 0.25
1.1.9.4 | Install wood stove and chimney | 1 lot | 2024-01-26: 0.25; 2024-01-29: 0.25; 2024-01-30: 0.25; 2024-01-31: 0.25
| Plastic climbing rocks | 1 lot | 2024-01-24: 0.25; 2024-01-25: 0.25; 2024-01-26: 0.25; 2024-01-29: 0.25
1.1.9.3 | Install climbing wall | 1 lot | 2024-01-24: 0.25; 2024-01-25: 0.25; 2024-01-26: 0.25; 2024-01-29: 0.25
| Floor insulation | 36 Square Feet | 2024-01-11: 18; 2024-01-12: 18
1.1.4.2 | Install floor board | 36 Square Feet | 2024-01-11: 18; 2024-01-12: 18
| Miscelleneous (5% of $1000) | 15 |  | 0.25 | 0.25 | 0.25 | 0.25 |  |  | 0.33 | 0.58 | 1.08 | 1.25 | 0.75 |  |  | 0.75 | 0.75 | 0.5 | 0.5 | 0.75 |  |  | 0.75 | 0.25 | 1.5 | 1.5 | 0.75 |  |  | 0.75 | 0.5 | 0.5 | 0.25
1.1.3.2 | Install base frames | 1 | 2024-01-02: 0.25; 2024-01-03: 0.25; 2024-01-04: 0.25; 2024-01-05: 0.25
1.1.4.1 | Install wire mesh and floor insulations | 1 | 2024-01-08: 0.33; 2024-01-09: 0.33; 2024-01-10: 0.33
1.1.4.2 | Install floor board | 1 | 2024-01-11: 0.5; 2024-01-12: 0.5
1.1.5.1 | Assemble and install wall frame | 1 | 2024-01-10: 0.5; 2024-01-11: 0.5
1.1.5.2 | Install wall boards | 1 | 2024-01-15: 0.5; 2024-01-16: 0.5
1.1.6.1 | Measure and cut rafter to size | 1 | 2024-01-09: 0.25; 2024-01-10: 0.25; 2024-01-11: 0.25; 2024-01-12: 0.25
1.1.6.2 | Install rafter | 1 | 2024-01-15: 0.25; 2024-01-16: 0.25; 2024-01-17: 0.25; 2024-01-18: 0.25
1.1.6.3 | Install roof boards | 1 | 2024-01-19: 0.5; 2024-01-22: 0.5
1.1.6.4 | Install roof insualtion (asphalt felt) | 1 | 2024-01-17: 0.25; 2024-01-18: 0.25; 2024-01-19: 0.25; 2024-01-22: 0.25
1.1.8.1 | Install wooden seethrough door | 1 | bar: 2024-01-24
1.1.9.1 | Install rockwool | 1 | bar: 2024-01-25
1.1.9.2 | Instal T&G wood panel | 1 | 2024-01-23: 0.25; 2024-01-24: 0.25; 2024-01-25: 0.25; 2024-01-26: 0.25
1.1.9.3 | Install climbing wall | 1 | 2024-01-24: 0.25; 2024-01-25: 0.25; 2024-01-26: 0.25; 2024-01-29: 0.25
1.1.9.4 | Install wood stove and chimney | 1 | 2024-01-26: 0.25; 2024-01-29: 0.25; 2024-01-30: 0.25; 2024-01-31: 0.25
1.1.10.1 | Install cedar shakes | 1 | 2024-01-29: 0.25; 2024-01-30: 0.25; 2024-01-31: 0.25; 2024-02-01: 0.25

## Gantt Chart
WBS Code | Task Name | Duration | Start | Finish
1.1.1.1 | Gather requirement and plan | 1 | 2024-01-01 | 2024-01-01
1.1.2.1 | Generate budget | 2 | 2024-01-02 | 2024-01-03
1.1.2.2 | Purchase material | 5 | 2024-01-04 | 2024-01-08
1.1.3.1 | Position concrete base | 1 | 2024-01-04 | 2024-01-04
1.1.3.2 | Install base frames | 4 | 2024-01-02 | 2024-01-05
1.1.4.1 | Install wire mesh and floor insulations | 3 | 2024-01-08 | 2024-01-10
1.1.4.2 | Install floor board | 2 | 2024-01-11 | 2024-01-12
1.1.5.1 | Assemble and install wall frame | 2 | 2024-01-10 | 2024-01-11
1.1.5.2 | Install wall boards | 2 | 2024-01-15 | 2024-01-16
1.1.6.1 | Measure and cut rafter to size | 4 | 2024-01-09 | 2024-01-12
1.1.6.2 | Install rafter | 4 | 2024-01-15 | 2024-01-18
1.1.6.3 | Install roof boards | 4 | 2024-01-19 | 2024-01-22
1.1.6.4 | Install roof insualtion (asphalt felt) | 6 | 2024-01-17 | 2024-01-22
1.1.6.5 | Install aluminium roofing sheet | 6 | 2024-01-17 | 2024-01-22
1.1.7.1 | Install fabricated aluminium windown | 1 | 2024-01-23 | 2024-01-23
1.1.8.1 | Install wooden seethrough door | 1 | 2024-01-24 | 2024-01-24
1.1.9.1 | Install rockwool | 1 | 2024-01-25 | 2024-01-25
1.1.9.2 | Instal T&G wood panel | 4 | 2024-01-23 | 2024-01-26
1.1.9.3 | Install climbing wall | 6 | 2024-01-24 | 2024-01-29
1.1.9.4 | Install wood stove and chimney | 6 | 2024-01-26 | 2024-01-31
1.1.10.1 | Install cedar shakes | 4 | 2024-01-29 | 2024-02-01
1.1.11.1 | Inspection and Sign off | 1 | 2024-02-02 | 2024-02-02

## EVM Worksheet
WBS | Task Name | WBS Element BAC | Planned Value - PV (BCWS) | % Complete | EV | BAC Duration | SV $ | SV as % of PV | SPI | EACdur (Just for the entire project) assuming performance doesn't change | ETCdur (Just for the entire project) | VACdur (Just for the entire project)
1 | A Frame Cqabin Project | 22500 | 9412.2 | 59% | 13275 | 25 | 3862.8 | 0.4104 | 1.4104 | 17.7254 | 5.2254 | 7.2746
1.1 | Construction of frame cabin | 22500 | 9412.2 | 59% | 13275 | 25 | 3862.8 | 0.4104 | 1.4104 | 17.7254 | 5.2254 | 7.2746
1.1.1 | Project initiatin | 330 | 330 | 100% | 330 | 1 | 0 | 0 | 1 | 1 | 0.5 | 0
1.1.1.1 | Gather requirement and plan | 330 | 330 | 100% | 330 | 1 | 0 | 0 | 1 | 1 | 0.5 | 0
1.1.2 | Procurement | 800 | 800 | 100% | 800 | 5 | 0 | 0 | 1 | 5 | 2.5 | 0
1.1.2.1 | Generate budget | 500 | 500 | 100% | 500 | 2 | 0 | 0 | 1 | 2 | 1 | 0
1.1.2.2 | Purchase material | 300 | 300 | 100% | 300 | 3 | 0 | 0 | 1 | 3 | 1.5 | 0
1.1.3 | Foundation work | 3066.07 | 3066.07 | 100% | 3066.07 | 4 | 0 | 0 | 1 | 4 | 2 | 0
1.1.3.1 | Position concrete base | 1950 | 1950 | 100% | 1950 | 1 | 0 | 0 | 1 | 1 | 0.5 | 0
1.1.3.2 | Install base frames | 1116.07 | 1116.07 | 100% | 1116.07 | 4 | 0 | 0 | 1 | 4 | 2 | 0
1.1.4 | Wire mesh | 1345.6 | 1345.6 | 75% | 1009.2 | 5 | -336.4 | -0.25 | 0.75 | 6.6667 | 4.1667 | -1.6667
1.1.4.1 | Install wire mesh and floor insulations | 701.6 | 701.6 | 75% | 526.2 | 3 | -175.4 | -0.25 | 0.75 | 4 | 2.5 | -1
1.1.4.2 | Install floor board | 644 | 644 | 75% | 483 | 2 | -161 | -0.25 | 0.75 | 2.6667 | 1.6667 | -0.66667
1.1.5 | Wall | 1695 | 1695 | 94% | 1593.3 | 5 | -101.7 | -0.06 | 0.94 | 5.3191 | 2.8191 | -0.31915
1.1.5.1 | Assemble and install wall frame | 515 | 515 | 75% | 386.25 | 2 | -128.75 | -0.25 | 0.75 | 2.6667 | 1.6667 | -0.66667
1.1.5.2 | Install wall boards | 1180 | 1180 | 100% | 1180 | 2 | 0 | 0 | 1 | 2 | 1 | 0
1.1.6 | Rafter and Roofing | 6447.6 | 2175.53 | 83% | 5351.508 | 10 | 3175.978 | 1.4599 | 2.4599 | 4.0653 | -0.93473 | 5.9347
1.1.6.1 | Measure and cut rafter to size | 650 | 650 | 100% | 650 | 4 | 0 | 0 | 1 | 4 | 2 | 0
1.1.6.2 | Install rafter | 755 | 566.25 | 100% | 755 | 4 | 188.75 | 0.33333 | 1.3333 | 3 | 1 | 1
1.1.6.3 | Install roof boards | 1205.5 | 0 | 0% | 0 | 2 | 0 | N/A | N/A | N/A | N/A | N/A
1.1.6.4 | Install roof insualtion (asphalt felt) | 2602.1 | 650.53 | 100% | 2602.1 | 4 | 1951.57 | 3 | 4 | 1 | -0.99999 | 3
1.1.6.5 | Install aluminium roofing sheet | 1235 | 308.75 | 50% | 617.5 | 4 | 308.75 | 1 | 2 | 2 | 0 | 2
1.1.7 | Window | 2100 | 0 | 0% | 0 | 1 | 0 | N/A | N/A | N/A | N/A | N/A
1.1.7.1 | Install fabricated aluminium windown | 2100 | 0 | 0% | 0 | 1 | 0 | N/A | N/A | N/A | N/A | N/A
1.1.8 | Door | 700 | 0 | 0% | 0 | 1 | 0 | N/A | N/A | N/A | N/A | N/A
1.1.8.1 | Install wooden seethrough door | 700 | 0 | 0% | 0 | 1 | 0 | N/A | N/A | N/A | N/A | N/A
1.1.9 | Interior | 4805.43 | 0 | 0% | 0 | 7 | 0 | N/A | N/A | N/A | N/A | N/A
1.1.9.1 | Install rockwool | 861.8 | 0 | 0% | 0 | 1 | 0 | N/A | N/A | N/A | N/A | N/A
1.1.9.2 | Instal T&G wood panel | 793.63 | 0 | 0% | 0 | 4 | 0 | N/A | N/A | N/A | N/A | N/A
1.1.9.3 | Install climbing wall | 1500 | 0 | 0% | 0 | 4 | 0 | N/A | N/A | N/A | N/A | N/A
1.1.9.4 | Install wood stove and chimney | 1650 | 0 | 0% | 0 | 4 | 0 | N/A | N/A | N/A | N/A | N/A
1.1.10 | Exterior | 880.3 | 0 | 0% | 0 | 4 | 0 | N/A | N/A | N/A | N/A | N/A
1.1.10.1 | Install cedar shakes | 880.3 | 0 | 0% | 0 | 4 | 0 | N/A | N/A | N/A | N/A | N/A
1.1.11 | Handover | 330 | 0 | 0% | 0 | 1 | 0 | N/A | N/A | N/A | N/A | N/A
1.1.11.1 | Inspection and Sign off | 330 | 0 | 0% | 0 | 1 | 0 | N/A | N/A | N/A | N/A | N/A