## Sheet1
Team Participation Minutes
This file is to be attached and sent with all group work assignments or the assignment will not be marked
For each team meeting, please copy the Meeting information.
Meeting: (For each team meeting, please copy the Meeting information.)
Date | 2024-02-04 |  | Not present |  | Date | 2024-06-04
Time | 20:00 |  |  |  | Time | 16:00
Location | B Building |  |  |  | Location | D Building
Attendees | Maitri Ramani |  |  |  | Attendees | Maitri Ramani
| S M Rakibul Basher |  |  |  |  | S M Rakibul Basher
| Gihan Shamike Liyanage |  |  |  |  | Gihan Shamike Liyanage
| Sushan Maharjan |  |  |  |  | Sushan Maharjan
Tasks: (For each team meeting, please copy the Meeting information.)
| TASK | PERSON | DUE DATE | COMPLETED & ISSUES
| Refer and understanding assignment | All | 2024-05-04 | Completed
| Create effective users stories | Maitri Ramani and Sushan Maharjan | 2024-05-04 | Completed
| Estimate project tasks | Gihan Shamike Liyanage and S M Rakibul Basher | 2024-05-04 | Completed
| Create Newsletter Product Backlog | Maitri Ramani | 2024-05-04 | Completed
| Create Newsletter Sprint Backlog | Sushan Maharjan | 2024-05-04 | Completed
| Create Word Document | S M Rakibul Basher | 2024-05-04 | Completed
| Create Newsletter Team Task Board PPT | Gihan Shamike Liyanage | 2024-05-04 | Completed
| File Formatting | All | 2024-06-04 | Completed
| Reference Check, Grammar Check, Proof Reading | All | 2024-06-04 | Completed
Note on D10: Date of meeting
Note on G10: List names of members of the team that do not attend meeting. If a member does not attend they still are given a task(s) to complete
Note on K10: Date of meeting
Note on D11: Time of meeting and duration (i.e. 1:00 pm to 1:30 pm)
Note on K11: Time of meeting and duration (i.e. 1:00 pm to 1:30 pm)
Note on D12: Physical location of meeting (E.g. D cafeteria)
Note on K12: Physical location of meeting (E.g. D cafeteria)
Note on D13: List all of the attendee that are present at the meeting. If some members are not present this is noted. Those not present are still assigned tasks for the assignment
Note on K13: List all of the attendee that are present at the meeting. If some members are not present this is noted. Those not present are still assigned tasks for the assignment
Note on D21: Describe the task to be completed.
Note on E21: Name of the person accountable for the task to be completed.
Note on F21: Date and time when the the task is to be completed.
Note on G21: This is the accountability of the facilitator. If the task is not compled by the due date the task is considered not compleded