## Product Backlog
Product Backlog Items (PBI's)
|  | Project Name: | Newsletter Project
|  | User Story or Feature (Functionality) |  |  | Estimate in Points | Acceptance Criteria | Rationale for Priortization | Notes | Sprint #
|  | As a | I want to | So that I can
| 1 | CEO | I want to write a welcome note for the inaugural newsletter | so that customers and employees feel welcomed and informed about CO's commitment. | 5 | - Note length should range from 125 to 200 words. - An image of the CEO should be included. | This creates a personal connection with the readers and sets the tone for the newsletter. | The welcome letter need to convey the CEO's excitement for the newsletter's debut and underscore CO's dedication to offering clients and staff insightful information. | 1
| 2 | Marketing team member | I want to include a customer testimonial in the newsletter | so that readers can see the value CO provides. | 3 | - A testimonial need to consist of 100–250 words. | Giving readers social proof can boost their sense of credibility and trust. | Choose an endorsement that demonstrates a satisfied customer's experience with CO's goods or services, highlighting the business's capacity to provide innovative and practical solutions. | 1
| 3 | Researcher | I want to write a feature story on the ergonomic positioning of PC monitors | so that readers can understand the optimal setup. | 8 | - Incorporate studies on the ideal height and separation. Offer a variety of choices to get the best configuration. - Add a sketch showing how the setup is done. | This knowledge is relevant to a broad audience because ergonomics is a major concern for many office workers. | Make sure the information answers frequently asked issues and concerns about ergonomics by conducting in-depth research to provide suggestions on monitor height and distance that are supported by evidence. | 2
| 4 | Content Writer | I want to create a "Question of the Week" section about highly adjustable home office products | so that readers can engage with the content. | 3 | An article should have a word count of 100–300. Provide a single image. Saying "yes you can adjust that" should be included. | Providing interactive content to readers can boost interest and retention. | Highlight the advantages of highly adaptable home office supplies and entice readers to look into the possibilities of individualized options. | 4
| 5 | Marketing team member | I want to offer a special promotion for the inaugural edition | so that readers are incentivized to engage with the newsletter. | 5 | - Offers should not exceed one hundred words. Incorporate a visual aid to pique attention. - Indicate how readers can take advantage of the deal. | Providing a promotion can boost participation and reader engagement. | Provide a compelling offer to encourage reader interaction and engagement while highlighting future email editions. | 4
| 6 | Marketing team member | I want to create a footer for the newsletter with key information and links | so that readers have access to important resources. | 2 | - Add three brief images of top products. - Add Twitter and "Facebook like" buttons. - Include CO's phone number, address, and unsubscribe link. | Links and pertinent information are provided in the footer to help readers get in touch with CO. | Create a visually beautiful footer that makes it easy for readers to navigate and contains important contact information, social networking buttons, and an unsubscribe option. | 6
| 7 | UI/UX Designer | I want to design a banner for the newsletter with the company logo and name | so that the newsletter has a professional and branded appearance. | 3 | - The banner should span the newsletter's width. - Put the name of the newsletter on the right and the corporate logo on the left. | A visually pleasing banner can improve professionalism and brand recognition. | Make an eye-catching banner that combines the name of the newsletter and the company emblem to draw readers in and strengthen brand identification. | 5
| 8 | UI/UX Designer | I want to design a newsletter signup box | so that new subscribers can easily join the mailing list. | 2 | - The first name, last name, and email address should be required in the signup form. | Expanding the list of subscribers enables subsequent newsletters to reach a wider audience and encourage more interaction. | Provide an intuitive sign-up form that makes subscribing easy and motivates readers to subscribe to the newsletter. | 2
| 9 | UI/UX Designer | I want to design a feedback/commentary text box | so that readers can provide input and engage with the content. | 2 | A title for the text field is necessary. Put a submit button there. | Reader satisfaction increases and involvement is encouraged when feedback is provided. | In order to promote community involvement and interaction, implement a feedback system that makes it simple for readers to express their ideas and queries. | 3
| 10 | Marketing team members | I want to include a link to a survey in the newsletter | so that readers can provide feedback on the content. | 2 | - The survey link has to be easy to see. - Give the survey a title and an explanation for your completion. | The newsletter's upcoming issues are made better by using questionnaires to collect input. | Include an obvious and persuasive call to action encouraging readers to complete a survey, stressing the significance of their input in determining the direction of next newsletter issues. | 1
| 11 | Content Writer | I want to write a 100-word product review of the new Flexi-light | so that readers are informed about its features. | 4 | A 100-word review is appropriate. | Giving readers product information enables them to make well-informed purchasing decisions. | Captivate readers to learn more about the features and functionality of the Flexi-light by writing a succinct yet useful review. | 7
| 12 | Content Writer | I want to provide a Tech Tip on "how to use Comments in PowerPoint" | so that readers can improve their productivity. | 4 | - The tip ought to be between 100 and 25 words. | Including useful advice in the email improves reader pleasure and adds value. | Help readers become more knowledgeable and productive by offering helpful advice on how to use comments in PowerPoint presentations. | 9
| 13 | Marketing team members | I want to include a blurb about the opening of the Ottawa store | so that readers are informed about CO's expansion. | 6 | - A 50-word blurb is recommended. - Provide a basic map and the address. | A company's growth and expansion can be seen in the news it shares regarding new store openings. | In order to entice readers to visit the new location, emphasize the significance of the Ottawa store opening and include pertinent location information. | 8
| 14 | Editorial Writer | I want to write an editorial on the need for specialized and customized office solutions | so that readers understand the importance of tailored solutions. | 5 | A 150–250 word editorial is the ideal length. | Insights and analysis on market trends provide the newsletter more value and increase reader engagement. | Stressing CO's experience and creativity in satisfying client needs, clearly state the importance of specialized and tailored office solutions in today's varied work environments. | 10
| 15 | Customer | I want to read about innovative office furniture solutions in the newsletter | so that I can stay informed about the latest trends. | 5 | - Provide details regarding creative alternatives for workplace furnishings. | Showcasing creative solutions keeps readers interested and demonstrates CO's experience. | Highlight distinctive features and designs in CO's most recent office furniture inventions to motivate readers. | 10
| 16 | Sales Representative | I want to include a section highlighting recent customer projects | so that readers can see real-world applications of CO's products. | 6 | - Add images and descriptions of current client projects. | Presenting accomplished projects enhances credibility and showcases CO's talents. | Highlight accomplishments from satisfied clients to show off CO's experience and capacity for providing specialized solutions. | 2
| 17 | Graphic Designer | I want to design visually appealing graphics and layouts for the newsletter | so that the content is engaging and easy to read. | 4 | - Layouts and graphics should improve readability and aesthetic appeal. | Effective visuals enhance the reading and comprehension experience for the reader. | Provide captivating images and layouts that improve reading and go well with the newsletter's content. | 3
| 18 | Customer | I want to see information about upcoming sales and promotions in the newsletter | so that I can take advantage of special offers. | 3 | - Provide information on forthcoming specials and promotions. | Informing readers ahead of time about sales promotes involvement and interaction. | To encourage reader engagement and increase sales, publicize impending specials and promotions. | 4
| 19 | Social Media Manager | I want to include social media buttons in the footer of the newsletter | so that readers can easily share content on their social networks. | 1 | Put Twitter and Facebook buttons on it. | Encouraging social media sharing increases brand visibility and the newsletter's reach. | To make it simple for readers to share newsletter content across many platforms, provide social media icons in the footer. | 3
| 20 | Content Writer | I want to include a section on office productivity tips | so that readers can optimize their workspaces. | 7 | - Offer helpful advice for raising productivity levels in the workplace. | By providing insightful advice, you can improve readers' productivity and work atmosphere. | Address the frequent issues that readers encounter and offer helpful advice for increasing office efficiency. | 6
| 21 | Marketing team member | I want to feature testimonials from satisfied customers | so that readers are inspired to explore CO's products. | 6 | - Accompany customer quotes with succinct testimonies. | Positive comments are shared to strengthen CO's trust and reputation. | To encourage customer involvement and retention, highlight your customer loyalty programs and awards. | 1
| 22 | Customer | I want to see examples of CO's customizable office furniture options | so that I can envision how they could fit my needs. | 4 | - Provide descriptions and pictures of the customisable furniture alternatives. | Customers are better equipped to make educated purchasing selections when adjustable options are visualized. | Provide advice on how to set up home offices efficiently so that remote workers may be catered to. | 7
| 23 | Marketing team member | I want to include a section highlighting CO's commitment to sustainability, | so that readers are aware of the company's values. | 5 | - Describe the activities and sustainable practices of CO. | Proving your dedication to sustainability appeals to readers who care about the environment. | In line with the environmental ideals of the readers, highlight CO's dedication to sustainability and eco-friendly operations. | 5
| 24 | Customer Service Representative | I want to include a customer satisfaction survey link in the newsletter | so that readers can provide feedback on their experiences. | 2 | The link to the survey should be simple to find. Please provide a brief description of the purpose of the survey. | Customer relationships are strengthened and areas for development are identified through the use of surveys to gather feedback. | In addition to stressing the value of feedback in enhancing client experiences, make sure the survey link is clearly visible for simple access. | 10
| 25 | Content Writer | I want to write a spotlight feature on a CO employee | so that readers can learn more about the people behind the company. | 8 | - Provide a CO employee's function and background in their profile. | By showcasing staff members, the organization humanizes itself and helps readers relate to it. | Give readers a quick overview of the featured employee's background and job description in order to highlight CO's brilliant team members and establish a personal connection. | 9
| 26 | Marketing team member | I want to include a section on upcoming events and trade shows where CO will be exhibiting | so that readers can attend and learn more about the company's offerings. | 8 | - Provide information about forthcoming trade exhibitions and activities. | Promoting a company's attendance at events fosters communication and engagement with readers. | To entice readers to visit and interact with the brand, highlight CO's involvement in forthcoming events. | 6
| 27 | Sales Representative | I want to include customer success stories in the newsletter | so that readers can see the positive impact of CO's products. | 10 | - Provide examples of how CO's solutions were able to resolve particular client issues. | By sharing success stories, you gain readers' trust and show them the real-world advantages of CO's solutions. | To establish credibility and trust with prospective customers, provide concrete instances of how CO's products have benefited clients. | 5
| 28 | Content Writer | I want to include a section on industry trends and insights | so that readers stay informed about developments in the office furniture industry. | 10 | - Offer analysis and insights on changes and trends in the sector. | Providing insightful information boosts reader engagement and establishes CO as a thought leader in the field. | To keep readers updated and establish CO as a thought leader in the field, provide insightful analysis and insights on industry trends. | 4
| 29 | Marketing team member | I want to include a spotlight on CO's community involvement and charitable initiatives | so that readers are aware of the company's philanthropic efforts. | 9 | Emphasize CO's philanthropic donations and involvement in local events. | A company's reputation is improved and readership is encouraged when it demonstrates social responsibility. | Emphasize CO's charitable endeavours to uphold the company's brand and exhibit corporate social responsibility. | 4
| 30 | Customer | I want to see a section on FAQs about CO's products and services | so that I can find answers to common questions. | 6 | - Provide succinct, understandable responses to often asked questions. | Addressing consumer questions and enhancing satisfaction are achieved by making information easily accessible. | Answer frequently asked questions in a clear and succinct manner to increase customer satisfaction and decrease support requests. | 1
| 31 | Content Writer | I want to include a section on home office organization tips | so that readers can optimize their work-from-home setups. | 1 | Offer helpful advice on how to efficiently arrange home offices. | Reader engagement and happiness are increased when helpful advice is provided. | Give readers helpful tips on how to set up their home offices so they can establish comfortable and productive workspaces. | 2
| 32 | Marketing team member | I want to include a customer spotlight featuring a notable client | so that readers can see examples of CO's high-profile partnerships. | 3 | - Use a testimonial and a brief profile to highlight a notable client. | Putting prominent clients on display improves CO's standing and trustworthiness. | Highlight illustrative clientele to showcase CO's legitimacy and fruitful collaborations. | 10
| 33 | Graphic Designer | I want to design eye-catching visuals for social media sharing | so that readers are encouraged to share newsletter content on their social networks. | 4 | - Make eye-catching visuals that are tailored for social media sites. | CO's reach can be increased by sharing content more often, which is facilitated by visually captivating content. | Create aesthetically pleasing visuals that will motivate readers to post content from your email on social media. | 5
| 34 | Content Writer | I want to include a section on ergonomic chair selection tips | so that readers can choose the right chair for their needs. | 3 | - Offer advice on the characteristics and factors of ergonomic chairs. | In order to establish cozy and healthful work spaces, readers should address ergonomic considerations. | To encourage reader comfort and well-being at work, offer advice on selecting ergonomic chairs. | 7
| 35 | Marketing team member | I want to include a section on upcoming product launches and innovations | so that readers are excited about CO's future offerings. | 8 | Emphasize forthcoming products along with their launch dates and brief descriptions. | Encourage reader involvement and interest by building anticipation for new offerings. | Give consumers a sneak glimpse at new products and their launch dates to create anticipation. | 2
| 36 | Customer Service Representative | I want to include a troubleshooting guide for common furniture assembly issues | so that readers can resolve problems independently. | 8 | - Offer detailed guidance for resolving typical assembly problems. | Providing workable solutions lowers support requests and increases customer satisfaction. | To enable readers to handle problems on their own, provide thorough instructions for fixing typical assembly problems. | 1
| 37 | Content Writer | I want to include a section on office decor ideas and inspiration | so that readers can personalize their workspaces. | 10 | - Display original ideas for office décor together with related pictures. | Providing readers with décor inspiration improves both reader engagement and their work environments. | Encourage readers to add personality and a positive vibe to their workspaces by providing them with unique office décor ideas. | 8
| 38 | Marketing team member | I want to include a section highlighting CO's awards and accolades | so that readers are aware of the company's achievements. | 9 | - Highlight CO's most recent honours and recognitions. | CO's credibility and reputation are improved by showcasing industry recognition. | Highlight CO's accomplishments to improve the reputation and credibility of the brand. | 2
| 39 | Sales Representative | I want to include customer reviews and ratings for CO's products | so that readers can see feedback from other customers. | 7 | - Provide ratings and reviews from customers for the highlighted products. | By presenting reviews as social proof, CO's products gain credibility and reliance. | To increase confidence in CO's products, emphasize positive customer reviews. | 10
| 40 | Graphic Designer | I want to design a visually appealing infographic summarizing key newsletter highlights | so that readers can easily digest the content. | 4 | - Compile the newsletter's important data and features into an infographic. | An infographic that summarizes content helps people read it more easily and remember it. | For ease of consumption and retention, compile the main points of the newsletter into an infographic. | 3
| 41 | Customer | I want to see a section on industry news and updates relevant to office furniture | so that I can stay informed about industry developments. | 2 | - Provide articles or summaries of news stories about pertinent industries. | Giving readers with industry information highlights CO's proficiency and keeps them updated. | To showcase CO's knowledge and inform readers, provide industry news and updates. | 4
| 42 | Marketing team member | I want to include a section on customer loyalty rewards and programs | so that readers are incentivized to continue engaging with CO. | 1 | Emphasize the perks and customer loyalty awards that are accessible to subscribers. | Stronger ties and more recurring business result from rewarding customer loyalty. | To encourage ongoing brand engagement, advertise customer loyalty programs and prizes. | 9
| 43 | Content Writer | I want to include a section on ergonomic accessories for home offices | so that readers can enhance their work setups. | 4 | - Offer advice and details regarding items that promote ergonomics. | Providing additional items increases reader happiness and the newsletter's worth. | In order to improve the comfort and efficiency of readers, make suggestions for ergonomic gear. | 3
| 44 | Marketing team member | I want to include a section on tips for remote team collaboration and communication | so that readers can improve teamwork in virtual environments. | 3 | - Offer helpful guidance and resources for remote cooperation. | Encouraging remote work habits takes into account reader demands and current developments. | To meet reader needs and take into account contemporary workplace trends, offer helpful advice on remote teamwork. | 2
| 45 | Customer Service Representative | I want to include a section addressing common customer inquiries and concerns | so that readers can find answers to their questions. | 2 | - Provide answers and FAQs for often asked questions by customers. | Providing useful information lowers support requests and customer annoyance. | Reduce support requests and increase customer happiness by offering insightful responses to frequently asked issues. | 3

## DoD, Velocity, # of Sprints
Product Backlog
| Newsletter Project | Velocity Calculations |  |  | Calculations for the # of Sprints Required for the Product Backlog
| Defintions of Done (DoD) | Sprint 1 Competed |  | 21
| In Agile and Scrum processes, the phrase "Definition of Done" (DoD) refers to a set of requirements that a product increment must satisfy in order for the team to declare it finished and available for clients. When a product increment is prepared for release, the team members all agree on it. | Sprint 2 Completed |  | 8 | Sprint Hours Remaining | 182
|  | Sprint 3 Completed |  | 6 | Calculated Velocity | 11.6667
|  |  | Total | 35
[5 empty] | Estimated for remaining | 15.6
| Deliverable consistency and quality are guaranteed by the DoD. Usually, teams use the DoD to assess a product increment's quality at the conclusion of a sprint. It is significant to remember that the Definition of Done is not created by a single person. Rather, it is decided upon by the whole project team, which consists of product owners, developers, testers, and other stakeholders. |  | Velocity | 11.6667
The project is estimated to be complete in 15.6 weeks.
Here are some examples of items you may find in a Definition of Done:
All testing completed
No known defects
Code review completed and passed
Meets compliance standards
Meets general security requirements
Once all of the items in the Definition of Done are checked off and complete, this Increment is considered Done

## Completed Product Backlog Items
Completed Product Backlog Items (completed PBI's)
|  | Project Name: | Newsletter Project
|  | User Story or Feature (Functionality) |  |  | Estimate in Points | Acceptance Criteria | Rationale for Priortization | Notes | Sprint #
|  | As a | I want to | So that I can
| 1 | CEO | I want to write a welcome note for the inaugural newsletter | so that customers and employees feel welcomed and informed about CO's commitment. | 5 | - Note length should range from 125 to 200 words. - An image of the CEO should be included. | This creates a personal connection with the readers and sets the tone for the newsletter. | The welcome letter need to convey the CEO's excitement for the newsletter's debut and underscore CO's dedication to offering clients and staff insightful information. | 1
| 2 | Researcher | I want to write a feature story on the ergonomic positioning of PC monitors | so that readers can understand the optimal setup. | 8 | - Incorporate studies on the ideal height and separation. Offer a variety of choices to get the best configuration. - Add a sketch showing how the setup is done. | This knowledge is relevant to a broad audience because ergonomics is a major concern for many office workers. | Make sure the information answers frequently asked issues and concerns about ergonomics by conducting in-depth research to provide suggestions on monitor height and distance that are supported by evidence. | 2
| 3 | UI/UX Designer | I want to design a feedback/commentary text box | so that readers can provide input and engage with the content. | 2 | A title for the text field is necessary. Put a submit button there. | Reader satisfaction increases and involvement is encouraged when feedback is provided. | In order to promote community involvement and interaction, implement a feedback system that makes it simple for readers to express their ideas and queries. | 3
| 4 | Marketing team members | I want to include a link to a survey in the newsletter | so that readers can provide feedback on the content. | 2 | - The survey link has to be easy to see. - Give the survey a title and an explanation for your completion. | The newsletter's upcoming issues are made better by using questionnaires to collect input. | Include an obvious and persuasive call to action encouraging readers to complete a survey, stressing the significance of their input in determining the direction of next newsletter issues. | 1
| 5 | Customer | I want to see a section on FAQs about CO's products and services | so that I can find answers to common questions. | 6 | - Provide succinct, understandable responses to often asked questions. | Addressing consumer questions and enhancing satisfaction are achieved by making information easily accessible. | Answer frequently asked questions in a clear and succinct manner to increase customer satisfaction and decrease support requests. | 1
| 6 | Customer Service Representative | I want to include a troubleshooting guide for common furniture assembly issues | so that readers can resolve problems independently. | 8 | - Offer detailed guidance for resolving typical assembly problems. | Providing workable solutions lowers support requests and increases customer satisfaction. | To enable readers to handle problems on their own, provide thorough instructions for fixing typical assembly problems. | 1
| 7 | Graphic Designer | I want to design a visually appealing infographic summarizing key newsletter highlights | so that readers can easily digest the content. | 4 | - Compile the newsletter's important data and features into an infographic. | An infographic that summarizes content helps people read it more easily and remember it. | For ease of consumption and retention, compile the main points of the newsletter into an infographic. | 3