## Sprint 1 Backlog
Sprint 1 Backlog
|  | Project Name: |  | Newsletter Project
| Story | User Story or Feature Tasks | [7 empty] | Total Estimate in Ideal Hours | Notes
|  | First Task | Est in Ideal Hours | Second Task | Est in Ideal Hours | Third Task | Est in Ideal Hours | Fourth Task | Est in Ideal Hours
| As a CEO I want to write a welcome note for the inaugural newsletter so that customers and employees feel welcomed and informed about CO's commitment. | Write a welcome note | 4 | Proofread | 3 | Have it reviewed | 2 |  |  | 9
| As a Marketing team member I want to include a customer testimonial in the newsletter so that readers can see the value CO provides. | Gather Testimonials | 3 | Filter testimonials | 4 | Pass it to design team | 1 |  |  | 8
| As a Marketing team members I want to include a link to a survey in the newsletter so that readers can provide feedback on the content. | Create Survey | 2 | Review and proofread | 2 | Have it approved and signed off | 1 |  |  | 5
| As a Marketing team member I want to feature testimonials from satisfied customers so that readers are inspired to explore CO's products. | Research and Gather Testimonials | 3 | Create Compelling Visual Content: | 5 | Implement Testimonial Section on Website | 2 | Promote Testimonials Across Marketing Channels: | 1 | 11
| As a Customer I want to see a section on FAQs about CO's products and services so that I can find answers to common questions. | Identify Common Customer Queries: | 3 | Develop Informative FAQ Content: | 1 | Regularly Update and Expand FAQ Section: | 2 |  |  | 6
| As a Customer Service Representative I want to include a troubleshooting guide for common furniture assembly issues so that readers can resolve problems independently. | Identify Common Furniture Assembly Issues: | 2 | Develop Comprehensive Troubleshooting Guide | 2 | Integrate Troubleshooting Guide into Customer Support Resources | 5 | Empower Customers with Self-Service Option | 2 | 11
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Sprint 1 Capacity and Burndown
Sprint 1 Backlog
Newsletter Project
| Sprint 1 Capacity Calculations in Ideal Hours | [6 empty] | Burndown Chart, Plan Line, not Actuals Line
| Task /Ideal Hours | Start (Day 0) - Ideal hours from Sprint Backlog | Ideal Hours Worked
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| Task 1 | 9 | 5 | 3 | 1 | 2
| Task 2 | 8 | 2 | 1 | 1
| Task 3 | 5 |  | 3 | 2
| Task 4 | 11 |  | 3 | 2 |  | 7
| Task 5 | 6
| Task 6 | 11
| Totals | 50 | 7 | 10 | 6 | 2 | 7
| Planned Burndown | 50 | 40 | 30 | 20 | 10 | 0
| Actual Burndown (Effort Remaining) | 50 | 43 | 33 | 27 | 25 | 18

## Sprint 2 Backlog
Sprint 2 Backlog
|  | Project Name: |  | Newsletter Project
| Story | User Story or Feature Tasks | [7 empty] | Total Estimate in Ideal Hours | Notes
|  | First Task | Est in Ideal Hours | Second Task | Est in Ideal Hours | Third Task | Est in Ideal Hours | Fourth Task | Est in Ideal Hours
| As a Researcher I want to write a feature story on the ergonomic positioning of PC monitors so that readers can understand the optimal setup. | Optimal Setup Explained | 2 | Article position locked | 1 |  |  |  |  | 3
| As a UI/UX Designer I want to design a newsletter signup box so that new subscribers can easily join the mailing list. | Designing a User-Friendly Newsletter Signup Box | 4 | Simplified Signup Process | 2 | Seamless Subscription Experience | 2 | Easy Access to Newsletter Sign-up | 2 | 10
| As a Sales Representative I want to include a section highlighting recent customer projects so that readers can see real-world applications of CO's products. | Highlighting Recent Customer Projects | 5 | Real-World Applications Showcase | 4 | Showcasing Customer Implementations | 1 |  |  | 10
| As a Content Writer I want to include a section on home office organization tips so that readers can optimize their work-from-home setups. | Home Office Organization Tips | 3 | Creating an Efficient Workspace | 3 | Organizational Strategies for Home Offices | 3 |  |  | 9
| As a Marketing team member I want to include a section on upcoming product launches and innovations so that readers are excited about CO's future offerings. | Sneak Peek at Future Products | 5 | Buzz Surrounding Future Launches | 5 |  |  |  |  | 10
| As a Marketing team member I want to include a section highlighting CO's awards and accolades so that readers are aware of the company's achievements. | Celebrating Company Success | 3 | Highlighting Industry Recognition | 6 |  |  |  |  | 9
| As a Marketing team member I want to include a section on tips for remote team collaboration and communication so that readers can improve teamwork in virtual environments. | Enhancing Virtual Teamwork | 2 | Optimizing Remote Communication | 3 |  |  |  |  | 5
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Sprint 2 Capacity and Burndown
Sprint 2 Backlog
Newsletter Project
| Sprint 1 Capacity Calculations in Ideal Hours | [6 empty] | Burndown Chart, Plan Line, not Actuals Line
| Task /Ideal Hours | Start (Day 0) - Ideal hours from Sprint Backlog | Ideal Hours Worked
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| Task 1 | 3 | 3
| Task 2 | 10
| Task 3 | 10
| Task 4 | 9
| Task 5 | 10
| Task 6 | 9
| Task 7 | 5
| Totals | 56 | 3 | 0 | 0 | 0 | 0
| Planned Burndown | 56 | 44.8 | 33.6 | 22.4 | 11.2 | 0
| Actual Burndown (Effort Remaining) | 56 | 53 | 53 | 53 | 53 | 53