## Project Activity R & O Matrix
Risks which the project could create | Risk |  |  | Overall Risk Priority 1, 2, or 3 | Risk assessment: severity (magnitude) of negative outcome |  |  |  | Risk assessment: probability or frequency of event happening, and extent to which it can be detected
Major Activity (any one activity could result in several alternative outcomes) | Hazard | Event | Alternative negative outcomes that could result | Priority to resolve Risk | How severe is the resulting negative outcome? Explain why. | Initial priority (1,2,3) to review, based on severity | Does the severity exceed risk tolerance? Explain why. | Revised priority (1,2,3) to review, based on risk tolerance | What is the probability or frequency of the event? Explain why. | Initial priority (1,2,3) to review, based on probability or frequency | If (or when) the event happens, can we easily see it happen? Explain why. | Revised priority (1,2,3) to review, based on visibility
Construction of Adelaide Street Underpass | Excavation and tunneling | Collapse of tunnel or excavation site | Delay in project timeline | 1 | The collapse of a tunnel or excavation site during the construction of the underpass would result in significant consequences. It could lead to injuries or fatalities among construction workers, delays in project completion, increased costs for repair and redesign, and damage to nearby infrastructure. Additionally, it could erode public trust in the project's safety and impact the reputation of the project stakeholders. | 1 | The severity of this outcome likely exceeds risk tolerance, as it poses substantial risks to human safety and project success. | 1 | The probability of a tunnel or excavation collapse depends on various factors such as soil stability, engineering controls, and construction practices. While collapses are rare, they can occur due to unforeseen geological conditions or construction errors. | 1 | Tunnel collapses typically occur suddenly and without warning, making them difficult to detect in advance. | 1
Construction of Adelaide Street Underpass |  |  | Increase in project costs due to repair or redesign | 1 |  | 1 |  | 1 |  | 1 |  | 1
Construction of Adelaide Street Underpass |  |  | Injury to construction workers | 1 |  | 1 |  | 1 |  | 1 |  | 1
Intersection Improvements at Central Avenue | Traffic congestion and diversions | Traffic accidents or collisions | Injury or fatalities to motorists, pedestrians, or cyclists | 2 | Traffic accidents or collisions resulting from congestion and diversions at Central Avenue intersections could lead to injuries, fatalities, property damage, and delays in emergency response times. These outcomes would have significant implications for public safety, project reputation, and stakeholder satisfaction. | 2 | While the severity is high, it may not exceed risk tolerance thresholds if appropriate mitigation measures are in place to minimize the likelihood and impact of accidents. | 2 | The probability of traffic accidents or collisions increases during periods of congestion and diversions. Factors such as driver behavior, road conditions, and | 2 | Traffic accidents are usually visible occurrences that can be readily observed and reported. | 2
Intersection Improvements at Central Avenue |  |  | Property damage to vehicles or surrounding structures | 2 |  | 2 |  | 2 |  | 2 |  | 2
Active Transportation Connection Development | Pedestrian and cyclist safety | Accidents or conflicts with vehicular traffic | Legal liabilities due to accidents or injuries | 1 | Pedestrian and cyclist accidents resulting from safety hazards in active transportation connections could lead to injuries, legal liabilities, project delays, and reduced public trust in the project's effectiveness. These outcomes would have significant consequences for public safety and project success. | 1 | The severity of this outcome may exceed risk tolerance, especially considering the legal and reputational risks associated with pedestrian and cyclist accidents. | 1 | The probability of pedestrian and cyclist accidents depends on factors such as infrastructure design, traffic volumes, and user behavior. High-risk areas such as intersections and shared pathways may experience more frequent accidents. | 1 | Pedestrian and cyclist accidents are typically visible events that are reported and investigated. | 1
Active Transportation Connection Development |  |  | Increase in pedestrian and cyclist injuries | 1 |  | 1 |  | 1 |  | 1 |  | 1
Road Detour Implementation | Traffic diversion and rerouting | Traffic congestion or gridlock | Increased travel time and commuting frustrations for motorists | 2 | Traffic congestion and disruptions caused by road detours could result in increased travel time, frustrations for motorists, economic losses for businesses, environmental concerns, and community dissatisfaction. These outcomes would have significant impacts on mobility, commerce, and public perception of the project. | 2 | While the severity is high, it may fall within risk tolerance thresholds if mitigation measures are in place to manage traffic flow and minimize disruptions. | 2 | The probability of traffic congestion and disruptions during road detours is high, especially during peak travel times. Increased traffic volumes, limited alternative routes, and construction activities contribute to congestion. | 2 | Traffic congestion is easily observable and experienced by motorists and pedestrians. | 2
Road Detour Implementation |  |  | Negative impact on nearby residential neighborhoods due to increased traffic volume | 2 |  | 2 |  | 2 |  | 2 |  | 2
Railway Crossing Closure for Underpass Construction | Disruption to railway operations | Rail service delays or interruptions | Impact on freight and passenger rail services, leading to delays in goods transportation and commuter travel | 1 | Disruption to railway operations due to the closure for underpass construction could lead to delays in freight and passenger services, economic losses, public frustration, regulatory penalties, and legal disputes. These outcomes would have significant ramifications for transportation, commerce, and stakeholder relationships. | 1 | The severity of this outcome likely exceeds risk tolerance thresholds, given the criticality of railway operations and the potential for significant financial and reputational losses. | 1 | The probability of railway operation disruptions depends on factors such as construction schedules, coordination with railway operators, and unforeseen technical issues. While disruptions are relatively rare, they can occur during critical project phases. | 1 | Railway disruptions are easily noticeable by passengers, railway staff, and project stakeholders. | 1
Opportunities which the project could create | Opportunity |  |  | Opportunity Priority 1, 2 or 3 | Opportunity assessment: What and how large is the Benefit of the Opportunity? |  |  |  | Opportunity assessment: probability or frequency of event happening, and extent to which it can be detected
Major Activity (any one activity could result in several alternative outcomes) | Situation | Event | Alternative benefits (positive outcomes) that could result | Priority to realize opportunity & deliver benefits | How large is the resulting positive outcome? Explain why. | Initial priority (1,2,3) to review, based on size of benefit? | Does the benefit exceed benefits of 'status quo'? Explain why. | Revised priority (1,2,3) to review, based on added benefits? | What is the probability or frequency of the event? Explain why. | Initial priority (1,2,3) to review, based on probability or frequency | If (or when) the event happens, can we easily see it happen? Explain why. | Revised priority (1,2,3) to review, based on visibility
Development of Active Transportation Connection | City planning | Implementation of new pedestrian and cyclist pathways | Reduced traffic congestion | 1 | The positive outcome of reduced traffic congestion and improved public health is significant, as it addresses key urban challenges. | 1 | The benefits of creating safe pathways exceed the status quo of relying solely on vehicle transport. | 1 | The probability of successful implementation is medium, but the benefits are substantial. | 1 | Once pathways are established, it will be easy to see the positive impact on pedestrian and cyclist movement. | 1
Development of Active Transportation Connection |  |  | Improved air quality, enhanced public health | 1 |  | 1 |  | 1 |  | 1 |  | 1
Intersection Improvements at Central Avenue | Urban development | Installation of traffic lights and pedestrian crossings | Improved traffic flow | 2 | The benefits of improved traffic flow and pedestrian safety positively impact both commuters and residents, contributing to overall urban livability. | 2 | The benefits of safer intersections and smoother traffic flow exceed the current situation. | 2 | The probability of successful implementation is high due to established urban planning processes and expertise. | 2 | Changes in traffic flow and safety measures will be readily visible after implementation, reinforcing the positive impact. | 2
Intersection Improvements at Central Avenue |  |  | Enhanced pedestrian safety, reduced accidents | 2 |  | 2 |  | 2 |  | 2 |  | 2

## External Factor R & O Matrix
Risks which could be created by factors external to the project | Risk |  |  | Overall Risk Priority 1, 2, or 3 | Risk assessment: severity (magnitude) of negative outcome |  |  |  | Risk assessment: probability or frequency of event happening, and extent to which it can be detected
Factor (based on STEEPLE analysis tool) | Hazard | Event | Alternative negative outcomes that could result | Priority to resolve Risk | How severe is the resulting negative outcome? Explain why. | Initial priority (1,2,3) to review, based on severity | Does the severity exceed risk tolerance? Explain why. | Revised priority (1,2,3) to review, based on risk tolerance | What is the probability or frequency of the event? Explain why. | Initial priority (1,2,3) to review, based on probability or frequency | If (or when) the event happens, can we easily see it happen? Explain why. | Revised priority (1,2,3) to review, based on visibility
Social # 1 Community Opposition | Resistance from local residents or community groups | Public protests, petitions, or legal challenges | Project delays due to legal proceedings or permit revocations Increased construction costs from additional mitigation measures Damage to stakeholder relationships and public perception | 1 | Community opposition can result in significant delays and increased costs due to legal challenges or permitting issues. Damage to stakeholder relations can also impact project success. | 1 | Community opposition poses severe risks to project success and should be closely monitored and addressed. | 1 | Probability of protests or legal challenges is high due to community concerns. | 1 | Events such as protests or legal challenges are typically visible and can be monitored through media coverage or legal notices. | 1
Social # 2 Public Perception | Negative media coverage or public sentiment | Media campaigns, social media backlash, or community forums | Difficulty in securing future project approvals or funding Decreased public participation and support for project initiatives Reputational damage to project sponsors and stakeholders | 2 | Negative public perception can hinder project funding and support, leading to reputational damage. | 2 | While negative public perception is concerning, it may not pose an immediate threat to project success. | 2 | Probability of negative media coverage or social media backlash depends on project visibility and public interest. | 2 | Visibility of negative public perception can be monitored through media monitoring and public sentiment analysis. | 2
Technological # 1 Construction Technology Failure | Equipment malfunction or technical glitches | Machinery breakdowns, software errors, or safety system failures | Worksite accidents leading to injuries or fatalities Project delays due to equipment repairs or replacements Increased construction costs from downtime and productivity losses | 1 | Construction technology failures can lead to worksite accidents, delays, and increased costs, posing significant risks to project timelines and budgets. | 1 | The severity of technology failures exceeds risk tolerance as they can jeopardize worker safety and project delivery. | 1 | Probability of technology failures depends on the reliability of equipment and systems. | 1 | Technology failures are typically easily detectable through equipment monitoring systems or regular inspections. | 1
Technological # 2 Data Security Breach | Cybersecurity vulnerabilities or data breaches | Unauthorized access, hacking, or data theft | Exposure of sensitive project information to competitors or hackers Legal penalties and fines for data privacy violations Loss of stakeholder trust and confidence in project management | 2 | Data breaches can lead to significant consequences such as legal penalties and loss of stakeholder trust, impacting project success. | 2 | While data breaches are serious, they may not exceed risk tolerance if adequate security measures are in place. | 2 | Probability of data breaches depends on the effectiveness of cybersecurity measures. | 2 | Data breaches are often easily detectable through security monitoring systems and can be identified through abnormal activity. | 2
Economic # 1 Funding Shortfall | Budget constraints or financial instability | Government funding cuts, donor withdrawals, or economic downturns | Project downsizing or cancellation Incomplete or substandard project deliverables Legal disputes with funding agencies or sponsors | 1 | Funding shortfalls can lead to project downsizing and delays, impacting project scope and delivery. | 1 | Funding shortfalls exceed risk tolerance as they can compromise project viability and success. | 1 | Probability of funding shortfalls depends on government budget priorities and economic conditions. | 1 | Funding shortfalls are usually visible through budget announcements or communication from funding agencies. | 1
Economic #2 Market Instability | Fluctuations in market conditions or resource availability | Supply chain disruptions, currency fluctuations, or inflation | Increased material costs and project expenditures Delayed procurement of essential project resources Impact on project timelines and delivery schedules | 2 | Market instability can lead to increased costs and delays, posing risks to project budgets and schedules. | 2 | While market instability is concerning, it may not exceed risk tolerance if mitigation measures are in place. | 2 | Probability of market instability depends on factors such as economic indicators and industry trends. | 2 | Market instability indicators are often visible through economic reports and market analyses. | 2
Environmental # 1 Ecological Damage | Potential harm to natural ecosystems or habitats | Spills, leaks, or contamination from construction activities | Ecological damage to waterways, soil, or vegetation Legal fines and penalties for environmental violations Reputational damage and public outcry against project sponsors | 1 | Ecological damage can result in significant cleanup costs and legal penalties, as well as damage to the project's reputation. | 1 | Ecological damage exceeds risk tolerance due to its potential for significant legal and reputational consequences. | 1 | Probability of ecological damage depends on project activities and environmental sensitivity. | 1 | Ecological damage is usually visible and can be detected through environmental monitoring or incident reports | 1
Environmental # 2 Natural Disasters | Unpredictable natural events or phenomena | Floods, earthquakes, hurricanes, or wildfires | Destruction of project infrastructure and assets Loss of life or injuries to project workers or nearby residents Project delays and increased costs for recovery and reconstruction | 1 | Natural disasters can cause severe damage to project infrastructure, leading to safety hazards and delays. | 1 | Natural disasters are beyond risk tolerance as they pose significant threats to project assets and timelines. | 1 | Probability of natural disasters depends on geographical location and historical weather patterns. | 1 | Natural disasters are usually easily detectable through weather forecasts and warnings. | 1
Political # 1 Regulatory Changes | Government policy shifts or legislative reforms | Introduction of new laws, regulations, or zoning restrictions | Project redesign to comply with updated regulations Delayed project approvals or permits Legal challenges and disputes over regulatory interpretations | 1 | Regulatory changes can lead to project redesign and delays, resulting in legal disputes and increased costs. | 1 | Regulatory changes often exceed risk tolerance as they can significantly impact project timelines and budgets. | 1 | Probability of regulatory changes depends on government priorities and legislative agendas. | 1 | Regulatory changes are usually visible through official announcements or legislative updates. | 1
Political # 2 Government Instability | Political unrest, leadership changes, or governance issues | Elections, regime changes, or political upheavals | Shifting project priorities or funding allocations Policy reversals impacting project feasibility or viability Increased bureaucratic hurdles and administrative delays | 2 | Government instability can lead to shifts in project priorities and policies, resulting in administrative challenges and delays. | 2 | While government instability poses risks, it may not exceed risk tolerance if contingency plans are in place. | 2 | Probability of government instability depends on political factors and historical instability. | 2 | Government instability indicators can be monitored through political news and analysis. | 2
Legal #1 Contract Disputes | Contractual disagreements or breaches | Disputes over project specifications, timelines, or payment terms | Project delays or interruptions due to legal proceedings Financial losses from legal fees and settlements Damage to stakeholder relationships and project reputation | 1 | Contract disputes can lead to project delays and legal expenses, as well as damage to stakeholder relationships. | 1 | Contract disputes exceed risk tolerance as they can disrupt project progress and relationships. | 1 | Probability of contract disputes depends on the clarity of contract terms and stakeholder alignment. | 1 | Contract disputes are usually visible through legal notifications or correspondence between parties. | 1
Legal # 2 Litigation Risk | Legal challenges or lawsuits | Claims of harm or violations brought against project stakeholders | Legal expenses and settlements impacting project finances Reputational damage and public scrutiny Project delays or modifications to address legal requirements | 1 | Litigation risks can result in significant legal expenses, reputational damage, and project delays. | 1 | Litigation risks exceed risk tolerance due to their potential for financial and reputational harm. | 1 | Probability of litigation risk depends on project activities and stakeholder relations. | 1 | Litigation risks are typically visible through legal notifications or communication from affected parties. | 1
Ethical # 1 Stakeholder Equity | Perceived injustices or inequalities | Allegations of discrimination, favoritism, or marginalization | Public backlash and community protests Loss of stakeholder | 2 | Stakeholder equity concerns can lead to public backlash and loss of trust, resulting in project disruptions. | 2 | While stakeholder equity is important, it may not exceed risk tolerance if addressed promptly. | 2 | Probability of stakeholder equity issues depends on stakeholder perceptions and project interactions. | 2 | Stakeholder equity concerns may be visible through social media posts, community feedback, or stakeholder surveys. | 2
Ethical # 2 Conflict of Interest | Potential conflicts of interest among project stakeholders or decision-makers. | Situations where individuals or entities may prioritize personal or professional interests over the project's objectives. | Compromised decision-making processes leading to suboptimal project outcomes. Damage to the project's reputation and integrity. Legal or ethical investigations resulting in delays or disruptions to project progress. | 1 | Conflict of interest can lead to compromised decision-making and loss of stakeholder trust, posing risks to project integrity. | 1 | Conflict of interest exceeds risk tolerance as it undermines project transparency and trust. | 1 | Probability of conflict of interest depends on stakeholder relationships and ethical guidelines. | 1 | Conflict of interest may be visible through conflicts disclosure statements or whistleblowing reports. | 1
Opportunities which could be created by factors external to the project | Opportunity |  |  | Opportunity Priority 1, 2 or 3 | Opportunity assessment: What and how large is the Benefit of the Opportunity? |  |  |  | Opportunity assessment: probability or frequency of event happening, and extent to which it can be detected
Factor (based on STEEPLE analysis tool) | Situation | Event | Alternative benefits (positive outcomes) that could result | Priority to realize opportunity & deliver benefits | How large is the resulting positive outcome? Explain why. | Initial priority (1,2,3) to review, based on size of benefit? | Does the benefit exceed benefits of 'status quo'? Explain why. | Revised priority (1,2,3) to review, based on added benefits? | What is the probability or frequency of the event? Explain why. | Initial priority (1,2,3) to review, based on probability or frequency | If (or when) the event happens, can we easily see it happen? Explain why. | Revised priority (1,2,3) to review, based on visibility
Social # 1 Infrastructure Development | Economic growth in the region | Government investment in infrastructure projects | Job creation, improved transportation networks | 1 | Economic growth and development resulting from infrastructure investment have significant positive impacts on employment, transportation, and overall regional prosperity. 1 | 1 | Infrastructure development creates more jobs, improves transportation, and boosts economic activity compared to the absence of such investments. | 1 | The probability of government investment in infrastructure is high due to policy priorities and budget allocations. | 1 | Investments in infrastructure projects are highly visible through government announcements, public tenders, and construction activities. | 1
Social # 2 |  |  | Enhanced regional development | 1 |  | 1 |  | 1 |  | 1 |  | 1
Technological # 1 Technological Advancements | Rapid advancements in construction technology | Introduction of advanced construction methods and materials | Increased efficiency and safety. | 1 | Adoption of advanced construction technology can revolutionize project execution by streamlining processes, reducing costs, and enhancing safety measures. | 1 | Advanced technology offers substantial benefits compared to traditional methods, leading to greater efficiency and improved project outcomes. | 1 | The likelihood of technological advancements in the construction industry is high due to ongoing research and development efforts. | 1 | Technological innovations are easily noticeable through industry publications, product demonstrations, and case studies showcasing successful implementations. | 1
Technological # 2 |  |  | Reduced construction time and costs | 1 |  | 1 |  | 1 |  | 1 |  | 1

## R& O Response Matrix
Project Risk Factors | Risk Response |  |  | Assessment of Risk Response
Project Activities and External Factors | Mitigate, avoid, transfer, accept? | Contingency Plan: action to take if the negative outcome happens | Plan B: action to take if the contingency plan fails | Feasibility | Time to Implement (probability X days) | Cost to implement (probability X $) | Qualitative Benefit of implementing physical, social, environmental | Quantitative Benefit of implementing: financial, economic
Construction of Adelaide Street Underpass | Mitigate | Regular inspections and safety protocols | Activation of emergency response and evacuation | High | Medium (20 days) | High ($70,000) | Enhanced worker safety and project efficiency | Prevention of costly accidents and delays
Intersection Improvements at Central Avenue | Mitigate | Traffic management plan and signal optimization | Implementation of alternative routes | High | Medium (15 days) | Medium ($50,000) | Improved traffic flow and safety | Reduction of congestion and travel time
Active Transportation Connection Development | Mitigate | Collaboration with local cycling and pedestrian groups | Adoption of alternative routing solutions | High | Medium-high (25 days) | Medium-high ($80,000) | Promotion of sustainable transportation options | Enhancement of community well-being
Road Detour Implementation | Mitigate | Advance communication and signage for detour routes | Implementation of temporary traffic controls | High | Low-medium (10 days) | Medium ($40,000) | Minimization of disruption to road users | Reduction of detour-related congestion
Railway Crossing Closure for Underpass Construction | Transfer | Coordination with railway authorities for closure arrangements | Establishment of contingency traffic plans | High | Medium-high (25 days) | High ($90,000) | Transfer of safety risks and liabilities during construction | Protection of project assets and schedules
Social # 1 Community Opposition | Mitigate | Community engagement to address concerns and provide transparent communication | Allocate additional resources for legal support and community outreach | High | Medium-high (30 days) | High ($50,000) | Improved community relations and project acceptance | Potential cost savings from avoiding legal disputes and project delays
Social # 2 Public Perception | Mitigate | Public relations campaign to improve project perception and highlight benefits | Develop alternative communication strategies for different stakeholder groups | High | Medium (20 days) | Medium ($30,000) | Enhanced public support and engagement | Potential increase in project funding and partnerships
Technological # 1 Construction Technology Failure | Mitigate | Regular equipment maintenance and safety inspections | Establish emergency response protocols and alternative work plans | High | Low-medium (15 days) | High ($70,000) | Enhanced worker safety and project efficiency | Prevention of costly accidents and project delays
Technological # 2 Data Security Breach | Mitigate | Implementation of robust cybersecurity measures and regular audits | Data backup and recovery procedures, incident response team activation | High | Medium (20 days) | High ($60,000) | Protection of sensitive information and stakeholder trust | Prevention of financial losses and reputational damage
Economic # 1 Funding Shortfall | Accept | Diversification of funding sources and creation of a reserve fund | Scaling back non-essential project components or seeking alternative financing | High | Medium-high (25 days) | High ($100,000) | Flexibility in funding and project adaptability | Minimization of financial risks and project disruptions
Economic # 2 Market Instability | Mitigate | Continuous monitoring of market trends and early identification of potential risks | Development of risk hedging strategies and partnerships with suppliers | High | Medium (20 days) | Medium-high ($80,000) | Reduced exposure to market fluctuations and supply chain disruptions | Preservation of project budget and schedule integrity
Environmental # 1 Ecological Damage | Mitigate | Implementation of stringent environmental protection measures and emergency response plans | Collaboration with environmental agencies and community organizations | High | High (35 days) | High ($120,000) | Preservation of ecosystems and community goodwill | Prevention of legal liabilities and reputational harm
Environmental # 2 Natural Disasters | Transfer | Purchase of comprehensive insurance coverage for natural disasters and force majeure events | Establish emergency evacuation and disaster recovery protocols | High | Low-medium (15 days) | High ($90,000) | Transfer of financial risks to insurance providers | Protection of project assets and financial stability
Political # 1 Regulatory Change | Mitigate | Active engagement with policymakers and regulatory bodies to anticipate and address potential changes | Legal review of project compliance and lobbying efforts for policy advocacy | High | Medium-high (25 days) | High ($80,000) | Maintaining regulatory compliance and project alignment | Prevention of regulatory delays and legal disputes
Political # 2 Government Instability | Accept | Scenario planning and development of flexible project plans to adapt to political changes | Establishment of stakeholder engagement and advocacy networks | High | Medium (20 days) | Medium ($50,000) | Adaptability to political dynamics and decision-making processes | Reduction of project exposure to political risks and uncertainties
Legal #1 Contract Disputes | Mitigate | Contractual risk assessments and negotiations to clarify terms and responsibilities | Engagement of legal counsel for dispute resolution and mediation | High | High (35 days) | High ($100,000) | Protection of project interests and compliance with legal requirements | Minimization of legal liabilities and financial losses
Legal #2 Litigation Risk | Transfer | Purchase of liability insurance and establishment of legal contingency funds | Retention of experienced legal counsel and development of dispute resolution protocols | High | Medium-high (25 days) | High ($80,000) | Transfer of legal risks and financial liabilities | Protection of project finances and stakeholder interests
Ethical # 1 Stakeholder Equity | Mitigate | Establishment of clear ethical guidelines and codes of conduct for project stakeholders | Implementation of ethics training programs and whistleblower mechanisms | High | Medium (20 days) | Medium ($40,000) | Promotion of transparency and accountability in project operations | Prevention of ethical violations and damage to project reputation
Ethical # 2 Conflict of Interest | Avoid | Disclosure of conflicts of interest and recusal of affected parties from decision-making processes | Establishment of independent oversight committees and conflict resolution mechanisms | High | Medium (20 days) | Medium ($60,000) | Preservation of project integrity and stakeholder trust | Prevention of conflicts of interest and legal liabilities
Project Opportunities | Opportunity Response |  |  | Assessment of Opportunity Response
Project Activities and External Factors | Enhance, Exploit, Share, Accept? (opposite of Risk Responses) | Benefits Realization Plan: action to take if the positive outcome happens | Opportunity Plan B: action to take if the benefits realization plan fails | Feasibility | Time to Implement (probability X days) | Cost to implement (probability X $) | Qualitative Benefit of implementing physical, social, environmental | Quantitative Benefit of implementing: financial, economic
Development of Active Transportation Connection | Exploit | Collaborate with local authorities to promote active transportation options and integrate them into urban planning. | If the initial plan fails, engage with community stakeholders and conduct surveys to identify alternative solutions. | High | Medium (50%) X 60 days | High (75%) X $50,000 | Enhances community health and well-being by providing safe and sustainable transportation alternatives, reduces traffic congestion and pollution. | Increases property values, reduces healthcare costs, and boosts local economies through increased tourism and recreational activities.
Intersection Improvements at Central Avenue | Enhance | Implement traffic flow optimization measures and upgrade intersection infrastructure to enhance safety and reduce congestion. | If initial improvements are ineffective, conduct further traffic studies and consult with traffic engineering experts to identify additional enhancement opportunities. | High | Medium (50%) X 90 days | High (75%) X $100,000 | Improves traffic safety, reduces accidents, enhances pedestrian and cyclist accessibility, and promotes smoother traffic flow. | Reduces vehicle operating costs, decreases travel time, and lowers the risk of accidents, resulting in potential savings for individuals and businesses.
Social # 1 Infrastructure Development | Exploit | Collaborate with government agencies and private sector partners to secure funding for infrastructure projects and expedite development timelines. | If funding efforts fall short, explore alternative financing options such as public-private partnerships or crowdfunding initiatives. | High | High (75%) X 120 days | High (75%) X $200,000 | Enhances public infrastructure, stimulates economic growth, creates job opportunities, and improves overall quality of life for residents. | Generates direct and indirect economic benefits through increased employment, business development, and property value appreciation, leading to long-term economic prosperity.
Technological # 1 Technological Advancements | Exploit | Invest in research and development to adopt cutting-edge construction technologies and methodologies to improve project efficiency and outcomes. | If technological implementation faces challenges, collaborate with industry leaders and experts to troubleshoot issues and optimize technology integration. | High | High (75%) X 180 days | High (75%) X $300,000 | Increases construction productivity, enhances safety, reduces environmental impact, and improves project quality and timeliness. | Lowers construction costs, accelerates project delivery, minimizes resource waste, and enhances competitiveness, resulting in higher profitability and market share.

## Summary R & O Matrix
Project Risk Factors | Risk |  |  | Risk assessment |  |  | Risk Response |  |  | Assessment of Risk Response
Project Activities and External Factors | Hazard | Event | Negative outcome | Severity of negative outcome | Probability / frequency of event | Visibility of event | Mitigate, avoid, transfer, accept | Contingency | Plan B | Feasibility | Cost | Benefit
Construction of Adelaide Street Underpass | Excavation and tunneling | Collapse of tunnel or excavation site | Delay in project timeline | 1 | 1 | 1 | Mitigate | Regular inspections and safety protocols | Activation of emergency response and evacuation | High | High ($70,000) | Enhanced worker safety and project efficiency
Intersection Improvements at Central Avenue | Traffic congestion and diversions | Traffic accidents or collisions | Injury or fatalities to motorists, pedestrians, or cyclists | 2 | 2 | 2 | Mitigate | Traffic management plan and signal optimization | Implementation of alternative routes | High | Medium ($50,000) | Improved traffic flow and safety
Active Transportation Connection Development | Pedestrian and cyclist safety | Accidents or conflicts with vehicular traffic | Legal liabilities due to accidents or injuries | 1 | 1 | 1 | Mitigate | Collaboration with local cycling and pedestrian groups | Adoption of alternative routing solutions | High | Medium-high ($80,000) | Promotion of sustainable transportation options
Road Detour Implementation | Traffic diversion and rerouting | Traffic congestion or gridlock | Increased travel time and commuting frustrations for motorists | 2 | 2 | 2 | Mitigate | Advance communication and signage for detour routes | Implementation of temporary traffic controls | High | Medium ($40,000) | Minimization of disruption to road users
Railway Crossing Closure for Underpass Construction | Disruption to railway operations | Rail service delays or interruptions | Impact on freight and passenger rail services, leading to delays in goods transportation and commuter travel | 1 | 1 | 1 | Transfer | Coordination with railway authorities for closure arrangements | Establishment of contingency traffic plans | High | High ($90,000) | Transfer of safety risks and liabilities during construction
Social # 1 Community Opposition | Resistance from local residents or community groups | Public protests, petitions, or legal challenges | Project delays due to legal proceedings or permit revocations Increased construction costs from additional mitigation measures Damage to stakeholder relationships and public perception | 1 | 1 | 1 | Mitigate | Community engagement to address concerns and provide transparent communication | Allocate additional resources for legal support and community outreach | High | High ($50,000) | Improved community relations and project acceptance
Social # 2 Public Perception | Negative media coverage or public sentiment | Media campaigns, social media backlash, or community forums | Difficulty in securing future project approvals or funding Decreased public participation and support for project initiatives Reputational damage to project sponsors and stakeholders | 2 | 2 | 2 | Mitigate | Public relations campaign to improve project perception and highlight benefits | Develop alternative communication strategies for different stakeholder groups | High | Medium ($30,000) | Enhanced public support and engagement
Technological # 1 Construction Technology Failure | Equipment malfunction or technical glitches | Machinery breakdowns, software errors, or safety system failures | Worksite accidents leading to injuries or fatalities Project delays due to equipment repairs or replacements Increased construction costs from downtime and productivity losses | 1 | 1 | 1 | Mitigate | Regular equipment maintenance and safety inspections | Establish emergency response protocols and alternative work plans | High | High ($70,000) | Enhanced worker safety and project efficiency
Technological # 2 Data Security Breach | Cybersecurity vulnerabilities or data breaches | Unauthorized access, hacking, or data theft | Exposure of sensitive project information to competitors or hackers Legal penalties and fines for data privacy violations Loss of stakeholder trust and confidence in project management | 2 | 2 | 2 | Mitigate | Implementation of robust cybersecurity measures and regular audits | Data backup and recovery procedures, incident response team activation | High | High ($60,000) | Protection of sensitive information and stakeholder trust
Economic # 1 Funding Shortfall | Budget constraints or financial instability | Government funding cuts, donor withdrawals, or economic downturns | Project downsizing or cancellation Incomplete or substandard project deliverables Legal disputes with funding agencies or sponsors | 1 | 1 | 1 | Accept | Diversification of funding sources and creation of a reserve fund | Scaling back non-essential project components or seeking alternative financing | High | High ($100,000) | Flexibility in funding and project adaptability
Economic # 2 Market Instability | Fluctuations in market conditions or resource availability | Supply chain disruptions, currency fluctuations, or inflation | Increased material costs and project expenditures Delayed procurement of essential project resources Impact on project timelines and delivery schedules | 2 | 2 | 2 | Mitigate | Continuous monitoring of market trends and early identification of potential risks | Development of risk hedging strategies and partnerships with suppliers | High | Medium-high ($80,000) | Reduced exposure to market fluctuations and supply chain disruptions
Environmental # 1 Ecological Damage | Potential harm to natural ecosystems or habitats | Spills, leaks, or contamination from construction activities | Ecological damage to waterways, soil, or vegetation Legal fines and penalties for environmental violations Reputational damage and public outcry against project sponsors | 1 | 1 | 1 | Mitigate | Implementation of stringent environmental protection measures and emergency response plans | Collaboration with environmental agencies and community organizations | High | High ($120,000) | Preservation of ecosystems and community goodwill
Environmental # 2 Natural Disasters | Unpredictable natural events or phenomena | Floods, earthquakes, hurricanes, or wildfires | Destruction of project infrastructure and assets Loss of life or injuries to project workers or nearby residents Project delays and increased costs for recovery and reconstruction | 1 | 1 | 1 | Transfer | Purchase of comprehensive insurance coverage for natural disasters and force majeure events | Establish emergency evacuation and disaster recovery protocols | High | High ($90,000) | Transfer of financial risks to insurance providers
Political # 1 Regulatory Change | Government policy shifts or legislative reforms | Introduction of new laws, regulations, or zoning restrictions | Project redesign to comply with updated regulations Delayed project approvals or permits Legal challenges and disputes over regulatory interpretations | 1 | 1 | 1 | Mitigate | Active engagement with policymakers and regulatory bodies to anticipate and address potential changes | Legal review of project compliance and lobbying efforts for policy advocacy | High | High ($80,000) | Maintaining regulatory compliance and project alignment
Political # 2 Government Instability | Political unrest, leadership changes, or governance issues | Elections, regime changes, or political upheavals | Shifting project priorities or funding allocations Policy reversals impacting project feasibility or viability Increased bureaucratic hurdles and administrative delays | 2 | 2 | 2 | Accept | Scenario planning and development of flexible project plans to adapt to political changes | Establishment of stakeholder engagement and advocacy networks | High | Medium ($50,000) | Adaptability to political dynamics and decision-making processes
Legal #1 Contract Disputes | Contractual disagreements or breaches | Disputes over project specifications, timelines, or payment terms | Project delays or interruptions due to legal proceedings Financial losses from legal fees and settlements Damage to stakeholder relationships and project reputation | 1 | 1 | 1 | Mitigate | Contractual risk assessments and negotiations to clarify terms and responsibilities | Engagement of legal counsel for dispute resolution and mediation | High | High ($100,000) | Protection of project interests and compliance with legal requirements
Legal #2 Litigation Risk | Legal challenges or lawsuits | Claims of harm or violations brought against project stakeholders | Legal expenses and settlements impacting project finances Reputational damage and public scrutiny Project delays or modifications to address legal requirements | 1 | 1 | 1 | Transfer | Purchase of liability insurance and establishment of legal contingency funds | Retention of experienced legal counsel and development of dispute resolution protocols | High | High ($80,000) | Transfer of legal risks and financial liabilities
Ethical # 1 Stakeholder Equity | Perceived injustices or inequalities | Allegations of discrimination, favoritism, or marginalization | Public backlash and community protests Loss of stakeholder | 2 | 2 | 2 | Mitigate | Establishment of clear ethical guidelines and codes of conduct for project stakeholders | Implementation of ethics training programs and whistleblower mechanisms | High | Medium ($40,000) | Promotion of transparency and accountability in project operations
Ethical # 2 Conflict of Interest | Potential conflicts of interest among project stakeholders or decision-makers. | Situations where individuals or entities may prioritize personal or professional interests over the project's objectives. | Compromised decision-making processes leading to suboptimal project outcomes. Damage to the project's reputation and integrity. Legal or ethical investigations resulting in delays or disruptions to project progress. | 1 | 1 | 1 | Avoid | Disclosure of conflicts of interest and recusal of affected parties from decision-making processes | Establishment of independent oversight committees and conflict resolution mechanisms | High | Medium ($60,000) | Preservation of project integrity and stakeholder trust
Project Risk Opportunity Factors | Opportunity |  |  | Opportunity assessment |  |  | Opportunity response |  |  | Assessment of Opportunity Response
Project Activities and External Factors | Situation | Event | Positive outcome | Benefits from positive outcome | Probability / frequency of event | Visibility of event | Enhance, Exploit, Share, Accept? (opposite of Risk Responses) | Benefits Realization Plan: action to take if the positive outcome happens | Opportunity Plan B: action to take if the benefits realization plan fails | Feasibility | Cost | Benefit
Development of Active Transportation Connection | City planning | Implementation of new pedestrian and cyclist pathways | Reduced traffic congestion Improved air quality, enhanced public health | 1 | 1 | 1 | Exploit | Collaborate with local authorities to promote active transportation options and integrate them into urban planning. | If the initial plan fails, engage with community stakeholders and conduct surveys to identify alternative solutions. | High | High (75%) X $50,000 | Enhances community health and well-being by providing safe and sustainable transportation alternatives, reduces traffic congestion and pollution.
Intersection Improvements at Central Avenue | Urban development | Installation of traffic lights and pedestrian crossings | Improved traffic flow and Enhanced pedestrian safety, reduced accidents | 2 | 2 | 2 | Enhance | Implement traffic flow optimization measures and upgrade intersection infrastructure to enhance safety and reduce congestion. | If initial improvements are ineffective, conduct further traffic studies and consult with traffic engineering experts to identify additional enhancement opportunities. | High | High (75%) X $100,000 | Improves traffic safety, reduces accidents, enhances pedestrian and cyclist accessibility, and promotes smoother traffic flow.
Social # 1 Infrastructure Development | Economic growth in the region | Government investment in infrastructure projects | Job creation, improved transportation networks and Enhanced regional development | 1 | 1 | 1 | Exploit | Collaborate with government agencies and private sector partners to secure funding for infrastructure projects and expedite development timelines. | If funding efforts fall short, explore alternative financing options such as public-private partnerships or crowdfunding initiatives. | High | High (75%) X $200,000 | Enhances public infrastructure, stimulates economic growth, creates job opportunities, and improves overall quality of life for residents.
Technological # 1 Technological Advancements | Rapid advancements in construction technology | Introduction of advanced construction methods and materials | Increased efficiency and safety. Reduced construction time and costs. | 1 | 1 | 1 | Exploit | Invest in research and development to adopt cutting-edge construction technologies and methodologies to improve project efficiency and outcomes. | If technological implementation faces challenges, collaborate with industry leaders and experts to troubleshoot issues and optimize technology integration. | High | High (75%) X $300,000 | Increases construction productivity, enhances safety, reduces environmental impact, and improves project quality and timeliness.

## Risk & Opportunity Register
RISK |  |  | BRIEF DESCRIPTION OF IMPACT | PROBABILITY (High/Med./Low) | IMPACT (High/Med./Low) | RANKING (High/Med. /Low) | MITIGATION STRATEGY/ ACTION PLAN (Avoid, Transfer, Mitigate or Accept) | Triggers | MITIGATED RANKING | RESPONSIBILITY (Group & Individual) | Move into quant. analysis? ( Move Forward) | Time Probability | Time Impact (days) | Time Expected Monetary Value (days) | Cost Probability | Cost Impact | Cost Expected Monetary Value | Move into Plan Risk Responses? | Contingency Plan | Trigger | Fallback Plan | Trigger
I |  | Overall Project Risks | [6 empty] | Category Lead:
I | 1 | Construction of Adelaide Street Underpass Collapse of tunnel or excavation site | Delay in project timeline | High | High | High | Mitigate | Construction activities | High | Engineering Team (Group) | Yes | 50% | 30 | 15 | 75% | 100000 | 75000 | Yes | Evacuation of workers and public, emergency response plan | Tunnel excavation equipment malfunction | Engage additional rescue personnel | Delayed response to emergency situation
I | 2 | Intersection Improvements at Central Avenue Traffic accidents or collisions | Injury or fatalities to motorists, pedestrians, or cyclists | Med. | Med. | Med. | Mitigate | Increased traffic volume and road changes | Med. | Traffic Engineer (Individual) | No | 10% | 0 | 0 | 50% | 40000 | 20000 | Yes | Implement traffic calming measures, increase signage | High traffic congestion during peak hours | Implement temporary traffic control measures | Failure to mitigate traffic congestion
I | 3 | Active Transportation Connection Development Pedestrian and cyclist safety | Legal liabilities due to accidents or injuries | High | High | High | Mitigate | Construction activities | Med. | Safety Officer (Individual) | Yes | 50% | 20 | 10 | 25% | 20000 | 5000 | Yes | Implement safety barriers, increase awareness campaigns | Increase in accidents involving pedestrians/cyclists | Implement safety training for workers | Failure to ensure safety measures
I | 4 | Road Detour Implementation Traffic diversion and rerouting | Increased travel time and commuting frustrations for motorists | Med. | Med. | Med. | Mitigate | Road construction and detour implementation | Low | Project Manager (Individual) | No | 0 | 0 | 0 | 10% | 0 | 0 | Yes | Adjust construction schedule, provide alternate routes | Detour route blocked due to unforeseen circumstances | Implement temporary traffic control measures | Insufficient traffic management
I | 5 | Railway Crossing Closure for Underpass Construction Disruption to railway operations | Impact on freight and passenger rail services, leading to delays in goods transportation and commuter travel | High | High | High | Transfer | Closure of railway crossing for construction | High | Construction Manager (Individual) | Yes | 75% | 30 | 22.5 | 75% | 150000 | 112500 | Yes | Coordinate with railway authorities, implement alternative transportation methods | Railway closure notice received | Implement shuttle services | Insufficient shuttle services
I | 6 | Social # 1 Community Opposition | Project delays due to legal proceedings or permit revocations Increased construction costs from additional mitigation measures Damage to stakeholder relationships and public perception | High | High | High | Mitigate | Project announcement and engagement | Med. | Public Relations Team (Group) | No |  |  | 0 | 50% |  | 0 | Yes | Conduct community meetings, address concerns through dialogue | Opposition from local community leaders | Engage in mediation process | Failure to reach consensus
I | 7 | Social # 2 Public Perception | Difficulty in securing future project approvals or funding Decreased public participation and support for project initiatives Reputational damage to project sponsors and stakeholders | Med. | Med. | Med. | Mitigate | Media coverage and public opinion | Low | Communications Officer (Individual) | Yes | 25% | 15 | 3.75 | 25% | 50000 | 12500 | No | N/A | N/A | N/A | N/A
I | 8 | Technological # 1 Construction Technology Failure | Worksite accidents leading to injuries or fatalities Project delays due to equipment repairs or replacements Increased construction costs from downtime and productivity losses | High | High | High | Mitigate | Equipment malfunction or software errors | High | Technology Team (Group) | Yes | 75% | 20 | 15 | 75% | 80000 | 60000 | Yes | Backup systems activation, regular maintenance checks | Malfunction detected in construction equipment | Implement software update | Failure to resolve technology issue
I | 9 | Technological # 2 Data Security Breach | Exposure of sensitive project information to competitors or hackers Legal penalties and fines for data privacy violations Loss of stakeholder trust and confidence in project management | Med. | Med. | Med. | Mitigate | Cybersecurity vulnerabilities | Med. | IT Security Team (Group) | Yes | 50% | 25 | 12.5 | 75% | 120000 | 90000 | Yes | Activate incident response plan, isolate affected systems | Unusual network activity detected | Activate backup systems | Failure of backup systems
I | 10 | Economic # 1 Funding Shortfall | Project downsizing or cancellation Incomplete or substandard project deliverables Legal disputes with funding agencies or sponsors | High | High | High | Accept | Insufficient project budget | High | Finance Department (Group) | No |  |  | 0 | 75% |  | 0 | Yes | Seek additional funding sources, prioritize expenditures | Funding request denied by stakeholders | Implement cost-saving measures | Insufficient cost-saving measures
I | 11 | Economic # 2 Market Instability | Increased material costs and project expenditures Delayed procurement of essential project resources Impact on project timelines and delivery schedules | Med. | Med. | Med. | Mitigate | Economic downturn | Med. | Project Management Team (Group) | Yes | 50% | 20 | 10 | 50% | 70000 | 35000 | Yes | Diversify revenue streams, renegotiate contracts | Sudden drop in market indices | Activate emergency fund | Inadequate emergency fund
I | 12 | Environmental # 1 Ecological Damage | Ecological damage to waterways, soil, or vegetation Legal fines and penalties for environmental violations Reputational damage and public outcry against project sponsors | High | High | High | Mitigate | Construction activities | High | Environmental Compliance Officer (Individual) | Yes | 75% | 30 | 22.5 | 75% |  | 0 | Yes | Implement environmental protection measures, clean-up efforts | Contaminant spill detected | Engage environmental cleanup team | Delayed response to environmental threat
I | 13 | Environmental # 2 Natural Disasters | Destruction of project infrastructure and assets Loss of life or injuries to project workers or nearby residents Project delays and increased costs for recovery and reconstruction | High | High | High | Transfer | Extreme weather events | High | Emergency Response Team (Group) | Yes | 75% | 40 | 30 | 75% | 200000 | 150000 | Yes | Activate emergency response plan, evacuate affected areas | Severe weather warning issued | Activate emergency shelters | Inadequate emergency shelters
I | 14 | Political # 1 Regulatory Change | Project redesign to comply with updated regulations Delayed project approvals or permits Legal challenges and disputes over regulatory interpretations | High | High | High | Mitigate | Legislative or policy changes | Med. | Legal Team (Group) | Yes | 50% | 20 | 10 | 50% | 70000 | 35000 | Yes | Review and update compliance procedures, seek legal counsel | New regulation announced | Seek legal interpretation | Delayed legal interpretation
I | 15 | Political # 2 Government Instability | Shifting project priorities or funding allocations Policy reversals impacting project feasibility or viability Increased bureaucratic hurdles and administrative delays | Med. | Med. | Med. | Accept | Political unrest or regime change | High | Government Relations Manager (Individual) | Yes | 75% | 25 | 18.75 | 75% | 120000 | 90000 | Yes | Monitor political situation, engage with government officials | Civil unrest reported | Activate crisis management plan | Ineffective crisis management
I | 16 | Legal #1 Contract Disputes | Project delays or interruptions due to legal proceedings Financial losses from legal fees and settlements Damage to stakeholder relationships and project reputation | High | High | High | Mitigate | Breach of contract terms or agreements | Med. | Legal Team (Group) | Yes | 50% | 30 | 15 | 50% | 100000 | 50000 | Yes | Negotiate terms with contractors, seek legal resolution | Dispute with contractor identified | Engage in mediation process | Failure of mediation process
I | 17 | Legal #2 Litigation Risk | Legal expenses and settlements impacting project finances Reputational damage and public scrutiny Project delays or modifications to address legal requirements | High | High | High | Transfer | Legal disputes or lawsuits | High | Legal Team (Group) | Yes | 75% | 40 | 30 | 75% | 150000 | 112500 | Yes | Prepare legal defense, engage in settlement negotiations | Legal notice received | Initiate legal proceedings | Ineffective legal defense
I | 18 | Ethical # 1 Stakeholder Equity | Public backlash and community protests Loss of stakeholder | Med. | Med. | Med. | Mitigate | Dissatisfaction or opposition from stakeholders | Med. | Stakeholder Engagement Team (Group) | No |  |  | 0 | 50% |  | 0 | Yes | Address concerns through communication and engagement | Stakeholder protest or demonstration | Initiate stakeholder dialogue
I | 19 | Ethical # 2 Conflict of Interest | Compromised decision-making processes leading to suboptimal project outcomes. Damage to the project's reputation and integrity. Legal or ethical investigations resulting in delays or disruptions to project progress. | Med. | High | High | Avoid | Ethical breaches or conflicting interests | Med. | Ethics Committee (Group) | No | 0 | 0 | 0 | 50% | 0 | 0 | Yes | Investigate allegations, enforce conflict-of-interest policies | Conflict of interest reported | Conduct internal investigation
|  | Opportunity | BRIEF DESCRIPTION OF Benefit |  |  |  | Action Plan Enhance, Exploit, Share, Accept? | Triggers |  | RESPONSIBILITY (Group & Individual)
I | 1 | Development of Active Transportation Connection Implementation of new pedestrian and cyclist pathways | Reduced traffic congestion Improved air quality, enhanced public health | High | High | High | Exploit | Urban development initiatives | High | Project Manager (Individual), Engineering Team (Group) | Yes | 50% | 30 | 15 | 25% | 40000 | 10000 | Yes | Public engagement, collaboration with local authorities | Approval of project funding | Seek alternative funding sources | Initial design not approved
I | 2 | Intersection Improvements at Central Avenue Installation of traffic lights and pedestrian crossings | Improved traffic flow and Enhanced pedestrian safety, reduced accidents | High | High | High | Enhance | Traffic congestion issues | High | Traffic Engineer (Individual), Construction Team (Group) | Yes | 75% | 45 | 33.75 | 75% | 100000 | 75000 | Yes | Traffic flow analysis, stakeholder engagement | Funding secured | Seek public-private partnerships | Contractor default on project
I | 3 | Social # 1 Infrastructure Development | Job creation, improved transportation networks and Enhanced regional development | High | High | High | Exploit | Population growth and urbanization | High | Urban Planner (Individual), City Council (Group) | Yes | 50% | 60 | 30 | 75% | 120000 | 90000 | Yes | Community engagement, public-private partnerships | Funding secured | Seek additional funding sources | Delayed approvals from regulatory authorities
I | 4 | Technological # 1 Technological Advancements | Increased efficiency and safety. Reduced construction time and costs. | High | High | High | Exploit | Technological advancements in the industry | High | Technology Manager (Individual), R&D Team (Group) | Yes | 75% | 90 | 67.5 | 75% | 150000 | 112500 | Yes | Research and development, testing phase | Prototype successfully tested | Explore alternative technologies | Insufficient research funding
|  |  |  | Low | Low | Low |  |  | Med. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | Low
|  |  |  | Low | Low | Low |  |  | Med.
|  | Risk per activity |  | Low | Low | Low
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | High
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | High
|  |  |  | Low | Low | Low |  |  | Low
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | Low
|  |  |  | Low | Low | Low |  |  | Med.
|  |  |  | Low | Low | Low |  |  | Low
|  |  |  | Low | Low | Low |  |  | Low
|  |  |  | Low | Low | Low |  |  | Low
|  |  |  | Low | Low | Low |  |  | Low
|  |  |  | Low | Low | Low |  |  | Low
Average
*List Values - Do Not Delete
[13 empty] | Prob | Imp.
[13 empty] | High | High
[13 empty] | Med. | Med.
[13 empty] | Low | Low
Reason for Moving Forward
The Probability and Imapct criteria lie in the range of 1-3 if low, 4-6 if Medium and 7-9 if high. We have an overall risk register avgerage P x I Score of 23. We have decided to keep 23 as our threshold for analysing further risk(moving forward). We have reached to a consensus that not much can go wrong with a score range of 20-28 as mitigation is not a very difficult task. Hence we have a score of 23 as our threshold for this project.
|  |  |  | Prob vs Impact |  | = Rank
|  |  |  | High | High | High
|  |  |  | Med. | High | High
|  |  |  | High | Med. | High
|  |  |  | Low | High | Med.
|  |  |  | Med. | Med. | Med.
|  |  |  | High | Low | Med.
|  |  |  | Low | Med. | Low
|  |  |  | Med. | Low | Low
|  |  |  | Low | Low | Low
Risk Response and Mitigation Strategies
Avoid: Revise approach to avoid the risk in the first place.
Transfer: Transfer the risk to others via contracts, insurance, etc.
Mitigate: Revise approach to reduce risk probability/ impact.
Accept: Accept the risk and develop contingencies.
Corporate Level Risk Rankings

## Impact & Probability
Risk Response and Mitigation Strategies
Avoid: Revise approach to avoid the risk in the first place.
Transfer: Transfer the risk to others via contracts, insurance, etc.
Mitigate: Revise approach to reduce risk probability/ impact.
Accept: Accept the risk and develop contingencies.
Corporate Level Risk Rankings
High
Medium
Low
I
M
P
A
C
T
P
ROBABILITY
Risk is likely to occur
without mitigation
.
Significant impact to project
schedule
,
quality
,
scope
and
/
or cost
.
Risk is not likely to occur
.
Minor impact to project
schedule
,
quality
,
scope
and
/
or cost
.
Risk is likely to occur
without mitigation
.
Minor impact to project
schedule
,
quality
,
scope
and
/
or cost
.
Risk may occur
.
Moderate impact to project
schedule
,
quality
,
scope
and
/
or cost
.
Risk may occur
.
Minor impact to project
schedule
,
quality
,
scope
and
/
or cost
.
Risk may occur
.
Significant
impact to project schedule
,
quality
,
scope and
/
or cost
.
Risk is not likely to occur
.
Moderate impact to project
schedule
,
quality
,
scope
and
/
or cost
.
Risk is not likely to occur
.
Significant impact to project
schedule
,
quality
,
scope
and
/
or cost
.
Risk is likely to occur
without mitigation
.
Moderate
impact to project schedule
,
quality
,
scope and
/
or cost
.
H
i
g
h
M
e
d
i
u
m
L
o
w
C
ORPORATE
L
EVEL
R
ISK
R
ANKINGS

## Time Budget Calculations
Estimating Form
Orignal estimate |  |  |  | Time | Cost
Risk identification, and qualititave and quantitative risk anaylsis result in :
Original Risks | Probability | Impact |  | Expected monetary value
|  | Time in days | Cost in $ | Time in days | Cost in $
Environmental # 2 Natural Disasters | 75% | 40 | 200000 | 30 | 150000
Social #2 Public Perception | 25% | 15 | 50000 | 3.75 | 12500
Technological #1 Construction Technology Failure | 75% | 20 | 80000 | 15 | 60000
Technological #2 Data Security Breach | 50% | 25 | 120000 | 12.5 | 60000
Economic #2 Market Instability | 50% | 20 | 70000 | 10 | 35000
|  |  |  | 71.25 | 317500
|  |  |  | 120 | 520000
|  |  |  | 191.25 | 837500
|  |  |  | Time in days | Cost in $
| Probability | Impact |  | EMV
|  | Time | Cost in $ | Time in Days | Cost in $
Social # 1 Infrastructure Development | 50% | 60 | 120000 | 30 | 60000
Technological # 1 Technological Advancements | 75% | 90 | 150000 | 67.5 | 112500
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 97.5 | 172500
Final project estimate |  |  |  | 97.5 | 172500
Savings resulting from Risk Management: |  |  |  | 93.75 | 665000

## References
References
Adelaide Street North – CP Grade Separation ("Adelaide Underpass"). (2023). Retrieved from getinvolved.london.ca: https://getinvolved.london.ca/adelaide
Baxter, M. (2023). Adelaide Street underpass project a breath of fresh air for London residents. Retrieved from canada.constructconnect.com: https://canada.constructconnect.com/dcn/news/infrastructure/2023/09/adelaide-street-underpass-project-a-breath-of-fresh-air-for-london-residents
(n.d.). City of London ¦ Adelaide Street North - Canadian Pacific Railway Grade Separation Class Environmental Assessment Study Report. City of London.
CityofLondonOntario. (2022). Adelaide Underpass Construction Public Update Meeting. Retrieved from youtube.com: https://www.youtube.com/watch?v=hmVhqVJR8Wc
Garfield Dales, P. D. (2022). Contract Award: Tender RFT 21-97 Adelaide Street North CPR. London, ON: City of London.
Module 2 - MGMT 6062 - PROJECT RISK AND QUALITY. (2023). Retrieved from fanshaweonline.ca: https://www.fanshaweonline.ca/d2l/le/content/1558568/viewContent/14845266/View
Module 3 MGMT 6062 Identify Risks & Opportunities. (2023). Retrieved from fanshaweonline.ca: https://www.fanshaweonline.ca/d2l/le/content/1558568/viewContent/14069186/View
Module 4 MGMT 6062 Qualitative Risk & Opportunity Analysis. (2023). Retrieved from fanshaweonline.ca: https://www.fanshaweonline.ca/content/23F/1558568-MGMT-6062-(01)-24W/PowerPoints/Module%204%20Qualitative%20risk%20analysis.pdf?isCourseFile=true&ou=1558568
Module 5 MGMT 6062 Quantitative Risk & Opportunity Analysis. (2023). Retrieved from fanshaweonline.ca: https://www.fanshaweonline.ca/content/23F/1558568-MGMT-6062-(01)-24W/PowerPoints/Module%205%20Quantitative%20risk%20analysis.pdf?isCourseFile=true&ou=1558568
Module 6 MGMT 6062 Plan Risk & Opportunity Responses. (2023). Retrieved from fanshaweonline.ca: https://www.fanshaweonline.ca/d2l/le/content/1558568/viewContent/14069196/View
Prastowo, T. &. (2020). Risk management on railway projects: A literature view. Facta universitatis - series: Architecture and Civil Engineering.
Simon, A. (2023). Adelaide Street North to be closed as of Wednesday for underpass rail lift. Retrieved from globalnews.ca: https://globalnews.ca/news/9912091/adelaide-street-north-closure-london/
Stacey, M. (2022, Dec). The big dig: An inside look at the massive Adelaide underpass project. Retrieved from lfpress.com: https://lfpress.com/news/local-news/the-big-dig-an-inside-look-at-the-massive-adelaide-underpass-project
Stacey, M. (2023). Sticker shock: Cost of Adelaide Street underpass balloons by 50%. Retrieved from lfpress.com: https://lfpress.com/news/local-news/sticker-shock-cost-of-adelaide-street-underpass-balloons
The official website for the City of London, O. (2022). Adelaide Street North Underpass. Retrieved from london.ca: https://london.ca/projects/adelaide-street-north-underpass
Vincenzo Marchettaa, A. D. (2022). A methodology for introducing the impact of risk analysis in local railways improvements decisions.

## Team
S M Rakibul Basher | 1168369
Gihan Shamike Liyanage | 1142109