## Risk & Opportunity Register
|  | BRIEF DESCRIPTION OF IMPACT | PROBABILITY (High/Med./Low) | IMPACT (High/Med./Low) | RANKING (High/Med. /Low) | Probability Score | Impact Score | Risk Score | MITIGATION STRATEGY/ ACTION PLAN (Avoid, Transfer, Mitigate or Accept) | Triggers | MITIGATED RANKING | RESPONSIBILITY (Group & Individual) | Move into quant. analysis? ( Move Forwar) | Time Probability | Time Impact (days) | Time Expected Monetary Value (days) | Cost Probability | Cost Impact ($) | Cost Expected Monetary Value($) | Move into Plan Risk Responses? | Contingency Plan | Trigger | Fallback Plan | Trigger
| Overall Project Risks | [9 empty] | Category Lead:
1 | Unforeseen Weather Conditions - Environmental | Adverse weather patterns (e.g., heavy rain, snowstorms, extreme temperatures) Extreme weather conditions disrupts outdoor construction operations. Negative impacts: Project delays, increased labor costs, potential safety hazards | Med. | High | High | 5 | 9 | 45 | Mitigate The mitigation strategy for unfavorable weather conditions involves implementing contingency plans, such as adjusting work schedules or temporarily suspending outdoor operations, to minimize disruptions and ensure the safety of personnel and assets. | Weather forecasts indicating high likelihood of adverse conditions | Med. | Construction Manager (Group) | Move Forward | 0.6 | -540 | -324 | 0.6 | -120000 | -72000 | Yes | Adjust project schedules to accommodate delays caused by adverse weather events. | Allocate additional resources for indoor tasks during inclement weather. Extend project timeline to accommodate weather-related delays. | Weather forecasts indicating high likelihood of adverse conditions | Extend project timeline to accommodate weather-related delays
2 | Regulatory Approval Delays - Legal | Delays in regulatory approvals might negatively impact project timelines and budget. | High | High | High | 8 | 9 | 72 | Avoid Establish close communication with regulatory bodies, provide complete and accurate documentation, and monitor approval progress closely. | Lengthy regulatory approval processes | High | Project Manager (Group) | Move forward | 0.8 | -90 | -72 | 0.8 | -250000 | -200000 | Yes | Implement an expedited review process for pending approvals and seek assistance from regulatory agencies if necessary. | Allocate additional resources for expedited approval processes if delays occur. | Delays in regulatory response beyond predefined thresholds | Explore alternative regulatory pathways if significant delays persist
3 | Material Price Fluctuations - Economical | Fluctuations in material prices impact project budget. | Med. | High | High | 5 | 8 | 40 | Transfer Transfer risk through long-term material supply contracts or hedging strategies. | Significant price changes in key construction materials | Med. | Procurement Manager (Group) | [7 empty] | Yes | Negotiate long-term contracts with suppliers to lock in prices or identify alternative sources for materials. | Allocate budget reserves to absorb cost fluctuations. | Sudden increase in material costs | Explore alternative materials or suppliers if costs become prohibitive
4 | Labor Shortages - Economical | Labor shortages due to unforeseen market conditions may delay project milestones. | Med. | High | High | 6 | 9 | 54 | Mitigate Mitigate by exploring subcontracting options or investing in training programs to address skill shortages. | Difficulty in filling key positions within the project team | Med. | Human Resources Manager (Group) | Move Forward | 0.4 | -50 | -20 | 0.4 | -50000 | -20000 | Yes | Partner with temporary staffing agencies to secure additional labor resources or redistribute workloads among existing team members. | Explore subcontracting options or invest in training programs to address skill shortages. | Difficulty in filling key positions within the project team | Adjust project schedule and scope to accommodate labor constraints
5 | Equipment failures - Technological | Equipment failures which construction will delay the project which thereby increase the cost of construction and will also cost potential safety hazards | Med. | High | High | 5 | 9 | 45 | Mitigate - For avoiding the chances of failures of any equipments while construction, regular maintenance has to be carried out. Always have a backup equipment. | If there is a sudden increase in requirement of maintenance than usual maintenance. | Med. | Equipment maintenance team | Move forward | 0.7 | -40 | -28 | 0.7 | -150000 | -105000 | Yes | Quickly activate the backup equipment and repair the broken one | If there is a long time needed for activation | If the backup equipement didn’t work rent the equipment from nearby local rentals | If it takes more duration than usual time to start working
6 | Utility Interuptions - Technological | The interruptions caused to basic utilities such as water, electricity, communication channels etc adversly affect construction works as well as the local community. This causes delays in project and increase the cost. Utility interruptions also effect the small businesses accross the street. | Med. | High | High | 6 | 7 | 42 | Transfer- involve utility providers and sign agreements with them to share this risk. Communicate with themm to minimize the interruption of utilities. | Any delays seen in providing utility, any fluctuations in supply. | Med. | Facilities management team | [7 empty] | Yes | Should have a backup power source to avoid interruption for construction works | Fluctuations in utility supply | Temporarily stop the construction works and work on utility supply works | Any delays in utility restoration
7 | Traffic disruptions - Social | Traffic disruptions due to construction works causes incovenience for public transportation. This also effects the small businesses in the locality, because the accessibility gets decreased and people coming to purchase thing from that locality will reduce accordingly. | Med. | High | High | 6 | 7 | 42 | Avoid - Schedule the main construction works during off peak hours to reduce the traffic disruptions | If there is any public compaints due to traffic delays, any sudden traffic congestions. | High | Project team who prepare the daily schedules, Traffic management team | [7 empty] | Yes | Effective communication for rerouting the traffic directions | If there is an increase in traffic congestion on roads | Communicate with local people for helping to divert the traffic flow | Complaints from public, traffic congestion
8 | Regulatory Compliance Changes - Legal | Regulatory changes in safety standards may lead to project compliance issues. | Med. | High | High | 5 | 8 | 40 | Mitigate Regularly review and update safety protocols to align with regulatory changes. | Notification of impending safety standard revisions | High | Safety Compliance Officer (Group) | [7 empty] | Yes | Retain legal counsel to assess the impact of regulatory changes and develop strategies for timely compliance. | Regularly review and update safety protocols to align with regulatory changes. | Introduction of stricter safety standards or enforcement measures | Engage legal counsel to assess compliance and mitigate potential penalties
9 | Environmental Regulation Changes - Legal | Environmental regulations evolve, impacting project compliance. | Med. | High | High | 5 | 8 | 40 | Mitigate Stay updated on regulatory changes, engage with regulatory bodies, and implement proactive environmental management practices. | Notification of impending regulatory changes | High | Environmental Compliance Officer (Group) | [7 empty] | Yes | Conduct regular environmental audits to ensure compliance with evolving regulations and adjust project plans accordingly. | Stay updated on regulatory changes, engage with regulatory bodies, and implement proactive environmental management practices. | Changes in environmental legislation or standards | Adapt project plans and designs to align with new regulatory requirements
10 | Community Opposition - Social | Community resistance to project development. | Med. | High | High | 5 | 9 | 45 | Mitigate Mitigate by engaging with local stakeholders, addressing concerns transparently, and implementing community benefit programs. | Notice of community opposition or negative media coverage | High | Community Relations Manager (Group) | [7 empty] | Yes | Engage in open dialogue with community leaders and offer concessions or incentives to address concerns and garner support. | Engage with local stakeholders, address concerns transparently, and implement community benefit programs. | Opposition from local residents or interest groups | Explore alternative project locations or designs to mitigate community resistance
11 | Supply Chain Disruptions - | Supply chain disruptions leading to unavailability of resources on time. | Med. | High | High | 5 | 9 | 45 | Mitigate Diversify supplier base, maintain buffer stock for critical materials, and establish clear communication channels with suppliers. | Delivery delays from primary suppliers | Med. | Procurement Manager (Group) | Move forward | 0.5 | -90 | -45 | 0.5 | -150000 | -75000 | Yes | Maintain strategic stockpiles of critical materials and establish backup suppliers to mitigate the effects of disruptions. | Diversify supplier base, maintain buffer stock for critical materials, and establish clear communication channels with suppliers. | Suppliers fail to deliver necessary materials on time | Identify alternative suppliers and expedited shipping options in case of disruptions
12 | Labor Strikes - Ethical | Labor strikes or disputes will affect the project progress. This can temporarily pause the construction works, which thereby affect the project timeline. | Low | High | Med. | 2 | 7 | 14 | Mitigate Foster positive labor relations, establish open communication channels, and address worker concerns proactively. | Notice of strike or labor unrest from union representatives | Med. | Human Resources Manager (Group) | [7 empty] | Yes | Develop contingency plans to redistribute responsibilities and prioritize critical tasks during labor disputes. | Foster positive labor relations, establish open communication channels, and address worker concerns proactively. | Labor union disagreements or grievances | Allocate additional resources for overtime or temporary labor if strikes occur
13 | Design Changes | Any modifications in the design will leacd to changes in scope of the project. Any incomplete ot inaccurate initial designs can lead to request for changes in design by stakeholders | Med. | Med. | Med. | 5 | 5 | 25 | Mitigate Implement robust change management procedures, conduct impact assessments, and seek stakeholder approvals for scope modifications. | Scope change requests from stakeholders | Med. | Project Manager (Group) | [7 empty] | Yes | Establish a change control board to assess proposed scope changes and evaluate their impact on project objectives and timelines. | Implement robust change management procedures, conduct impact assessments, and seek stakeholder approvals for scope modifications. | Scope change requests from stakeholders | Allocate additional funds or reallocate resources to accommodate approved scope changes
14 | Construction of Adelaide Street Underpass Collapse of tunnel or excavation site | Collapse of tunnel results in serious accidents | Low | High | Med. | 2 | 9 | 18 | Mitigate - Give more importance to safety while designing and implementation | Stress indicators reaching the threshold value | High | Engineering Team (Group) | [7 empty] | Yes | Evacuation of workers and public, emergency response plan | Tunnel excavation equipment malfunction | Engage additional rescue personnel | Delayed response to emergency situation
15 | Traffic accidents or collisions | Injury or fatalities to motorists, pedestrians, or cyclists | Med. | High | High | 5 | 7 | 25 | Avoid - By using proper safety signs and employees to check the safety | The rate of accidents increasing beyond a limit | High | Traffic Engineer (Individual) | [7 empty] | Yes | Implement traffic calming measures, increase signage | High traffic congestion during peak hours | Implement temporary traffic control measures | Failure to mitigate traffic congestion
16 | Active Transportation Connection Development Pedestrian and cyclist unsafety | Legal liabilities due to accidents or injuries | Med. | Med. | Med. | 5 | 6 | 30 | Avoid - By using proper safety signs and employees to check the safety | Reports of accidenst happened to pedestriants and cyclists | High | Safety Officer (Individual) | [7 empty] | Yes | Implement safety barriers, increase awareness campaigns | Increase in accidents involving pedestrians/cyclists | Implement safety training for workers | Failure to ensure safety measures
17 | Road Detour Implementation Traffic diversion and rerouting | Increased travel time and commuting frustrations for motorists | High | Low | Med. | 8 | 2 | 16 | Transfer - Plan appropriate alternative routes without causing hinderence to public transportation, seek th ehelp of transportation department within the city | Complaints from the passengers | Med. | Project Manager (Individual) | [7 empty] | Yes | Adjust construction schedule, provide alternate routes | Detour route blocked due to unforeseen circumstances | Implement temporary traffic control measures | Insufficient traffic management
18 | Railway Crossing Closure for Underpass Construction Disruption to railway operations | Impact on freight and passenger rail services, leading to delays in goods transportation and commuter travel | Med. | High | High | 6 | 8 | 48 | Mitigate - Plan the schedule of work accordingly | Delays in railway operations | Med. | Construction Manager (Individual) | [7 empty] | Yes | Coordinate with railway authorities, implement alternative transportation methods | Railway closure notice received | Implement shuttle services | Insufficient shuttle services
19 | Social Public Perception | Difficulty in securing future project approvals or funding Decreased public participation and support for project initiatives Reputational damage to project sponsors and stakeholders | Med. | Med. | Med. | 5 | 5 | 25 | Mitigate - Create a proper communication channel for public to participate | Media posting negative news regarding the project | Med. | Communications Officer (Individual) | [7 empty] | Yes | Conduct public relation campaigns for improve public participation | Negative public responses through medias | Readjust the communication stratergies by discussing with the experts | Negative public survey results
20 | Technological Construction Technology Failure | Worksite accidents leading to injuries or fatalities Project delays due to equipment repairs or replacements Increased construction costs from downtime and productivity losses | Med. | High | High | 5 | 8 | 40 | Mitigate- constant monitoring required | Equipment malfunction or software errors | Med. | Technology Team (Group) | [7 empty] | Yes | Backup systems activation, regular maintenance checks | Malfunction detected in construction equipment | Implement software update | Failure to resolve technology issue
21 | Technological Data Security Breach | Exposure of sensitive project information to competitors or hackers Legal penalties and fines for data privacy violations Loss of stakeholder trust and confidence in project management | Low | High | Med. | 3 | 8 | 24 | Transfer - requires proper security measures, so collaborate with cybersecurity firms | Cybersecurity vulnerabilities | High | IT Security Team (Group) | [7 empty] | Yes | Activate incident response plan, isolate affected systems | Unusual network activity detected | Activate backup systems | Failure of backup systems
22 | Economic Funding Shortfall | Project downsizing or cancellation Incomplete or substandard project deliverables Legal disputes with funding agencies or sponsors | Low | High | Med. | 3 | 7 | 21 | Accept - should always have a contingency reserve to use for unforseen expenses | Insufficient project budget | Med. | Finance Department (Group) | [7 empty] | Yes | Seek additional funding sources, prioritize expenditures | Funding request denied by stakeholders | Implement cost-saving measures | Insufficient cost-saving measures
23 | Economic Market Instability | Increased material costs and project expenditures Delayed procurement of essential project resources Impact on project timelines and delivery schedules | Low | High | Med. | 3 | 5 | 15 | Transfer - should have more than one funding sources | Economic downturn | High | Project Management Team (Group) | [7 empty] | Yes | Diversify revenue streams, renegotiate contracts | Sudden drop in market indices | Activate emergency fund | Inadequate emergency fund
24 | Environmental Ecological Damage | Ecological damage to waterways, soil, or vegetation Legal fines and penalties for environmental violations Reputational damage and public outcry against project sponsors | Med. | Med. | Med. | 5 | 5 | 25 | Avoid- should conduct environemental impact assessments | Construction activities | Med. | Environmental Compliance Officer (Individual) | [7 empty] | Yes | Implement environmental protection measures, clean-up efforts | Contaminant spill detected | Engage environmental cleanup team | Delayed response to environmental threat
25 | Environmental Natural Disasters | Destruction of project infrastructure and assets Loss of life or injuries to project workers or nearby residents Project delays and increased costs for recovery and reconstruction | Low | High | Med. | 2 | 9 | 18 | Mitigate - should prepare emergency plans for unforseen natural disasters | Extreme weather events | Med. | Emergency Response Team (Group) | [7 empty] | Yes | Activate emergency response plan, evacuate affected areas | Severe weather warning issued | Activate emergency shelters | Inadequate emergency shelters
26 | Political Regulatory Change | Project redesign to comply with updated regulations Delayed project approvals or permits Legal challenges and disputes over regulatory interpretations | Low | Med. | Low | 2 | 6 | 12 | Mitigate - should regularly monitor with the authoroties regarding the regulations | Legislative or policy changes | Med. | Legal Team (Group) | [7 empty] | Yes | Review and update compliance procedures, seek legal counsel | New regulation announced | Seek legal interpretation | Delayed legal interpretation
27 | Political Government Instability | Shifting project priorities or funding allocations Policy reversals impacting project feasibility or viability Increased bureaucratic hurdles and administrative delays | Med. | Med. | Med. | 5 | 5 | 25 | Transfer - engage in contact with the government authorities for any updates | Political unrest or regime change | Med. | Government Relations Manager (Individual) | [7 empty] | Yes | Monitor political situation, engage with government officials | Civil unrest reported | Activate crisis management plan | Ineffective crisis management
28 | Legal Contract Disputes | Project delays or interruptions due to legal proceedings Financial losses from legal fees and settlements Damage to stakeholder relationships and project reputation | Med. | Med. | Med. | 5 | 5 | 25 | Mitigate - Clearly define the contracts | Breach of contract terms or agreements | Med. | Legal Team (Group) | [7 empty] | Yes | Negotiate terms with contractors, seek legal resolution | Dispute with contractor identified | Engage in mediation process | Failure of mediation process
29 | Legal Litigation Risk | Legal expenses and settlements impacting project finances Reputational damage and public scrutiny Project delays or modifications to address legal requirements | Low | High | Med. | 2 | 7 | 14 | Transfer- should contact authorities for legal partnership | Legal disputes or lawsuits | Med. | Legal Team (Group) | [7 empty] | Yes | Prepare legal defense, engage in settlement negotiations | Legal notice received | Initiate legal proceedings | Ineffective legal defense
30 | Ethical Stakeholder Equity | Public backlash and community protests Loss of stakeholder | Low | Med. | Low | 2 | 5 | 10 | Mitigate - concerns of stakeholders has to be addressed fairly and in a timely manner | Dissatisfaction or opposition from stakeholders | Med. | Stakeholder Engagement Team (Group) | [7 empty] | Yes | Address concerns through communication and engagement | Stakeholder protest or demonstration | Initiate stakeholder dialogue | still conflicts persist among stakeholders
31 | Ethical # 2 Conflict of Interest | Compromised decision-making processes leading to suboptimal project outcomes. Damage to the project's reputation and integrity. Legal or ethical investigations resulting in delays or disruptions to project progress. | Med. | Med. | Med. | 5 | 5 | 25 | Avoid - should provide ethics training to all the parties | Ethical breaches or conflicting interests | Med. | Ethics Committee (Group) | [7 empty] | Yes | Investigate allegations, enforce conflict-of-interest policies | Conflict of interest reported | Conduct internal investigation | serious complaint from authorities
32 | Foundation settlement - Technical | Foundation layed getting settled unevenly, this will impact the structure adversly. | Med. | Med. | Med. | 3 | 9 | 27 | Mitigate - should conduct regular structural monitoring at every construction stage | The stress indicators showing higher values beyond threshold value | Med. | Engineering Team (Group) | [7 empty] | Yes | Form a rapid response team | still the values beyond threshold value | Foundation design has to be re-evaluated and changed | Still the settlement persists
33 | Soil Instability - Environmental | Instability of soil during excavation processes | Med. | Med. | Med. | 4 | 8 | 32 | Mitigate - soil analysis and testing has to be conducted | Soil instability observed during excavation processes | High | Engineering Team (Group) | Move Forward | 0.4 | -100 | -40 | 0.75 | -308000 | -231000 | Yes | Implementing stabilization techniques | triggers observed in the soil stability | Experts should conduct reassessment and change the excavation plan if required | The instability of soil persists
34 | Scope creep - Project management risk | If there occurs any unplanned expansion in the initially prepared scope of the project | Med. | Med. | Med. | 3 | 8 | 24 | Avoid - Invest adequate time in developing the scope for avoiding future changes | Any deviations required from the defined scope for the completion of the project. | Med. | Project Management Team (Group) | Move Forward | 0.3 | -50 | -15 | 0.8 | -10000000 | -8000000 | Yes | Stregthening the change control process | observing scope deviations | Thorough scope review ghas to be carried out | Issues of scope screep persists
35 | Land pollution - Environmental | During the construction processes and material storage stages there are chances of occurrence of contamination of land. | Med. | Med. | Med. | 5 | 5 | 25 | Mitigate- proper waste management processes are required | Receiving violation notices for improper disposal of construction wastes on site | Med. | Environmental Compliance Officer (Individual) | Move forward | 0.7 | -300 | -210 | 0.7 | -300000 | -210000 | Yes | Implementing best waste mangement processes | Contamination of soil and water | Crrying out soil remedial measures | Still the water and soil found polluted
36 | Challenges in technology integration - Technological | This inclues the difficulties faced while intergrating various new technologies for the project completion. | Med. | Med. | Med. | 5 | 5 | 25 | Mitigate - Proper trainings provided to the construction teams by conducting technology assessments | Observing inefficiencies in the construction processes | Med. | Engineering Team (Group) | Move Forward | 0.5 | -200 | -100 | 0.7 | -1500000 | -1050000 | Yes | Forming a rapid response team for taking immediate actions | Observed triggers in the technology issues | Adjusting the technology integration methods | Still finding difficult to manage different technologies simultaneously
37 | Noise pollution - Environmental | Excessive uncontrolled noise generation during the operations of construction work. | High | Med. | High | 7 | 6 | 42 | Avoid - implement noise reduction measures | Any violations observed in the noise level regulations | Med. | Environmental Compliance Officer (Individual) | Mov forward | 0.7 | -700 | -490 | 0.5 | -130000 | -65000 | Yes | Implementing noise reduction measures | Complaints form the community | Adjusting the timeline of work accordingly | Noise violation notices from the authorities
38 | Fluctuations in Currency conversions - Economical | Project costs might be impacted by any unpredicted currency exchange rates | Low | High | Med. | 3 | 7 | 21 | Transfer- Consider establishing financial reserves while preparing the scope | Any changes observed in the currency conversion rates | Med. | Finance Department (Group) | Move forward | 0.5 | -100 | -50 | 0.9 | -1000000 | -900000 | Yes | Financial monitoring at regular intervals - better financial stratergies | Currency fluctuations effecting the funding of project | Adjusting the project budget if required | Still shortage of funding persists
39 | Deforestation - Environmental | During the construction processes there are chances of cutting of trees | Med. | Med. | Med. | 6 | 6 | 36 | Avoid - Conducting environmental impact assessments | Receiving violation notices | Med. | Environmental Compliance Officer (Individual) | Move forward | 0.7 | -240 | -168 | 0.4 | -100000 | -40000 | Yes | Chnages in the construction practices | Adverse effects in local vegetation | Environment friendly construction practices | Concerns of local authorities persists
40 | Material quality issues- Quality control risks | Using low quality materials for construction can impact the strength of structures | Med. | High | High | 6 | 8 | 48 | Mitigate - Should have strict quality constrol measures | Failures occurong during material testing | High | Engineering Team (Group) | Move forward | 0.5 | -450 | -225 | 0.8 | -500000 | -400000 | Yes | Replacement of low quality materials | Quality test failures | Implementing more efficient and strict quality control measures | Negative comments on quality control review
Opputunity Risks
1 | Strong collaboration within stakeholders | Effective collaboration among stakeholders fosters effective communication, efficient decision making and lead to collectively working for the goal. | Med. | High | High | 5 | 8 | 40 | Enhance - Identify all the stakeholders, develop a clear communication stratergy,always welcome feedbacks and ideas from the stakeholders | Diverse sakeholder groups may trigger the ability to agree upon a signle way of approach. There might be difference in opinions. Difficult to manage the complex variety of stakeholders involved. | High | Project manager and stake holder engagement teams. | Move Forward | 0.8 | 807 | 645.6 | 0.8 | 4380000 | 3504000 | Enhance | Enhance the stakeholder relationships by building strong communication channels | Any challenges faced in communication channels | Build a communication management plan among stakeholders | Any disputes occur while stakeholder collaboration
2 | Advanced construction technologies | Adoption of advanced construction technologies will increase the efficiency of the project with improved project outcomes and shall result in potential cost savings. | High | High | High | 8 | 8 | 64 | Enhance - Do a reasearch on the available advanced technologies in construction industry. Conduct meetings with the stakeholders including technology experts and analyse all the technologies that can be used for this project considering the budget. Incorporate the selected approppriate innovate technologies to the project. | Innovative technologies improves the efficiency and cost effectiveness of the project. Thre can be shortages in skilled labours for using advanced technologies. | Med. | Project manager and design engineer | Move Forward | 0.8 | 807 | 645.6 | 0.8 | 8760000 | 7008000 | Exploit | Ugrade the construction practices using todays industry advancess | not showing efficiency while project prgresses | Consult technology experts for implementing new practices efficiently | Extended time for implementing new practices
3 | Development of Active Transportation Connection Implementation of new pedestrian and cyclist pathways | Reduced traffic congestion Improved air quality, enhanced public health | Med. | High | High | 5 | 9 | 45 | Exploit | Urban development initiatives | High | Project Manager (Individual), Engineering Team (Group) | Yes | 0.5 | 30 | 15 | 0.5 | 40000 | 20000 | Yes | Public engagement, collaboration with local authorities | Approval of project funding | Seek alternative funding sources | Initial design not approved
4 | Intersection Improvements at Central Avenue Installation of traffic lights and pedestrian crossings | Improved traffic flow and Enhanced pedestrian safety, reduced accidents | High | High | High | 8 | 9 | 72 | Enhance | Traffic congestion issues | High | Traffic Engineer (Individual), Construction Team (Group) | Yes | 0.75 | 45 | 33.75 | 0.75 | 100000 | 75000 | Yes | Traffic flow analysis, stakeholder engagement | Funding secured | Seek public-private partnerships | Contractor default on project
5 | Social # 1 Infrastructure Development | Job creation, improved transportation networks and Enhanced regional development | Med. | High | High | 5 | 8 | 40 | Exploit | Population growth and urbanization | High | Urban Planner (Individual), City Council (Group) | Yes | 0.5 | 60 | 30 | 0.5 | 120000 | 60000 | Yes | Community engagement, public-private partnerships | Funding secured | Seek additional funding sources | Delayed approvals from regulatory authorities
6 | Technological # 1 Technological Advancements | Increased efficiency and safety. Reduced construction time and costs. | Med. | High | High | 6 | 9 | 54 | Exploit | Technological advancements in the industry | High | Technology Manager (Individual), R&D Team (Group) | Yes | 0.75 | 90 | 67.5 | 0.75 | 150000 | 112500 | Yes | Research and development, testing phase | Prototype successfully tested | Explore alternative technologies | Insufficient research funding
7 | Social #2 Community Engagement | Enhanced community participation, Improved project acceptance | Med. | Med. | Med. | 5 | 9 | 45 | Exploit | Community concerns and interests | High | Community Engagement Officer (Individual), Public Relations Team (Group) | Yes | 0.5 | 20 | 10 | 0.5 | 20000 | 10000 | Yes | Open forums, public consultations | Positive feedback from community | Adjust project plans based on community feedback | Lack of community engagement
8 | Economic #3 Cost-saving Measures | Reduced project expenses, Improved financial efficiency | High | High | High | 9 | 9 | 81 | Enhance | Budget constraints | High | Finance Department (Group), Project Manager (Individual) | Yes | 0.9 | 30 | 27 | 0.9 | 80000 | 72000 | Yes | Implement cost-saving strategies, renegotiate contracts | Successful negotiation of lower costs | Seek alternative suppliers | Failure to negotiate favorable terms
9 | Environmental #3 Sustainability Initiatives | Environmental conservation, Long-term ecological benefits | Med. | High | High | 6 | 9 | 54 | Exploit | Environmental regulations, Corporate sustainability goals | High | Environmental Compliance Officer (Individual), Sustainability Committee (Group) | Yes | 0.5 | 45 | 22.5 | 0.5 | 70000 | 35000 | Yes | Implement sustainable practices, energy-efficient technologies | Successful adoption of green initiatives | Educate staff on sustainable practices | Lack of stakeholder buy-in
10 | Political #3 Public Support | Political backing, Regulatory approvals, Reduced bureaucratic hurdles | High | High | High | 8 | 9 | 72 | Enhance | Political landscape, Regulatory requirements | High | Government Relations Manager (Individual), Legal Team (Group) | Yes | 0.75 | 60 | 45 | 0.75 | 90000 | 67500 | Yes | Lobbying efforts, stakeholder engagement | Public endorsement of project | Legal challenge to project approval | Lack of political support
11 | Political # 3 Stakeholder Collaboration | Enhanced stakeholder relations, Improved project governance | High | High | High | 8 | 9 | 72 | Enhance | Stakeholder opposition | High | Government Relations Manager (Individual), Stakeholder Engagement Team (Group) | Yes | 0.75 | 40 | 30 | 0.75 | 100000 | 75000 | Yes | Stakeholder meetings, mediation efforts | Consensus reached with stakeholders | Engage in alternative dispute resolution | Persistent opposition from stakeholders
12 | Technological # 3 Automation | Increased productivity, Streamlined processes | High | High | High | 7 | 9 | 63 | Enhance | Manual labor inefficiencies | High | Technology Manager (Individual), Operations Team (Group) | Yes | 0.9 | 25 | 22.5 | 0.9 | 120000 | 108000 | Yes | Automation implementation, training programs | Successful integration of automation systems | Explore advanced automation technologies | Resistance from workforce
13 | Environmental # 3 Green Infrastructure | Sustainable development, Environmental conservation | Med. | High | High | 6 | 9 | 54 | Exploit | Environmental protection initiatives | High | Environmental Compliance Officer (Individual), Engineering Team (Group) | Yes | 0.6 | 50 | 30 | 0.6 | 90000 | 54000 |  | Implement green infrastructure practices | Successful implementation of green initiatives | Explore alternative eco-friendly options | Resistance from stakeholders
14 | Social # 3 Workforce Training | Skilled labor force, Increased productivity | Med. | Med. | Med. | 4 | 6 | 24 | Enhance | Lack of skilled workforce | High | Human Resources Department (Group), Operations Manager (Individual) | Yes | 0.6 | 30 | 18 | 0.6 | 60000 | 36000 | Yes | Training programs, skill development initiatives | Successful completion of training programs | Hire skilled workers | Inadequate training facilities
34 | Note : Considering impact days between 2022 April to 2023 April, which is the construction period of this project. The total budget of this project is 87.6million. The cost impact is calculated based on this value. |  | Med. | High | High | 0 | 0 | 0 |  |  | High
13 |  |  | Med. | High | High | 0 | 0 | 0 |  |  | Med.
16 |  |  | Med. | Med. | Med. | 0 | 0 | 0 |  |  | Med.
22 |  |  | Med. | Med. | Med. | 0 | 0 | 0 |  |  | Med.
28 |  |  | Med. | Med. | Med. | 0 | 0 | 0 |  |  | Med.
30 |  |  | Med. | Med. | Med. | 0 | 0 | 0 |  |  | Med.
15 |  |  | Low | High | Med. | 0 | 0 | 0 |  |  | Med.
25 |  |  | Low | Med. | Low | 0 | 0 | 0 |  |  | Med.
26 |  |  | Med. | Med. | Med. | 0 | 0 | 0 |  |  | Med.
14 |  |  | Med. | Low | Low | 0 | 0 | 0 |  |  | Med.
19 |  |  | Low | High | Med. | 0 | 0 | 0 |  |  | High
23 |  |  | Low | Med. | Low | 0 | 0 | 0 |  |  | Low
24 |  |  | Low | Med. | Low | 0 | 0 | 0 |  |  | Med.
32 |  |  | Low | Low | Low | 0 | 0 | 0 |  |  | Low
17 |  |  | Low | Low | Low | 0 | 0 | 0 |  |  | Med.
18 |  |  | Low | Low | Low | 0 | 0 | 0 |  |  | Low
20 |  |  | Low | Low | Low | 0 | 0 | 0 |  |  | Low
31 |  |  | Low | Low | Low | 0 | 0 | 0 |  |  | Low
21 |  |  | Low | Low | Low | 0 | 0 | 0 |  |  | Low
33 |  |  | Low | Low | Low | 0 | 0 | 0 |  |  | Low
[5 empty] | Average |  |  | 27.3649
*List Values - Do Not Delete
[15 empty] | Prob | Imp.
[15 empty] | High | High
[15 empty] | Med. | Med.
[15 empty] | Low | Low
Reason for Moving Forward
The Probability and Imapct criteria lie in the range of 1-3 if low, 4-6 if Medium and 7-9 if high. We have an overall risk register avgerage P x I Score of 23. We have decided to keep 23 as our threshold for analysing further risk(moving forward). We have reached to a consensus that not much can go wrong with a score range of 20-28 as mitigation is not a very difficult task. Hence we have a score of 23 as our threshold for this project.
|  |  | Prob vs Impact |  | = Rank
|  |  | High | High | High
|  |  | Med. | High | High
|  |  | High | Med. | High
|  |  | Low | High | Med.
|  |  | Med. | Med. | Med.
|  |  | High | Low | Med.
|  |  | Low | Med. | Low
|  |  | Med. | Low | Low
|  |  | Low | Low | Low
Risk Response and Mitigation Strategies
Avoid: Revise approach to avoid the risk in the first place.
Transfer: Transfer the risk to others via contracts, insurance, etc.
Mitigate: Revise approach to reduce risk probability/ impact.
Accept: Accept the risk and develop contingencies.
Corporate Level Risk Rankings
Risk Response and Mitigation Strategies
Avoid: Revise approach to avoid the risk in the first place.
Transfer: Transfer the risk to others via contracts, insurance, etc.
Mitigate: Revise approach to reduce risk probability/ impact.
Accept: Accept the risk and develop contingencies.
Corporate Level Risk Rankings

## Impact & Probability
Risk Response and Mitigation Strategies
Avoid: Revise approach to avoid the risk in the first place.
Transfer: Transfer the risk to others via contracts, insurance, etc.
Mitigate: Revise approach to reduce risk probability/ impact.
Accept: Accept the risk and develop contingencies.
Corporate Level Risk Rankings

## Time Budget Calculations
Estimating Form
Orignal estimate |  |  |  | Time | Cost
Risk identification, and qualititave and quantitative risk anaylsis result in :
Original Risks | Probability | Impact |  | Expected monetary value
|  | Time in days | Cost in $ | Time in days | Cost in $
Unforeseen Weather Conditions | 0.6 | -540 | -120000 | -324 | -72000
Regulatory Approval Delays | 0.8 | -90 | -250000 | -72 | -200000
Labor Shortages | 0.4 | -50 | -50000 | -20 | -20000
Equipment failures | 0.7 | -40 | -150000 | -28 | -105000
Supply Chain Disruptions | 0.5 | -90 | -150000 | -45 | -75000
Soil Instability - Environmental | 0.4 | -100 | -308000 | -40 | -123200
Scope creep - Project management risk | 0.3 | -50 | -10000000 | -15 | -3000000
Land pollution - Environmental | 0.7 | -300 | -300000 | -210 | -210000
Challenges in technology integration - Technological | 0.5 | -200 | -1500000 | -100 | -750000
Noise pollution - Environmental | 0.7 | -700 | -130000 | -490 | -91000
Fluctuations in Currency conversions - Economical | 0.5 | -100 | -1000000 | -50 | -500000
Deforestation - Environmental | 0.7 | -240 | -100000 | -168 | -70000
Material quality issues- Quality control risks | 0.5 | -450 | -500000 | -225 | -250000
|  |  |  | -1787 | -5466200
|  |  |  | -2950 | -14558000
|  |  |  | -4737 | -20024200
|  |  |  | Time in days | Cost in $
Opportunity risks
| Probability | Impact |  | EMV
|  | Time | Cost in $ | Time in Days | Cost in $
Strong collaboration within stakeholders | 0.8 | 807 | 4380000 | 645.6 | 3504000
Advanced construction technologies | 0.8 | 807 | 7008000 | 645.6 | 5606400
Development of Active Transportation Connection Implementation of new pedestrian and cyclist pathways | 0.5 | 30 | 40000 | 15 | 20000
Intersection Improvements at Central Avenue Installation of traffic lights and pedestrian crossings | 0.75 | 45 | 100000 | 33.75 | 75000
Social # 1 Infrastructure Development | 0.5 | 60 | 120000 | 30 | 60000
Technological # 1 Technological Advancements | 0.75 | 90 | 150000 | 67.5 | 112500
Social #2 Community Engagement | 0.5 | 20 | 20000 | 10 | 10000
Economic #3 Cost-saving Measures | 0.9 | 30 | 80000 | 27 | 72000
Environmental #3 Sustainability Initiatives | 0.5 | 45 | 70000 | 22.5 | 35000
Political #3 Public Support | 0.75 | 60 | 90000 | 45 | 67500
Political # 3 Stakeholder Collaboration | 0.75 | 40 | 100000 | 30 | 75000
Technological # 3 Automation | 0.9 | 25 | 120000 | 22.5 | 108000
Environmental # 3 Green Infrastructure | 0.6 | 50 | 90000 | 30 | 54000
Social # 3 Workforce Training | 0.6 | 30 | 60000 | 18 | 36000
0
|  |  |  | 1642.45 | 9110400
Final project estimate |  |  |  | 1642.45 | 9110400
Savings due to risk management: |  |  |  | -3094.55 | -10913800

## risk matrix categorization
Risk Matrix Categorization
Sl no | Range | Type
1 | 1 to 3 | Low Risk
2 | 4 to 6 | Medium Risk
3 | 7 to 9 | High Risk

## Team members
Team Members | Student ID
Divya Mathew | 1192361
Roshna Mary | 1207683
S M Rakibul Basher | 1168369
Gihan Shamike Liyanage | 1142109

## References
References
Adelaide Street North – CP Grade Separation ("Adelaide Underpass"). (2023). Retrieved from getinvolved.london.ca: https://getinvolved.london.ca/adelaide
Baxter, M. (2023). Adelaide Street underpass project a breath of fresh air for London residents. Retrieved from canada.constructconnect.com: https://canada.constructconnect.com/dcn/news/infrastructure/2023/09/adelaide-street-underpass-project-a-breath-of-fresh-air-for-london-residents
(n.d.). City of London ¦ Adelaide Street North - Canadian Pacific Railway Grade Separation Class Environmental Assessment Study Report. City of London.
CityofLondonOntario. (2022). Adelaide Underpass Construction Public Update Meeting. Retrieved from youtube.com: https://www.youtube.com/watch?v=hmVhqVJR8Wc
Garfield Dales, P. D. (2022). Contract Award: Tender RFT 21-97 Adelaide Street North CPR. London, ON: City of London.
Module 2 - MGMT 6062 - PROJECT RISK AND QUALITY. (2023). Retrieved from fanshaweonline.ca: https://www.fanshaweonline.ca/d2l/le/content/1558568/viewContent/14845266/View
Module 3 MGMT 6062 Identify Risks & Opportunities. (2023). Retrieved from fanshaweonline.ca: https://www.fanshaweonline.ca/d2l/le/content/1558568/viewContent/14069186/View
Module 4 MGMT 6062 Qualitative Risk & Opportunity Analysis. (2023). Retrieved from fanshaweonline.ca: https://www.fanshaweonline.ca/content/23F/1558568-MGMT-6062-(01)-24W/PowerPoints/Module%204%20Qualitative%20risk%20analysis.pdf?isCourseFile=true&ou=1558568
Module 5 MGMT 6062 Quantitative Risk & Opportunity Analysis. (2023). Retrieved from fanshaweonline.ca: https://www.fanshaweonline.ca/content/23F/1558568-MGMT-6062-(01)-24W/PowerPoints/Module%205%20Quantitative%20risk%20analysis.pdf?isCourseFile=true&ou=1558568
Module 6 MGMT 6062 Plan Risk & Opportunity Responses. (2023). Retrieved from fanshaweonline.ca: https://www.fanshaweonline.ca/d2l/le/content/1558568/viewContent/14069196/View
Prastowo, T. &. (2020). Risk management on railway projects: A literature view. Facta universitatis - series: Architecture and Civil Engineering.
Simon, A. (2023). Adelaide Street North to be closed as of Wednesday for underpass rail lift. Retrieved from globalnews.ca: https://globalnews.ca/news/9912091/adelaide-street-north-closure-london/
Stacey, M. (2022, Dec). The big dig: An inside look at the massive Adelaide underpass project. Retrieved from lfpress.com: https://lfpress.com/news/local-news/the-big-dig-an-inside-look-at-the-massive-adelaide-underpass-project
Stacey, M. (2023). Sticker shock: Cost of Adelaide Street underpass balloons by 50%. Retrieved from lfpress.com: https://lfpress.com/news/local-news/sticker-shock-cost-of-adelaide-street-underpass-balloons
The official website for the City of London, O. (2022). Adelaide Street North Underpass. Retrieved from london.ca: https://london.ca/projects/adelaide-street-north-underpass
Vincenzo Marchettaa, A. D. (2022). A methodology for introducing the impact of risk analysis in local railways improvements decisions.