## List Of Customers
List of Customers
External Customers
Residents
Commuters
Cyclists
Pedestrians
Local businesses
Emergency services
Internal Customers
City of London's Engineering Department
Construction contractors
Government of Canada and Province of Ontario
City of London's maintenance crews
City of London's Transportation Department
Canadian Pacific Railway (CPR)
Hidden Customers
Environmental and Conservation Agencies
Historical preservation groups
Utilities companies
London Transit users
Future generations
| Priority | Customer | Reason
| 1 | Residents | Residents are directly impacted by the construction of the underpass as they live in the vicinity and will likely use the infrastructure. Their safety, convenience, and quality of life are paramount considerations. Prioritizing residents ensures that their needs and concerns are addressed, fostering community support and satisfaction with the project.
| 2 | Commuters | Commuters represent a significant user group who rely on efficient transportation infrastructure to commute to work, school, or other destinations. Prioritizing commuters ensures that the underpass contributes to smoother traffic flow, reduces congestion, and improves overall transportation efficiency. Their satisfaction is crucial for the success of the project, as it affects daily mobility and productivity.
| 3 | City of London's Transportation Department | The Transportation Department plays a key role in urban mobility and transportation planning. Prioritizing their needs ensures alignment with citywide transportation goals, safety standards, and traffic management strategies. Their input is essential for optimizing the design and functionality of the underpass within the broader transportation network.
| 4 | Local businesses | Local businesses are stakeholders whose operations may be impacted by the construction and operation of the underpass. Prioritizing local businesses involves mitigating potential disruptions, ensuring access to customers and suppliers, and minimizing economic impacts during and after construction. Their support and cooperation are vital for maintaining economic vitality in the area.
| 5 | Emergency services | Emergency services, including police, fire, and medical responders, rely on efficient transportation routes to reach their destinations quickly and safely. Prioritizing emergency services involves ensuring unimpeded access, adequate response times, and emergency preparedness measures. Their input is critical for designing infrastructure that supports emergency response efforts and enhances public safety.

## Customer Priortizing
L-Shaped Matrix | Residents | Commuters | Cyclists | Pedestrians | Local businesses | Emergency services | City of London's Engineering Department | Construction contractors | Government of Canada and Province of Ontario | City of London's maintenance crews | City of London's Transportation Department | Canadian Pacific Railway (CPR) | Environmental and Conservation Agencies | Historical preservation groups | Utilities companies | London Transit users | Future generations | Row Total | Relative Decimal Value
Residents |  | 5 | 5 | 5 | 1 | 0.5 | 0.1 | 0.1 | 0.1 | 0.5 | 0.1 | 0.1 | 1 | 1 | 0.5 | 0.5 | 1 | 21.5 | 0.039933 | Scoring Key | Row Total
Commuters | 0.2 |  | 1 | 1 | 0.5 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.1 | 0.1 | 5 | 5 | 0.5 | 0.5 | 1 | 15.8 | 0.029346 | 1 = Equally important | Sum of row scores
Cyclists | 0.2 | 1 |  | 1 | 0.5 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.1 | 0.1 | 5 | 5 | 0.5 | 1 | 1 | 16.3 | 0.030275 | 5 = More important | Grand Total
Pedestrians | 0.2 | 1 | 1 |  | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.1 | 1 | 1 | 1 | 0.5 | 0.5 | 10.3 | 0.019131 | 10 = Much more important | Sum of row totals
Local businesses | 1 | 2 | 2 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 1 | 14 | 0.026003 | 1/5 = Less important | Relative Decimal Value
Emergency services | 2 | 10 | 10 | 2 | 2 |  | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 5 | 10 | 1 | 5 | 1 | 52 | 0.096582 | 1/10 = Much less important | Row total divided by grand total
City of London's Engineering Department | 10 | 10 | 10 | 2 | 2 | 2 |  | 1 | 1 | 1 | 1 | 0.5 | 1 | 5 | 1 | 0.5 | 1 | 49 | 0.09101
Construction contractors | 10 | 10 | 10 | 2 | 2 | 1 | 1 |  | 1 | 1 | 1 | 0.5 | 1 | 5 | 1 | 1 | 0.5 | 48 | 0.089153
Government of Canada and Province of Ontario | 10 | 10 | 10 | 2 | 2 | 2 | 1 | 1 |  | 1 | 1 | 1 | 5 | 5 | 1 | 0.5 | 0.5 | 53 | 0.09844
City of London's maintenance crews | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 |  | 1 | 1 | 5 | 10 | 1 | 1 | 1 | 34 | 0.06315
City of London's Transportation Department | 10 | 10 | 10 | 2 | 2 | 2 | 1 | 1 | 1 | 1 |  | 0.5 | 5 | 10 | 0.5 | 1 | 1 | 58 | 0.10773
Canadian Pacific Railway (CPR) | 10 | 10 | 10 | 10 | 2 | 2 | 2 | 2 | 1 | 1 | 2 |  | 10 | 10 | 0.5 | 1 | 0.5 | 74 | 0.13744
Environmental and Conservation Agencies | 1 | 0.2 | 0.2 | 1 | 1 | 0.2 | 1 | 1 | 0.2 | 0.2 | 0.2 | 0.1 |  | 1 | 0.5 | 0.5 | 0.1 | 8.4 | 0.015602
Historical preservation groups | 1 | 0.2 | 0.2 | 1 | 1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 1 |  | 0.5 | 0.5 | 0.5 | 6.9 | 0.012816
Utilities companies | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 |  | 0.5 | 0.5 | 22 | 0.040862
London Transit users | 2 | 2 | 1 | 2 | 2 | 0.2 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 2 |  | 1 | 24.2 | 0.044948
Future generations | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 10 | 2 | 2 | 1 |  | 31 | 0.057578
Grand Total | [17 empty] | 538.4 | 1

## Requirements Prioritizing
Requirements Prioritization
The textbook (Rose) presents the Full Analytical Criteria Method (p50) for prioritizing requirements. For the Module 10 assignment, we will use a simplified approach with the following table. Rank each requirement from 1 to 10 where 10 is most important and 1 is least important. Provide justification for each evaluation. Identify priority ranking.
Importance: | 10 - Absolute requirement - the project cannot be successfully completed without this requirement
:
:
1 - Wish list item only
Requirement for the Adelaide Underpass | Importance (1-10) | Justification | Priority Ranking
Pedestrian Safety | 10 | Ensures the safety of pedestrians crossing the underpass | 1
Cyclist Convenience | 9 | Provides a smooth passage for cyclists | 2
Traffic Flow Efficiency | 9 | Ensures smooth traffic flow through the underpass | 3
Accessibility | 8 | Ensures accessibility for people with disabilities | 4
Adequate Lighting | 8 | Provides sufficient lighting for safety and visibility | 5
Minimal Environmental Impact | 7 | Minimizes disruption to the environment during construction and operation | 6
Aesthetics | 7 | Enhances the visual appeal of the underpass | 7
Noise Reduction | 6 | Minimizes noise pollution in the surrounding area | 8
Drainage Efficiency | 6 | Ensures effective drainage to prevent flooding
Durability | 5 | Ensures the structure's longevity and resilience
Emergency Accessibility | 5 | Provides emergency access to the underpass if needed
Integration with Surroundings | 5 | Blends seamlessly with the surrounding urban landscape
Maintenance Ease | 4 | Simplifies maintenance tasks for long-term upkeep
Clear Signage | 4 | Provides clear signage for navigation within the underpass
Bicycle Parking | 3 | Includes designated parking areas for bicycles
Green Space | 3 | Incorporates green spaces for recreational purposes

## Requirements Specifications
Requirements Specifications
| Requirements | Specifications
1 | Pedestrian Safety | Installation of pedestrian-friendly features such as well-marked crosswalks, tactile paving, and adequate lighting throughout the underpass. These specifications ensure that pedestrians can navigate the underpass safely, especially during low-light conditions or inclement weather, promoting pedestrian safety and accessibility.
2 | Cyclist Convenience | Dedicated bike lanes separated from vehicular traffic, bicycle parking facilities, and clear signage for cyclists. By providing designated lanes and parking, along with clear signage, cyclists are accommodated effectively, promoting convenience and encouraging cycling as a sustainable mode of transportation.
3 | Traffic Flow Efficiency | Multiple lanes for vehicular traffic, synchronized traffic signals, and efficient intersection design to minimize congestion. This specifications aim to optimize traffic flow, reduce delays, and improve overall traffic efficiency, ensuring smooth movement of vehicles through the underpass and minimizing potential traffic jams.
4 | Accessibility | ADA-compliant ramps, and tactile indicators for individuals with disabilities, ensuring barrier-free access to all areas of the underpass. By incorporating accessibility features, the underpass becomes inclusive, allowing people with disabilities to navigate the space independently and safely, promoting equality and accessibility for all.
5 | Adequate Lighting | High-quality LED lighting fixtures strategically placed to ensure uniform illumination and visibility throughout the underpass. Proper lighting enhances safety and visibility, especially during nighttime or inclement weather, reducing the risk of accidents and creating a welcoming environment for pedestrians and cyclists.
6 | Minimal Environmental Impact | Use of sustainable construction materials, implementation of stormwater management systems, and preservation of existing vegetation where possible. These aims to minimize disruption to the surrounding environment, reduce carbon footprint, and preserve natural resources, aligning with sustainable development goals and minimizing negative ecological impacts.
7 | Aesthetics | Architectural design elements, public art installations, and landscaping to enhance the visual appeal and cultural significance of the underpass. Incorporating aesthetic elements creates a visually pleasing and engaging space that contributes to the cultural identity of the community, fostering civic pride and enhancing the overall urban landscape.
8 | Noise Reduction | Sound barriers, acoustic panels, and noise-absorbing pavement materials to mitigate traffic noise and minimize disturbance to nearby residents. This aims to enhance the quality of life for nearby residents by reducing noise pollution, creating a more peaceful and comfortable living environment, and mitigating the negative effects of urban transportation on human health and well-being.

## References
References:
Adelaide Street North – CP Grade Separation ("Adelaide Underpass"). (2023). Retrieved from getinvolved.london.ca: https://getinvolved.london.ca/adelaide Baxter, M. (2023). Adelaide Street underpass project a breath of fresh air for London residents. Retrieved from canada.constructconnect.com: https://canada.constructconnect.com/dcn/news/infrastructure/2023/09/adelaide-street-underpass-project-a-breath-of-fresh-air-for-london-residents (n.d.). City of London ¦ Adelaide Street North - Canadian Pacific Railway Grade Separation Class Environmental Assessment Study Report. City of London. CityofLondonOntario. (2022). Adelaide Underpass Construction Public Update Meeting. Retrieved from youtube.com: https://www.youtube.com/watch?v=hmVhqVJR8Wc Garfield Dales, P. D. (2022). Contract Award: Tender RFT 21-97 Adelaide Street North CPR. London, ON: City of London. Prastowo, T. &. (2020). Risk management on railway projects: A literature view. Facta universitatis - series: Architecture and Civil Engineering. Simon, A. (2023). Adelaide Street North to be closed as of Wednesday for underpass rail lift. Retrieved from globalnews.ca: https://globalnews.ca/news/9912091/adelaide-street-north-closure-london/ Stacey, M. (2022, Dec). The big dig: An inside look at the massive Adelaide underpass project. Retrieved from lfpress.com: https://lfpress.com/news/local-news/the-big-dig-an-inside-look-at-the-massive-adelaide-underpass-project Stacey, M. (2023). Sticker shock: Cost of Adelaide Street underpass balloons by 50%. Retrieved from lfpress.com: https://lfpress.com/news/local-news/sticker-shock-cost-of-adelaide-street-underpass-balloons The official website for the City of London, O. (2022). Adelaide Street North Underpass. Retrieved from london.ca: https://london.ca/projects/adelaide-street-north-underpass