## Customer list worksheet
Customers List
Sl no | Customer | Category
1 | London city council | External
2 | Local business owners | External
3 | Local residents | External
4 | Transportation authority | External
5 | Project manager | Internal
6 | Architects and engineers | Internal
7 | Construction workers | Internal
8 | Procurement team | Internal
9 | Media | Hidden
10 | Future generation | Hidden
11 | City Planning Dept | Internal
12 | Construction Company | Internal
14 | Environmental Protection Agency | External
15 | Traffic Control Authority | External
16 | Project Stakeholders Committee | Internal
17 | Engineering Firm | Hidden
18 | Underground Utilities Company | External
20 | Project Finance Team | Internal
21 | Driver | External
22 | Nearby shopowners | External
23 | Supply chain team | Internal
24 | Utility service Providder | Hidden
25 | Emergency service provider | Hidden

## Customer prioritized worksheet
Criteria | London city council | Local business owners | Local residents | Transportation authority | Project manager | Architects and engineers | Construction workers | Procurement team | Media | Future generation | City Planning Dept | Construction Company | Environmental Protection Agency | Traffic Control Authority | Project Stakeholders Committee | Engineering Firm | Underground Utilities Company | Project Finance Team | Driver | Nearby shopowners | Supply Chain team | Utility Service Provider | Emergency service provider | Total (Row) | Relative decimal value
London city council |  | 10 | 5 | 1 | 0.1 | 0.2 | 0.2 | 1 | 10 | 1 | 1 | 0.2 | 1 | 0.1 | 1 | 0.1 | 0.2 | 0.2 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 32.3 | 0.02622
Local business owners | 0.1 |  | 1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 62.1 | 0.05041
Local residents | 0.2 | 1 |  | 1 | 0.1 | 0.1 | 0.1 | 0.1 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0.5 | 1 | 5 | 5 | 5 | 74.1 | 0.060151
Transportation authority | 1 | 5 | 1 |  | 0.2 | 0.2 | 0.2 | 0.2 | 10 | 10 | 5 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 64.8 | 0.052602
Project manager | 10 | 5 | 10 | 5 |  | 1 | 1 | 1 | 10 | 10 | 1 | 1 | 5 | 0.1 | 1 | 1 | 1 | 1 | 0.5 | 5 | 5 | 5 | 1 | 80.6 | 0.065427
Architects and engineers | 5 | 5 | 10 | 5 | 1 |  | 1 | 1 | 10 | 5 | 1 | 1 | 5 | 0.1 | 1 | 1 | 1 | 1 | 1 | 5 | 10 | 10 | 10 | 90.1 | 0.073139
Construction workers | 5 | 5 | 10 | 5 | 1 | 1 |  | 1 | 10 | 5 | 10 | 1 | 5 | 0.1 | 1 | 1 | 1 | 1 | 1 | 10 | 5 | 10 | 10 | 99.1 | 0.080445
Procurement team | 1 | 5 | 10 | 5 | 1 | 1 | 1 |  | 10 | 5 | 5 | 1 | 5 | 0.1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 58.1 | 0.047163
Media | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.2 | 5 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 0.1 | 0.1 | 0.1 | 0.5 | 0.1 | 51.9 | 0.04213
Future generation | 1 | 0.1 | 0.2 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 5 |  | 5 | 5 | 10 | 5 | 5 | 5 | 5 | 5 | 0.5 | 0.5 | 1 | 1 | 1 | 56.1 | 0.045539
City Planning Dept | 1 | 0.2 | 0.1 | 0.2 | 1 | 0.1 | 0.2 | 0.1 | 0.1 | 0.2 |  | 0.1 | 1 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.5 | 0.5 | 1 | 1 | 1 | 9 | 0.0073058
Construction Company | 1 | 0.2 | 0.1 | 0.2 | 5 | 1 | 1 | 1 | 0.1 | 0.2 | 5 |  | 1 | 0.2 | 0.2 | 1 | 1 | 1 | 1 | 5 | 5 | 10 | 10 | 50.2 | 0.04075
Environmental Protection Agency | 1 | 0.1 | 0.1 | 0.2 | 1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 5 | 0.1 |  | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.5 | 0.5 | 10.4 | 0.0084422
Traffic Control Authority | 0.2 | 0.1 | 0.1 | 1 | 0.1 | 1 | 0.1 | 1 | 0.1 | 0.1 | 5 | 0.1 | 1 |  | 1 | 0.1 | 5 | 5 | 1 | 5 | 10 | 10 | 10 | 57 | 0.04627
Project Stakeholders Committee | 1 | 0.1 | 0.1 | 0.2 | 1 | 1 | 0.1 | 1 | 0.1 | 0.1 | 5 | 0.1 | 1 | 0.2 |  | 0.1 | 1 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 17.1 | 0.013881
Engineering Firm | 10 | 0.1 | 0.1 | 0.1 | 1 | 1 | 0.1 | 1 | 0.1 | 0.1 | 5 | 1 | 10 | 1 | 1 |  | 1 | 1 | 0.1 | 0.5 | 5 | 5 | 1 | 45.2 | 0.036691
Underground Utilities Company | 1 | 0.1 | 0.1 | 0.1 | 1 | 1 | 0.1 | 0.1 | 0.1 | 0.1 | 5 | 0.1 | 1 | 0.2 | 1 | 1 |  | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 17 | 0.0138
Project Finance Team | 5 | 0.1 | 0.1 | 0.1 | 1 | 1 | 0.1 | 1 | 0.1 | 0.1 | 5 | 0.1 | 5 | 0.2 | 1 | 1 | 1 |  | 1 | 5 | 5 | 5 | 5 | 42.9 | 0.034824
Driver | 10 | 10 | 1 | 1 | 1 | 1 | 1 | 10 | 5 | 5 | 5 | 10 | 1 | 10 | 5 | 5 | 5 | 10 |  | 5 | 10 | 10 | 5 | 96 | 0
Nearby shopowners | 0.1 | 1 | 1 | 5 | 10 | 1 | 5 | 10 | 0.5 | 1 | 1 | 5 | 5 | 0.1 | 0.1 | 5 | 1 | 1 | 1 |  | 5 | 5 | 5 | 53.8 | 0.043672
Supply chain team | 10 | 5 | 1 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 5 | 10 | 10 | 1 | 0.1 | 0.1 | 5 | 10 | 1 | 1 |  | 1 | 1 | 67.2 | 0.05455
Utility service Providder | 1 | 1 | 5 | 10 | 1 | 0.5 | 0.1 | 1 | 5 | 5 | 5 | 1 | 1 | 0.1 | 0.1 | 0.5 | 1 | 0.5 | 1 | 1 | 1 |  | 1 | 42.8 | 0.034743
Emergency service provider | 1 | 5 | 5 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 5 | 5 | 10 |  | 54.1 | 0.043916
TOTAL | [23 empty] | 1231.9 | 1
[6 empty] | Scoring key | Row Total
[6 empty] | 1=Equally important | Sum of row scores
[6 empty] | 5= More important | Grand Total
[6 empty] | 10= Much more important | Sum of row totals
[6 empty] | 1/5 = Less important | Relative decimal value
[6 empty] | 1/10=Much less important | Row total divided by grand total

## Requirements priority worksheet
Requirements priority sheet
Customers (Rating 0 to 10)
| Sl no |  | London city council | Project manager | Architects and engineers | Construction workers | Procurement team | Total Row | Relative Decimal value | Priority | Specification | Rationale
Requirements | 1 | Safety masure during construction process | 3 | 10 | 8 | 10 | 4 | 35 | 0.039773 | 2 | Implement safety protocol throughout the construction processes. Make sure to provide safety training sessions to all workers and appoint safety offcicers on site for regular monitoring. Safety measures has to be conducted incomplaince with Occupational Health and Safety Act regulations | Priotitising safety measures is to protect the health and well-being of workers, contractors, and the public. This is to the risk of accidents, injuries, and fatalities can be minimized, ensuring a safe working environment.
| 2 | Minimizing disruption in traffic | 6 | 9 | 5 | 8 | 2 | 30 | 0.034091 |  | Prepare a traffic management plan that includes alternative routes, temporary traffic controls, and clear signage. Manage construction activities to minimize road closures and avoid peak traffic hours. | Minimising disruptions are crucial to avoid inconvinience to the pedestrians and local residents. Effective traffic managemnet stratergies has to be implemented to take care of smooth flow of traffic.
| 3 | Minimize ecological impact | 7 | 9 | 8 | 5 | 3 | 32 | 0.036364 | 5 | EMA has to be carried out before construction to understand the ecological impacts. | This is to protect the sensitive eco system, wild habitats and water quality of the surrounding region.
| 4 | Protect existing underground utility infrastructures | 1 | 9 | 9 | 10 | 3 | 32 | 0.036364 | 6 | Communicate with the utility providers. Understand the location of underground utilities before excavation processes. | Avoiding damges to the existing utility infrastructures is necessary to avoid utility disruptions. This is to minimise the risk and delays of essential services to the region.
| 5 | Follow the project timelime with minimal variations | 2 | 10 | 5 | 10 | 10 | 37 | 0.042045 | 1 | The project timeline has to be prepared in detail and followed striclty. | This is necessary to ensure the timely completion of the project and avoid the cost overruns. This is essential for the project success.
| 6 | Availability of materials on time | 2 | 7 | 2 | 4 | 10 | 25 | 0.028409 |  | Should have a detailed project procurement schedule. Proper communication with the suppliers is essential for timely delivery of materials. | This is essential for the timely completion of the project. Any delays in the delivery of materials will increase the cost of the project and with negatively impact the project.
| 7 | Meeting material quality standard | 1 | 9 | 7 | 4 | 8 | 29 | 0.032955 |  | Materials quality should be as per the regulations and standards. Quality checks has to be carried out before use. | This is to ensure the safety and durability of the work conducted. By adhering with the standards, the project can achieve the desired success.
| 8 | Strictly following the project budget | 3 | 10 | 5 | 8 | 8 | 34 | 0.038636 | 3 | Should have a detailed project budget. This has to be closely monitored throughout the project lifecycle. | The project budget has to be strictly followed for the sustainability and success of the project.
| 9 | Community engagements | 8 | 7 | 1 | 1 | 1 | 18 | 0.020455 |  | Should establish community engagement plants for proper collaboration with all the stakeholders. | This is essential to foster positive relationship and trust among the stakeholders.
| 10 | Using sustainable construction materials | 2 | 9 | 8 | 3 | 9 | 31 | 0.035227 | 8 | Follow LEED construction standards. Use recyclable materials to minimize waste. | This is to minimize the impacts to environment. Thereby reducing the carbob footprint.
| 11 | Uisng innovative construction techniques | 2 | 10 | 10 | 1 | 1 | 24 | 0.027273 |  | Use modern innovative technologies for increasing the productivity and systainability. | This is to improve the efficiency of the project.
| 12 | Minimising noise pollution while construction practices | 5 | 9 | 9 | 7 | 3 | 33 | 0.0375 | 4 | Implement noise control measures such as sound barriers and conducting construction at off peak hours etc | This is to avoid publich complaints, health issues and legal liabilities.
| 13 | Accesssibility of emergency vehicles when in need | 7 | 6 | 2 | 3 | 4 | 22 | 0.025 |  | Ensure clear routes for emergency vehicles during the construction | This is to ensure timely response incase of any emergencies.
| 14 | Following structural standards | 1 | 5 | 10 | 4 | 5 | 25 | 0.028409 |  | Structural standards has to be followed. Design is based on Canadian Highway Bridge Design Code to meet the standards. | This is to ensure safety, reliability and durability of the structures being constructed.
| 15 | Preserving natural habitats | 6 | 8 | 9 | 3 | 3 | 29 | 0.032955 |  | Conduct environmental impact assessments to protect the natural habitats. | This is carried out to maintain the ecilogical balance. And to take approppriate measures if we identify any threats to natual environment.
| 16 | Availability of equipments | 2 | 10 | 4 | 3 | 10 | 29 | 0.032955 |  | should mainatin inventory of construction equipments | This is to make sure the equipments are available on time when in need. Otherwise it may delay the project.
| 17 | Minimal disruption of local businesses | 7 | 9 | 3 | 8 | 4 | 31 | 0.035227 | 7 | Project timeline has to be planned in such a way causing minimal disruption to the local businesses. | This is to have community support for the construction purposes. Proper collboration of community is necessary for the success of the project.
| 18 | Traffic control | 9 | 10 | 8 | 7 | 6 | 40 | 0.045455 |  | Traffic lifht and other traffic sign and signal helps to control traffic. Moreover strict traffic rules are very crucial | proper traffic control always give better road experience and reduce accident risk and save times.
| 20 | Noice Minimization | 5 | 8 | 3 | 9 | 4 | 29 | 0.032955 |  | high-grade, durable materials for traffic control devices, barriers, and infrastructure components to ensure longevity, reliability, and performance. | High-grade materials offer enhanced durability, resistance to wear and tear, and prolonged lifespan, reducing maintenance needs and lifecycle costs while ensuring consistent performance and safety.
| 21 | Overall Sfety | 9 | 8 | 7 | 6 | 5 | 35 | 0.039773 |  | To reduce traffic-related noise pollution inside and around the underpass, use quiet pavement technology, sound-absorbing materials, and noise barriers. | Noise minimization enhances the comfort and well-being of nearby residents, reduces environmental impact, and contributes to a more pleasant and livable urban environment.
| 22 | Eco friendly | 8 | 7 | 6 | 5 | 4 | 30 | 0.034091 |  | Incorporate safety features such as guardrails, crash barriers, anti-skid surfaces, and advanced traffic management systems to mitigate risks, prevent accidents, and ensure the overall safety of motorists, pedestrians, and cyclists. | Prioritizing safety through effective design, engineering, and implementation of safety measures is paramount to protect all users of the underpass and reduce the likelihood of accidents, injuries, and fatalities.
| 23 | Substitution Road | 2 | 3 | 4 | 5 | 6 | 20 | 0.022727 |  | Adopt sustainable construction practices, utilize recyclable and low-carbon footprint materials, incorporate green infrastructure (e.g., permeable pavements, rain gardens), and implement energy-efficient lighting and traffic control systems to minimize environmental impact and promote ecological sustainability. | Eco-friendly practices and materials reduce the project's carbon footprint, conserve natural resources, mitigate climate change impacts, and enhance the overall environmental performance and sustainability of the underpass.
| 24 | Strict timephase | 3 | 4 | 5 | 6 | 7 | 25 | 0.028409 |  | Design and construct a substitution road or alternative route to divert traffic during construction, maintenance, or emergencies to minimize disruptions, congestion, and inconvenience for motorists and other road users. | Providing a substitution road or alternative route ensures continuous traffic flow, reduces delays, improves accessibility, and maintains transportation efficiency during construction activities, maintenance operations, or unforeseen events.
| 25 | High Grade Material | 6 | 7 | 5 | 4 | 3 | 25 | 0.028409 |  | Implement a strict time-phase schedule and traffic management plan to coordinate construction activities, lane closures, detours, and traffic control measures effectively, ensuring minimal disruptions, optimized traffic flow, and adherence to project timelines. | Adhering to a strict time-phase schedule minimizes construction-related disruptions, reduces inconvenience for motorists, businesses, and residents, and facilitates efficient project management, coordination, and completion within the stipulated timeframe.
| 26 | Proper signals and signs | 7 | 6 | 2 | 1 | 3 | 19 | 0.021591 |  | Install clear, visible, and standardized traffic signals, signs, markings, and information boards following applicable regulatory guidelines, standards, and best practices to guide, inform, and manage traffic safely and effectively within the underpass and surrounding areas. | Proper signals and signs are essential for communicating rules, regulations, directions, and warnings to motorists, cyclists, and pedestrians, facilitating safe, orderly, and efficient traffic movement, navigation, and compliance within the underpass and associated roadways.
| 27 | After construction maintanance | 2 | 3 | 4 | 5 | 2 | 16 | 0.018182
| 28 | Cost efficiency | 3 | 1 | 2 | 5 | 6 | 17 | 0.019318
| 29 | Proper ligthning | 5 | 4 | 3 | 2 | 1 | 15 | 0.017045
| 30 | Local economy friendly | 5 | 4 | 3 | 5 | 1 | 18 | 0.020455
| 31 | Pavement and cyclist way | 8 | 7 | 6 | 5 | 4 | 30 | 0.034091
| 32 | Emergency facilities | 6 | 5 | 4 | 3 | 3 | 21 | 0.023864
| 33 | Earthquake resistant | 4 | 5 | 6 | 1 | 2 | 18 | 0.020455
| 34 | Security and surveillance | 7 | 6 | 8 | 3 | 2 | 26 | 0.029545
|  |  | Total |  |  |  |  | 880 | 1

## References
REFERENCES
Adelaide Street North Underpass ¦ City of London. (n.d.-b). https://london.ca/projects/adelaide-street-north-underpass Law Document English View. (2018, November 19). Ontario.ca. https://www.ontario.ca/laws/regulation/910213 Module 10 (PowerPoint Slides). FanshaweOnline. https://www.fanshaweonline.ca/d2l/le/content/1348668/viewContent/11567375/View Hometown Structures (n.d.): How big is a 2-car garage? https://www.hometownstructures.com/blog/how-big-is-a-2-car-garage/ MedPlus Health (2018): 5 Essential home modifications for making a home wheelchair accessible. https://www.medplushealth.ca/blog/5-essential-home-modifications-for-making-a-home-wheelchair-accessible/ Kelly Scherr (March 29, 2022): Report to Planning and Environment Committee: https://pub-london.escribemeetings.com/filestream.ashx?DocumentId=90864. Noel Hayes (2024): MGMT-6062-(01)-24W: Module 11 Individual Quality Report: What's the Difference Between Requirements and Specifications? : https://www.fanshaweonline.ca/d2l/le/content/1558568/viewContent/14069210/View Noel Hayes (2024): MGMT-6062-(01)-24W: Module 11 Individual Quality Report: John Spacey( sep3, 2023),Requirements vs Specifications: https://www.fanshaweonline.ca/d2l/le/content/1558568/viewContent/14069210/Viewv McQueen, C. (2022): Module 10 (PowerPoint Slides). FanshaweOnline. https://www.fanshaweonline.ca/d2l/le/content/1348668/viewContent/11567375/View The Charlotte Observer (2022): Achieve ultimate protection with the best waterproof paints. https://www.charlotteobserver.com/reviews/waterproof-paint/