## Slide 1: MGMT 6055 Project Scope & requirements
Lawrence Kinlin School of Business
Module 3
Notes: Content for slides in this PPT file is drawn significantly from PMBOK, 6th edition, published by PMI (required text for this course)

## Slide 2: Learning Objectives
Review from last module:
  Putting a Project Idea on Paper: Statement of Work
  Authorizing the Project to Begin: Project Charter
Project Life Cycles, Triple Constraints
Develop Project Management Plan
Scope Management Knowledge Area
Plan Scope Management:
  RACI charts
Notes: Image Source: https://www.google.com/url?sa=i&rct=j&q=&esrc=s&source=images&cd=&cad=rja&uact=8&ved=2ahUKEwiM8cerhrbaAhXr54MKHX1qAM0QjRx6BAgAEAU&url=http%3A%2F%2Fpm4web.blogspot.com%2F2010%2F11%2F10-tips-for-keeping-momentum-on-web.html&psig=AOvVaw2RpULQXOSFAvWjnDGEa1Uc&ust=1523667462394880

## Slide 3: Statement of Work (SOW)
A narrative description of the work to be completed
Comes from senior management or the project sponsor
One or two page document
From last module…

## Slide 4: The Project Charter
A document that formally authorizes a project (or phase)
It establishes a partnership between the performing organization and requesting organization (external: customer)
Formally initiates the project
Assign a Project Manager
From last module…

## Slide 5: REMINDER TO STUDENTS!
For the mid-term and final exams in this course:
You will NOT need to memorize every input, tool & technique, and output (ITTO) for the processes we learn in each module.
But!
You WILL need to memorize some ITTOs for the exams - they will be highlighted in BLUE FONT in the PowerPoint slides.
If an ITTO is NOT highlighted in BLUE FONT in the course PowerPoint slides, then you are NOT required to memorize it when studying for the mid-term or final exam.
IMPORTANT!
From last module…

## Slide 6
Careful planning is required so that project objectives will be met The Project Manager is responsible for planning

## Slide 7: Project life cycle
Note that some documents are prepared before the project starts. We will learn about many more project documents in this course and in the program…
Figure 1-8 from PMBOK 6th ed. (p. 30)
Notes: Can measure performance against scope statement
Let everyone know what you’re doing and they can agree

## Slide 8: Waterfall vs. Agile project life cycles
Agile (or adaptive, or iterative) projects use a different methodology, with successive planning/execution cycles (you will learn about agile PM later in the PRJ program)
Waterfall projects: Also known as traditional or predictive projects
- Generally sequential
- Project activities are planned at the start and executed as the project progresses
Notes: Source: savaged.wordpress.com
Note: PMBOK 6th edition describes additional categories of project life cycles (see assigned readings)

## Slide 9: Prince2 (Project Management methodology seen in the UK and Europe)
(See Slide Notes)
Notes: Note: Students are not required to study/memorize this diagram. However, they ARE expected to know that PRINCE2 is conceptually different from PMBOK (see videos on next slide). Also, PMBOK is familiar to project managers around the world; PRINCE2 is relatively less common in North America but is more familiar to project managers in the UK and Europe. The first video on the next slide summarizes some key differences between PMBOK and PRINCE2.
Source: https://www.google.ca/url?sa=i&rct=j&q=&esrc=s&source=images&cd=&cad=rja&uact=8&ved=2ahUKEwirsvyN27XaAhUL2IMKHX2VBbAQjRx6BAgAEAU&url=http%3A%2F%2Fwww.davelitten.com%2Fprince2-2017-small-projects%2F&psig=AOvVaw3jn8hHf8fotYfdFdSg2c5p&ust=1523655915495914

## Slide 10: FYI…
If you’re curious about learning the differences between Prince2 and PMBOK, check out these videos!
https://www.youtube.com/watch?v=N67bCigkf_M (4 minutes)
https://www.youtube.com/watch?v=57BpgxZh7FQ (10 minutes)
If you want to learn more about the PMBOK 7th edition (and how it is different from the 6th edition), check out these links! PMI – PMBOK 7th edition Frequently Asked Questions (FAQ)
PMI – Comparing 6th and 7th editions of PMBOK (summary graphic)

## Slide 11: The Triple Constraints
Scope, cost, schedule are different elements of project management, but they are interrelated
FYI: Check out this YouTube video for an Explanation of the Triple Constraints triangle. It’s a fundamental concept in project management...

## Slide 12: Introduction to the Project Management Plan (“The Master Plan”)
Formal, approved document that defines how the project is executed, monitored and controlled.
May be detailed (for smaller projects) or a summary plan with subsidiary plans (for larger projects)
Part of the Project Integration Management knowledge area in PMBOK (not Scope Management) because it applies to more than scope-related processes

## Slide 13: Develop Project Management Plan
Notes: Source: PMBOK 6th edition (PMI) – Figure 4-4, p. 82

## Slide 14: What types of components would you see in a project management plan?
Scope management plan
Cost management plan
Scope management plan
Requirements management plan
Quality management plan
Risk management plan
Procurement management plan
Change management plan
Baselines
Life cycle description
Etc….
Notes: Source: PMBOK 6th edition (PMI) – p. 89

## Slide 15: Project Management Plan – Sample for small project
(FYI)

## Slide 16: Lets talk about Scope Management

## Slide 17: What is Scope and SCOPE MANAGEMENT?
The scope of a project tells you what it is you are creating or building, what it is you are trying to accomplish.
Scope Management is the set of project management processes (a “knowledge area”) concerned with determining and managing what is and what is not included in the project and product.

## Slide 28
THIS IS WHY PROJECT SCOPE NEEDS TO BE MANAGED (every stakeholder must have a shared and precise understanding of what will be produced by the end of the project)
Notes: Source: www.agile-scrum-master-training.com

## Slide 29
SIX scope-related processes (activities) are described in the PMBOK 6th ed. text
Source: PMBOK (6th ed), pg. 130

## Slide 30: Six Scope Processes
Plan Scope Management – How is scope going to be managed for the project?
Collect Requirements – Defining and documenting stakeholder (including client) needs, to meet the project objective
Define Scope - Produce a document (a “Scope Statement”) which is the master blueprint for the project and product
Create Work Breakdown Structure (WBS) – Produce a detailed breakdown of work elements for the project
Validate Scope – Obtain the approval from the client for the deliverables that are produced [Note: In the 4th edition of PMBOK, this process is called ‘Verify Scope’]
Control Scope – Compare actual results to planned results (and investigate/correct variations)
Notes: Collecting rqmt: defining and documenting stakeholder needs to meet the project objective
Define scope: develop a detailed description of the project and product

## Slide 31: Planning Scope Management

## Slide 32: Output: Scope Management Plan
Describes how the scope will be defined, developed, monitored, controlled, and verified
  How will the detailed scope statement be prepared? When will it be created? With what resources? Who will participate in its creation and who will approve it?
  How will the Work Breakdown structure be prepared? When will it be created? With what resources? Who will participate in its creation and who will approve it?
  How will deliverables be accepted? Who determines acceptance criteria? How do we contact them? When will acceptance happen?
  How will requests for changes to scope be handled? Are there forms or procedures that we need to adopt? Who is allowed to approve changes? Are there guidelines or timelines for the process?
  Roles and responsibilities of project team members and relevant stakeholders

## Slide 33: Output: Requirements Management Plan
Describes how the requirements will be identified, analyzed, documented, and managed. will be defined, developed, monitored, controlled, and verified
  How will requirements activities be planned, tracked through the project life cycle, and reported?
  Who will be involved in each of these tasks?
  How are priorities to be determined?
  Roles and Responsibilities

## Slide 34: Roles and Responsibilities
Can be organized into RACI Chart - Responsible, Accountable, Consult, Inform
Understand how these charts are designed AND how they can be used to identify potential problems (see videos next slide)

## Slide 35: RACI Charts
https://www.youtube.com/watch?v=MhowzlmvhlI
3-minute Youtube video about RACI charts…
https://www.youtube.com/watch?v=1U2gngDxFkc
5-minute Youtube video about RACI charts…

## Slide 36: Document flow
SOW (the idea for the project – completed before the project starts)
Project Charter (the document that formally authorizes and initiates the project)
Management Plan(s)
“PROGRESSIVE ELABORATION” (more detail about the project is added as
we proceed from one document to the next)