## WBS Dictionary 1.3.1.3
Project Name: | RFID Implementation for Adidas Warehouse
Work Package ID: | 1.3.1.3
Work Package name: | Purchase
Work Package Description: | Based on previous collected requirement for the project and IT suggestions of the RFI requirements and architecture needed for the project, the purchase of all material for the execution of the project will be made. The deliverable of this work package is obtaining the RFID Labels, Readers,Antennas, data management software and to set up the contract with the RFID specialist who will serve as a consultant of the project.
Assigned to | Kent Brian | Group/Department | IT/ Procurment/ PMO
Date Assgined | 2023-11-21 | Due Date | 2023-11-30
Estimated cost | 111000 | Account Code | ADI-1856
Deliverable | Design and Procurement | Resource Assigned | Project Manager/ IT analyst/ Procurement Analyst